## Slide 1: Taxi Service Outsourcing – Project Charter
Background | Scope | High-Level Risk / Assumptions
Lagos Land Transport in Shell Nigeria needs to move people from one location to another using taxi services. However, service delivery has been less than optimal due to insufficient resources (only 2 vehicles currently) to run the business causing delays and regrets. There is idle time and cost increase in introducing additional taxis though this could improve customer satisfaction. The situation has been further complicated by the recent unfeasible request from vendor for guaranteed demand on weekends with no activity for provision of additional resources. | Initial pilot with Taxi service Extend to adhoc movements to and from office locations for business need. Pick-up and drop-off of personnel on business trips within the taxi service areas of operations. | Vehicle/Asset roadworthiness and integrity from service provider. Compliance and competence of personnel to HSSE & SP CF. Compliance to Labor laws and trade union demands / Legal implications. Availability of taxi service app/asset and network uptime. Assurance of security / background checks of service provider personnel. NAPIMS buy-in
Objectives | Deliverables | Key Activities / Timeline / Estimates
To provide safe outsourced taxi service by 1st Qtr 2020 using a technology driven mobile application solution e.g. Uber, Taxify, etc. To improve Lagos Land Transport service delivery, reliability and performance. | Physical Model/App (to be reviewed with IT) Local requirement and specification (if needed) Change Management Plan Training Support documentation Resourcing (exploratory visit to Uber next week) | Planning, Proposal, PoC and approval 1 Aug 2019 Project Execution 15 Aug – 31 Oct 2019 Parallel run / Business UAT 1 Nov 2019 Knowledge Transfer 2 Jan – 31 Jan 2020 Go-Live & Hypercare 1 Feb – 30 Mar 2020 Project Close-out 31 Mar 2020
Benefits | Costs | Team / Stakeholders
The Outsourced Taxi Service will ensure the following: Better service delivery, reduced delays and improved reliability. Potential 1-yr savings of N3.6mln (F$12k) Improved quality of service. Improved visualisation and display through the Web based application. Better essential transport service availability. Elimination of the need for chargeback and easier cost allocation. |  | Steering / Approvers: Business: ?? IT: ?? Project Resources: ?? Project Team: ???
Dependencies
Resource availability (IT developer).
SN | Activity Detail | Cost ($)
1 | Consultancy | ??
2 | Training | ??
3 | Equipment/Hardware | ??
 | TOTAL | ??

## Slide 2
Savings assuming all risk addressed within tariff (e.g. Uber) = ~N14k per day
This amounts to N3.6mln in 1 year (F$12k) and will increase with increased scope and utilization.