## Asset Risk Visual
Bonga Asset Post Mitigation Risk Visual Q4 2018
TREND in Control & Risk Environment
(from previous quarter)
IMPROVING
STABLE
|  | Lack of OML 118 Lease Renewal & PSC extension | 2011 Oil Spill Litigation Claims | Adverse Fiscal PIB terms signed |  | DECLINING
ACCEPTABILITY (After the
impact of existing actions)
RISK LEVEL IS
ACCEPTABLE
MANAGEMENT OF THE RISK
NEEDS IMPROVEMENT
500m(USD)
|  | Security at Sea/ Terrorism | Unavailability of vessel for IWS | Asset Integrity: Waterflood system leaks (topsides pipelines) |  | MANAGEMENT OF THE RISK
|  | FPSO Suction Pile/ Mooring system reliability | NNPC Cargo Overlift | Water Injection Subsea Pipeline Leakages and Failure |  | NEEDS MAJOR IMPROVEMENT
|  | Loss of well integrity/ capacity | Gas Export Flexi joint Elastomer degredation
|  | WFL-01, WFL-03 Flexi joint Elastomer degredation | Corrosion of small bore pipings |  |  | RISK & ACTIONS
|  | Failure of tree coupler seals | Framo System (HPU and COT) reliability/ availability |  |  | UNDER REVIEW
|  | Oil Spill as a result of future Tandem offloading operation/ flowline leaks | Lagos Supply base Transition
Risk to Physical Security
|  |  | IT Obsolescence |  |  | SHOWS CHANGE
Flare header movement
|  |  | Break out of Hydrogen Scavenger |  |  | NEW RISK
250m(USD)
|  | Unavailability of critical spares | Water injection wells decline/ unavailability | Sewage system blockages / failures |  | Risk Removed or
|  | Sand in the oil processing system | Reliability of critical equipment (HVAC, VRU, Cranes) |  |  | Delegated
|  | Insufficient PW capacity | Water breakthrough in wells earlier than planned, risk to IPSC.
|  | EFL insulation resistivity failure | Bonga Subsea Umbilical Leakages
|  | FMC Subsea Equipment Infant Failures | Unavailability of power turbines on diesel fuel as a result of Upstream filter clogging
|  | Keel Line Isolation Valve Actuator/ Valve failure | Structural and Piping failure due to corrosion
|  | Deferred production of BMIRP due to unavailability of VIEC in the LP separator | LP Separator internal buckling
|  | Chloride induced corrosion crack | Damage to flare tip
Subsea Shallow gas bubbles
COC on cracked weld between COT-4C & WBT-3S
50 m(USD)
LIKELIHOOD
|  | Low | Medium | High
Low
Medium
High
IMPACT

## LOD 1
Mgt System | Assurance Program | Assurance Cordinator | LOD | 2019 | Remarks
OE | Quaterly Asset Risk Review | Aiboni Elohor | LOD 1 | 4/ Year
OU Selected LOD 2 HSSE&SP Assurance | Temporary repair review | Jonathan Amakiri | LOD 1 | Quaterly
OU Selected LOD 2 HSSE&SP Assurance | Emergency Response Drills and Exercises | Aiboni Elohor | LOD 1 | 7/ Month
OU Selected LOD 2 HSSE&SP Assurance | Permit to Work and TRIC Effectiveness Review | Jonathan Amakiri | LOD 1 | 2 / Month
Asset Risk | Physical Conditions Monitoring | Jillis Van Duuren | LOD 1 | 7 / Month
OU Selected LOD 2 HSSE&SP Assurance | Handover (shift/hitch) Reviews | Jonathan Amakiri | LOD 1 | 2 / Month
OU Selected LOD 2 HSSE&SP Assurance | Emergency Response Equipment Inspection | Jonathan Amakiri | LOD 1 | 2 / Month
Asset Risk | DROS Hazard Hunt | Efeoku Jegbefume | LOD 1 | 2 / Month
OU Selected LOD 2 HSSE&SP Assurance | Secondary Chnages Close out review (Management of Change) | Jonathan Amakiri | LOD 1 | 1/ Month
OU Selected LOD 2 HSSE&SP Assurance | Medical Equipment Inspection | Aiboni Elohor | LOD 1 | 1 / Month
OE | Operations Integrity Reviews / Assessment (Review of Operational registers) | Jonathan Amakiri | LOD 1 | 1 / Month
OE | Risk Assesment Quality Reviews | Efeoku Jegbefume | LOD 1 | 1/ Month
Asset Risk | Work order close out Review | Jonathan Amakiri | LOD 1 | 1/ Month
Asset Risk | Flex Joint Visual Inspection | Narendranath Ramaiah | LOD 1 | 1/ Week
Asset Risk | H2S Monitoiring | Leo Chiejina | LOD 1 | Daily
Asset Risk | Well Integrity review | Edidth Mbanefo | LOD 1 | 1/ Month
Asset Risk | Process Safety Visualisation (Data Integrity and Usage) | Efeoku Jegbefume | LOD 1 | 1/ Month
Asset Risk | Cumulative Risk Assessment | Efeoku Jegbefume | LOD 1
OE/AMS | Document Review | Gafar Rasheed | LOD 1 | 1/ Month
OE | HSSE Case review (HSSE Critical Poisitions) | Vincent Jegbefune | LOD 1 | March
OE | Maintainance supervisor daily worksite review | Bonga OIM | LOD 1 | Daily
OE | AIPSM Review | Efeoku Jegbefume | LOD 1 | Monthly
OE | FLBM Review | Ogbe Mejebi | LOD 1 | Monthly
OE | FSR Review | George Chukwuma | LOD 1 | Weekly
HSSE&SP Assurance | Contract Management review - Homble Contact Performance review | Van Duuren Jillis | LOD 1 | July
AMS | Process Health Check - Integrated Activity Planning & Scheduling (IAPS) | Yemi Asaolu | LOD 1 | Q4 2019
AMS | Process Health Check - Manage Equipment Care (MEC) | Van Duuren Jillis | LOD 1 | Q4 2019
AMS | Process Health Check - Manage Threats and Opportunities (MTO) | Van Duuren Jillis | LOD 1 | Q4 2019
AMS | Process Health Check - Ensure Safe Production (ESP) | Osarode Iduoriyekemwen | LOD 1 | Q4 2019
AMS | Process Health Check - Well, Reservoir and Facility Management (WRFM) | Yemi Asaolu | LOD 1 | Q4 2019
| Bonga Regulatory Permits review | Efeoku Jegbefume | LOD 1 | Monthly
OE | Management Review | Elohor Aiboni | LOD 2 | Oct
OU Selected LOD 2 HSSE&SP Assurance | SCiN PTW LoD 2 Review LOD2 | Irene | LOD 2 | Q2 2019
OE | Process Safety health check review | Efeoku Jegbefume | LOD 2 | Nov
OU Selected LOD 2 HSSE&SP Assurance | Bonga FPSO Lifting - Assurance Audit | Huseyin Ozen/Utibe Akpanudo | LOD 2 | June
Statutory | DPR Statutory Annual Facility inspection | Efeoku Jegbefume | LOD 2 | June/Nov
| DPR HSE Audit/ OSCP | Efeoku Jegbefume | LOD 2 | Aug
OE | OPITO CMS MONITORING AUDIT AUDIT | Alex Omeh | LOD 2 | Mar
OE/ Risk | Internal Well Integrity Self health Check | Edith Mbanefo | LOD 2 | June
OU Selected LOD 2 HSSE&SP Assurance | Business Maritime Process Model (MPM) Review | Zuofa Tibiebiowei | LOD 2 | 2019-03-01
OU Selected LOD 2 HSSE&SP Assurance | Shell Maritime Business Review | Zuofa Tibiebiowei | LOD 3 | 2019-09-01
OU Selected LOD 2 HSSE&SP Assurance | Action close out effectiveness Review LOD1 - 3 including Exceptions BAL and 2016/7 Group LOD3 HSSE SP CF Audits. | Efeoku Jegbefume | LOD 2 | 2019-09-01
OU Selected LOD 2 HSSE&SP Assurance | SCiN Process Safety Review (PSR) Fix Program Review | Efeoku Jegbefume | LOD 2 | 2019-10-01
OU Selected LOD 2 HSSE&SP Assurance | SCiN Environmental Management Plan (EMP) effectiveness Review | Efeoku Jegbefume | LOD 2 | TBA
OU Selected LOD 2 HSSE&SP Assurance | ISO 14001:2015 BSI Audits | Efeoku Jegbefume | LOD 2 | 2019-12-01
OU Selected LOD 2 HSSE&SP Assurance / OE | SCiN Green House Gas (Stage 2 & 1) Audits | Efeoku Jegbefume | LOD 2 | Mar/ Nov 2019
OU Selected LOD 2 HSSE&SP Assurance | SCiN Internal GHG Review | Efeoku Jegbefume | LOD 2 | Q1/Q3 2019
OU Selected LOD 2 HSSE&SP Assurance | Contractor HSE Management Review | Pius Okeadinma | LOD 2 | 2019-07-01
OE | Materials Management Review | Elohor Aiboni | LOD 2 | 2019-04-01
OE/ Risk | Corrosion Mgt Review | Van Duuren Jillis | LOD 2 | 2019-07-01
OE/ Risk | Chemical Mgt System Review | Aiboni Elohor | LOD 2 | 2019-09-01
Asset Risk | Regulatory permit audit review | Aiboni Elohor | LOD 2 | 2019-09-01
Statutory | Lloyds - SCE class verification survey | David Ojako | LOD 2 | 2019-10-01
OE | Hardware Barrier assesment | David Ojako | LOD 2 | TBA
OE/ Risk | Asset Register/ BOM's review | Aloys Mutisya | LOD-2 | 2019-09-01
Asset Risk | Maintainace Strategy Review | Van Duuren Jillis | LOD-2 | Feb
HSSE&SP Assurance | Process Safety Actions Effectiveness Review | Efeoku Jegbefume | LOD-2 | 2019-12-01
OE | PSF Implementation and reporting assessment | Efeoku Jegbefume | LOD-2 | Oct
OE | Passing Valves Assesment | Jonathan Amakiri | LOD-2 | 2019-02-01
OE/AMS | Risk review of the OE to AMS transition | Elohor Aiboni | LOD-2 | 2019-01-01
OE/AMS | Deviation Review | Van Duuren Jillis | LOD-2 | 2019-04-01
| Assurance Program | Assurance Cordinator | LOD | DATE
| Nigerian Oil Spill response | Ojo Afolabi | LOD-3 | JULY
| HRAA Nigeria | Ojo Afolabi | LOD-3 | MAY
| Nigeria pre award & post award contract management action follow up incl ABC | Ojo Afolabi | LOD-3 | SEPT
| Nigeria well delivery | Ojo Afolabi | LOD-3 | OCT
| Nigeria SEPCiN Transport (Air, Land and Marine) | Ojo Afolabi | LOD-3

## LOD 2
Mgt System | Assurance Program | Assurance Cordinator | LOD | TENTATIVE DATES
OE | Management Review | Elohor Aiboni | LOD 2 | Oct
OU Selected LOD 2 HSSE&SP Assurance | SCiN PTW LoD 2 Review LOD2 | Irene | LOD 2 | Q2 2019
OE | Process Safety health check review | Efeoku Jegbefume | LOD 2 | Nov
OU Selected LOD 2 HSSE&SP Assurance | Bonga FPSO Lifting - Assurance Audit | Huseyin Ozen/Utibe Akpanudo | LOD 2 | June
Statutory | DPR Statutory Annual Facility inspection | Efeoku Jegbefume | LOD 2 | June/Nov
| DPR HSE Audit/ OSCP | Efeoku Jegbefume | LOD 2 | Aug
OE | OPITO CMS MONITORING AUDIT AUDIT | Alex Omeh | LOD 2 | Mar
OE/ Risk | Internal Well Integrity Self health Check | Edith Mbanefo | LOD 2 | June
OU Selected LOD 2 HSSE&SP Assurance | Business Maritime Process Model (MPM) Review | Zuofa Tibiebiowei | LOD 2 | 2019-03-01
OU Selected LOD 2 HSSE&SP Assurance | Shell Maritime Business Review | Zuofa Tibiebiowei | LOD 3 | 2019-09-01
OU Selected LOD 2 HSSE&SP Assurance | Action close out effectiveness Review LOD1 - 3 including Exceptions BAL and 2016/7 Group LOD3 HSSE SP CF Audits. | Efeoku Jegbefume | LOD 2 | 2019-09-01
OU Selected LOD 2 HSSE&SP Assurance | SCiN Process Safety Review (PSR) Fix Program Review | Efeoku Jegbefume | LOD 2 | 2019-10-01
OU Selected LOD 2 HSSE&SP Assurance | SCiN Environmental Management Plan (EMP) effectiveness Review | Efeoku Jegbefume | LOD 2 | TBA
OU Selected LOD 2 HSSE&SP Assurance | ISO 14001:2015 BSI Audits | Efeoku Jegbefume | LOD 2 | 2019-12-01
OU Selected LOD 2 HSSE&SP Assurance / OE | SCiN Green House Gas (Stage 2 & 1) Audits | Efeoku Jegbefume | LOD 2 | Mar/ Nov 2019
OU Selected LOD 2 HSSE&SP Assurance | SCiN Internal GHG Review | Efeoku Jegbefume | LOD 2 | Q1/Q3 2019
OU Selected LOD 2 HSSE&SP Assurance | Contractor HSE Management Review | Pius Okeadinma | LOD 2 | 2019-07-01
OE | Materials Management Review | Elohor Aiboni | LOD 2 | 2019-04-01
OE/ Risk | Corrosion Mgt Review | Van Duuren Jillis | LOD 2 | 2019-07-01
OE/ Risk | Chemical Mgt System Review | Aiboni Elohor | LOD 2 | 2019-09-01
Asset Risk | Regulatory permit audit review | Aiboni Elohor | LOD 2 | 2019-09-01
Statutory | Lloyds - SCE class verification survey | David Ojako | LOD 2 | 2019-10-01
OE | Hardware Barrier assesment | David Ojako | LOD 2 | TBA
OE/ Risk | Asset Register/ BOM's review | Aloys Mutisya | LOD-2 | 2019-09-01
Asset Risk | Maintainace Strategy Review | Van Duuren Jillis | LOD-2 | Feb
HSSE&SP Assurance | Process Safety Actions Effectiveness Review | Efeoku Jegbefume | LOD-2 | 2019-12-01
OE | PSF Implementation and reporting assessment | Efeoku Jegbefume | LOD-2 | Oct
OE | Passing Valves Assesment | Jonathan Amakiri | LOD-2 | 2019-02-01
OE/AMS | Risk review of the OE to AMS transition | Elohor Aiboni | LOD-2 | 2019-01-01
OE/AMS | Deviation Review | Van Duuren Jillis | LOD-2 | 2019-04-01

## LOD 3
SIA
Assurance Program | Assurance Cordinator | LOD | DATE
Nigerian Oil Spill response | Ojo Afolabi | LOD-3 | JULY
HRAA Nigeria | Ojo Afolabi | LOD-3 | MAY
Nigeria pre award & post award contract management action follow up incl ABC | Ojo Afolabi | LOD-3 | SEPT
Nigeria well delivery | Ojo Afolabi | LOD-3 | OCT
Nigeria SEPCiN Transport (Air, Land and Marine) | Ojo Afolabi | LOD-3

## EA (hidden)
EA Assurance Program | Assurance Cordinator | Frequency | Cost ($ Per assesment) | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
Process Safety Review | Wong Wai-Kiong | 5 yearly |  | 2020: Nov; 2025: Nov
HSE Case review | Wong Wai-Kiong | 5 yearly |  | 2019: Feb; 2024: Feb
5 yearly Re-Hazop | Wong Wai-Kiong | 5 yearly |  | 2021: Jan
MOC sustainanability | Umelo Chukwumemeka | 3 yearly
ORIP Sustainability | Peter Idoko
GHG Audit | Israel Ezenwaka/ Funmi | 6 Monthly |  | Mar/Oct | Mar/Oct | Mar/Oct | Mar/Oct | Mar/Oct | Mar/Oct | Mar/Oct | Mar/Oct | Mar/Oct
Offices, Accommodations and FLBs (UIO) | Irene
SCiN PTW LoD 2 Review | Irene
SCiN HSSE Data Verification LoD-2 Review | Irene
Nigeria: International Ship & Port Security (ISPS) | Irene
Bonga FPSO & Sea Eagle FPSO Insurance Survey | Irene
OI Sustainability | Ojikutu Mukaila
MIE MM Sustainability | Kalu Eleanya
MIE Calculative sustainability | Victor Anats | 3 yearly |  | 2018: July; 2021: July; 2024: July
WRFM health Check | Erhahon Lucky | 2 yealy |  | 2017: May; 2019: May; 2021: May; 2023: May; 2025: May
Shell Marine Business Review | Robert Goodwin |  |  | 2019: June; 2022: June
ISO 140001 assesment | John Jia
PTW Level 1 Audit | John Jia
PTW Level 2 Audit | John Jia
PTW Level 3 Audit | John Jia
PTW Level 4 Audit | John Jia | 2 weekly
HSE case calculative assesment
Environmenatl monitoring |  | Weekly
HSSE & SP Control Frame work audit | Adigun Oladele |  |  | 2019: June
Hard ware Barrier assesmnt | David Ojako | 2 Yearly |  | 2017: June - Aug; 2019: June - Aug; 2021: June - Aug; 2023: June - Aug; 2025: June - Aug
NIMASA cargo ship safety equipment and Radio certification surveys | David Ojako | Yearly | Yearly | June | June | June | June | June | June | June | June | June
Lloyds - SCE class verification survey | David Ojako | Yearly | Yearly | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov
Llyods - class endorsement survey | David Ojako | Yearly | Yearly | June | June | June | June | June | June | June | June | June
Process Safety health check |  | Yearly
EA FPSO Lifting - Assurance Audit | Kevin Allan | 6 monthly |  | Apr/Oct | Apr/Oct | Apr/Oct | Apr/Oct | Apr/Oct | Apr/Oct | Apr/Oct | Apr/Oct | Apr/Oct
Lifting and Hoisting Review | Kevin Allan
Refuge Pressurisation checks
OPITO monitoring audit | Alex Omeh
Waste Management Audit | John Jia
Note on E21: Bolanle.Adediran: Travel Logistics (Accomodation inclusive)