## Sheet1
EQUIPMENT PERFORMANCE IMPROVEMENT PROCESS
SUSTAIN PERFORMANCE - Establish Supervisor "Gemba" walk. - Establish Periodic equipment performance review. - Use ORIP process to initiate RCA and eliminate root cause of future failures.
MAKE IT EASY TO OPERATE - Close equipment specific staff competence gaps - Develop in-house troubleshooting skills - Institute Visual Controls to make it easy to spot changes in equipment operating conditon. - Put process in place to make rigt quantity of spares available in stock - Vendor Support Contract in place - Manuals and drawings available on site. 8. Clarify roles and responsibility.
DEVELOP STANDARD OF CARE - Estabilsh standard of cleanliness - Establish daily inspection routines - Make changes to PM routines if required - Enforce PM compliance - Establish level of spares stock required 7. Implement changes to maintenance routines
RESTORE TO "AS NEW" CONDITION Conduct Autonomous Care Workshop to Improve Equipment condition: - Clean equipment - Inspect for defects (if equipment is not ovehauled). - Rectify defects. 6. replace engine auxillaries that are ientified for change
RESTORE TO "AS DESIGNED" CONDITION - Effect repairs of known failures as campaign. - Overhaul equipment with OEM support - Carry out modification to equipment to restore operations to within envelope. 4. Carry out Engine major overhaul if due 5. Carry out Fluid end Inspection if due 6. Implement RCA Findings from step 2
ROOT CAUSE OF POOR PERFORMACE Conduct Reliability Review - PM History - CM History - Mean Time to Repair (MTTR) Analysis - impact of spares availability - Impact of vendor availability - Equipment specific Competence gaps - Document gaps (Manuals, drawings, etc.) - Changes in Operating conditions / envelope - Equipment / Component Obsolesence - Review report of past RCAs on equipment - Develop Action Plan - Cost Estimates 2. Develop action plan
KICK OFF: CASE FOR CHANGE & ToR Quantify loses to date and value of investment in improvement - Cost - Availability - Production Losses Nominate improvement team - Improvement Team kick off - Review improvement plan - Develop integrated schedule 1. Clarify Scope
ACTION PARTIES
ACTIVITY DURATION | 1 Weeks | 2 WEEKS | 3 MONTHS | 1 MONTH | 1 Month | 1 MONTH | On-going
PROJECTED IMPROVEMENT | BASELINE PERFORMANCE | ESTABLISH PERFORMANCE GAP | EQUIPMENT OUT | START-UP & RAMP UP | MAINTAIN PERFORMANCE | MAINTAIN PERFORMANCE | SUSTAIN PERFORMANCE - Establish Supervisor "Gemba" walk. - Establish Periodic equipment performance review. - Use ORIP process to initiate RCA and eliminate root cause of future failures.

## Solution Space
SOLUTION SPACE AS PROPOSED BY RELIABILITY REPORT
| Equipment Overhaul (OEM) | Equipment Modification | Autonomous Care Workshop | Sustain Performance
Inlet Gas Properties
Compressor Performance
Outlet Gas Properties
Engine Fuel Gas Properties
Engine Performance
Ancillary Equipment
Compressor & Engine Controls
Operation & Maintenance Instruction
O&M Competncies
O&M Competncies

## Sheet3
Action | Duration | Status (Not started/in Progress/Completed
1. Clarify Scope | 1 Week
2. Develop action plan | 2 Weeks
4. Carry out Engine major overhaul if due | 3 months
5. Carry out Fluid end Inspection if due | 3 Months
6. Implement RCA Findings from step 2 | 3 Months
6. replace engine auxillaries that are ientified for change | 1 Month
7. Implement changes to maintenance routines | 1 Month
8. Clarify roles and responsibility. | 1 Month