## FS Cadence
L1……….L2…..…..L3…….…..L4…..…...L5
| S/No. | ISSUE | JUSTIFICATION | % Occurrence | RCA STATUS | TIMELINE FOR EXECUTION/ACTION PARTY |  |  | COST OF EXECUTION ($) | STATUS
[6 empty] | START DATE | END DATE | ACTION PARTY
Non-Technical Risks | 1 | Put a firm plan in place for dedicated crew | Ensure discipline supervisors have dedicated crew for daily trips to FS | 0 | No | 10.11.2017 | 15.12.2017 | Adebisi/Terfa | DIY | No firm plan exists
| 2 | Put a firm plan in place for early start and late return | Early start will ensure quick recovery and early retuirn will reduce fatigue and feeding issues | 0 | No | 10.11.2017 | 15.12.2017 | Oluseyi/Goodi | DIY | No firm plan exists
| 3 | Improve GSF Gunboat reliability- ASA to share implementation plan | Reliability have increased however there is room for improvement | 0 | No | 10.11.2017 | 30.11.2017 | Ibitoye/Okpom | DIY | Effort is in place- Ibitoye to share plan
| 4 | Improve/replace Passenger boat for increased reliability | Mail has been sent for replacement | 0 | No | 16.11.2017 | 15.12.2017 | Harcourt/Jonathan | Contract Enforcement | Harcourt pursuing seatruck as replacement
| 5 | Revamp Soku Community Power | Failed generator not yet replaced | 0 | No | 16.11.2017 | 31.12.2018 | Chibs Anyim | F$1,000,000:00 | Stalled at NAPIMS, to purchase through GMoU. Val to Enage Anyim on firm plans
| 6 | Comply to no flares policy- by revamping AG booster compressor | Efforts to improve reliability of the AG Booster compressor | 0 | No | 16.11.2017 | 30.06.2018 | Olayinka Dada | $YYYY | In AM cadence. Yinka to share plan for booster compressor
SHORT TERM | 1 | Install UPS and commission (Ref Wave card no XXXX) | This is to prevent the sudden loss of power to critical control infrastructure in the FAR. | 6.33 | No | 16.11.2017 | 31.03.2018 | Aminu Sani/Olabode Adeleye | 6557.377 | Now In PUM cadence. Floor collapsed. Require scoping, repairs and completion of activity. Plan is to use asset engineering who are currently mobilized in the location
| 2 | Complete installation of AMF panel and commission | There is a charge controller challenge that is unresolved for automation | 0 | No | 16.11.2017 | 30.03.2018 | Aminu Sani/Olabode Adeleye | DIY | Recent visit by maintenanace support has not resolved the issue
| 3 | Procure new PRM for calibration of field instrument | Plant Resouce Manager is a system required for instrument calibration (Escalated for AM help) | 35.44 | No | 16.11.2017 | 20.12.2017 | Sam Adejumo/Oluseye Philips/Ogubio | 12000 | DIY is preffered approach, however cost is $12,000 EWS and Engineering work station to be replaced. Options to be explored is configuring Dell machines expected from Onne Warehouse to solve this issue. PACO team/Dominic Nwasinachi can handle this
| 4 | Service and overhaul Export Pumps 1 & 2 | Engine Changeout and Overhauls on EP2 is completed, Outstanding items in EP1 due to be completed are (1) Complete installation of discharge pressure transmitter and (2) Confirm workability of installing engine speed cable connection between the pump and the FAR | 11.4 | Yes | 15.12.2017 | 15.01.2018 | Sam Adejumo/Oluseye Philips/Ogubio | DIY | Source for right transmitter and install
| 5 | Restore Tetra communication signal in the Field Auxilliary Room when door is closed | Once the control room door is closed, tetra signal disappears on the hand-held radio. | 0 | No | 01.01.2017 | 28.02.2018 | Eka Ituen/Abolo, Inyengiyikabo | 1637.7049 | Awaiting scoping by IT Operations
| 6 | Carry out a vibration study for static and rotating equipment in the flow station | we have noticed increased vibration in the flow station after the production volumes increased | 0 | No | 16.11.2017 | 21.12.2017 | Foster Ezenwelu | DIY
| 7 | Procure new EWS system EWS- Engineering Work station | Current system indicates blue screen and is indicative of system failure | 0 | No | 16.11.2017 | 20.12.2017 | Sam Adejumo/Oluseye Philips/Ogubio | 12000 | DIY is preferred approach, however cost is $12,000 EWS- Engineering work station to be replaced. Options to be explored is configuring Dell machines expected from Onne Warehouse to solve this issue. PACO team/Dominic Nwasinachi can handle this
| 8 | Install new 45PIZA112 transmitter on the export line | This a significant Bad Actor in 2017 YTD dump. This may be from third party activity or spurious signal | 15 | No | 16.11.2017 | 23.12.2017 | Sam Adejumo/Oluseye Philips/Ogubio | DIY | In stock
MEDIUM TERM | 1 | Procure two nos of speed controller of the export pumps | Mean time to installation is high. Should be treated like critical spare | 0 | No | 16.11.2017 | 30.05.2018 | Sam Adejumo/Oluseye Philips/Ogubio | 14000 | Coded, to be placed on order.
| 2 | Procure power wizard spare for diesel generator | This is necessary after the power wizard fix | 0 | No | 16.11.2017 | 30.05.2018 | Sam Adejumo/Oluseye Philips/Ogubio | 1475.4098 | WO raisded for maintennace execution team for material order
| 3 | Procure five spares of LCP 100 and install chinese cap for MSDVs | The local control panel has frequent failure. Just got approval for two units from hot desk. We need minmum of 5 nos as spares. In addition, we need to build a shade to prevent water ingress into module | 0 | No | 16.11.2017 | 30.05.2018 | Sam Adejumo/Oluseye Philips/Ogubio | 2500 | To check if coded and placed on order.
| 4 | Procure 6 Masoneilan Field view Positioners for MSDVs | Mean time to installation is high. Should be treated like critical spare | 0 | No | 16.11.2017 | 30.05.2018 | Sam Adejumo/Oluseye Philips/Ogubio | 12000 | To check if on order
| 5 | Procure two core processors for the coriolis meter runs 1&2. | 45FQR 001 & 002 are not available | 0 | No | 16.11.2017 | 30.05.2018 | Sam Adejumo/Oluseye Philips/Ogubio | 10000 | Core processor been coded. Ordering to be completed ASAP. Plan in progress for purchase of Chinese caps to help improve ingress protection.
| 6 | Procure four nos spare vibration switch for export pumps | There's need to procure and calibrate additional vibration switches due to increased vibration observed in the flow station | 0 | No | 16.11.2017 | 30.05.2018 | Sam Adejumo/Oluseye Philips/Ogubio | 2280 | Maintenance execution team to be engaged for this effort
| 7 | Identify defective Fire & Gas Detector, Procure new ones and replace | Carry out PM campaign on the F7G systems. Identify defective units, purchase and install. Fire and Gas trip alarms have contributed to a significant number of trips. | 5.06 | No | 16.11.2017 | 30.06.2018 | Sam Adejumo/Oluseye Philips/Ogubio | 9000 | Coded, to be placed on order.
| 8 | Repair defective Instrument Air Compressor C6801 to ensure N+1 philosophy | For N+1 availability, procurement of a module and cooler | 0 | No | 16.11.2017 | 30.06.2018 | Shina Akinjagunla/ Andrew Okiomah | 11358.71 | Cooler cost expected
MEDIUM TERM with MT-IAP REQUIREMENT | 1 | Carry out weldolet repairs on W/26 ligament valve | This is subject to vibration study, however may be indication of increased vibration | No | No | 16.11.2017 | 31.03.2018 | Sam Adejumo/Oluseye Philips/Ogubio | 3278.6885 | Shutdown opportunity to be captured in MT-IAP
| 2 | Carry out replacement of MSDVs | IP rating is IP68 however water ingress, install two newly delivered MSDVs | 5.06 | No | 15.12.2017 | 31.03.2018 | Sam Adejumo/Oluseye Philips/Ogubio | DIY | Expected on site with milk run on 14th Nov SD opportunity to be captured in MT-IAP
| 3 | Carryout focused PM campaign on level control valves | Station trips on high level and control system failures | 8.86 | Yes | 01.12.2017 | 31.03.2018 | Sam Adejumo/Oluseye Philips/Ogubio | DIY | Shutdown opportunity to be captured in MT-IAP
| 4 | Service and overhaul H, LP and surge vessel backpressure controllers |  | 7.6 | No | 16.11.2017 | 31.03.2018 | Sam Adejumo/Oluseye Philips/Ogubio | DIY | Shutdown opportunity to be captured in MT-IAP
LONG TERM | 1 | Create a daily script for printing daily production ticket | For month-end third party reconciliation purposes. We often lose cash when we cant properly account for produced volumes | 0 | No | 15.01.2017 | 31.03.2018 | Sam Adejumo/Oluseye Philips/Ogubio | DIY | Configuration to be completed when EXAQUANTUM is available. Configuration to be done in-house.
| 2 | Implement auto functionality of Flare Knockout vessel (6601) FLKO | 1. A design review is required for the implementation of auto level control function on the flare knock out and fuel gas scrubber vessel. 2.To carry out joint team to investigate and resolve failure to start/stop of FLKO pumps. | 0 | No | 15.01.2018 | 30.06.2018 | Sam Adejumo/Oluseye Philips/Ogubio | 6000 | INTECH to Implement auto function,as the original design at project phase was not fully implemented by ROCI. Shut-down required for implementation. 3days work by the vendor.
| 3 | Install additional Export pump | Extra pump required for gross volume of 15,000bbls/d to maintain N+1 | 0 | No | 15.01.2019 | 30.06.2018 | Val Okwonkwo/Yinka Dada | 200000 | Val and Yinka to get cost update
| 4 | Put Flowstation to run on Auto (Design issues?) | Process engineer to initiate a study on how to achieve this ambition | 0 | No |  |  |  |  | Akaka (BI) advises this should be a separate initiave has the concept is vague
|  |  |  | 94.75 |  | Total Implementation cost (This excludes non-technical cost) DIY is preferred approach for PRM & EWS systems purchase however cost of $12,000 each is added |  |  | 304087.8903
[9 empty] | 104087.8903 | Without export pump
[9 empty] | 80087.8903 | Without PRM & EWS