## Rigless
| FIELDS | Well Code | Themes | Detailed Scope | RECEIVED MER TEST RESULTS |  |  | CARRY OUT DETAILED REVIEW, FMT TEAM ANALYSIS |  |  | FIELD IMPLEMENTATION OF BEAN UP OPPORTUNITIES
[5 empty] | Start | End | Action Party | Start | End | Action Party | Start | End | Action Party
3 | OTUMARA | OTUM035S, OTUM030L | Rigless | 1. Design and issue MER test Plan 2. Receieve MER test results 3. Carry out detailed review & analysis of the MER tests results 4. Calibrate well performance model to re-validate identified opportunities 5. Carry out further analysis with the Otumara production creaming curve to evaluate new rates and AG rates against compressor capacity constriant 6. Shaere execution sequence with programmer and operations. 7. Implement bean up opportunities and test intervals 8. Report gains | 2019-04-12 | 2019-04-12 | Somtochukwu Odumodu | 2019-04-12 | 2019-04-15 | Erasmus Nnanna / Somtochukwu Odumodu / Otugeme Stanley | 2019-04-15 | 2019-04-29 | Oyebode Oyedele / Agbaje Taiwo / Usin Effiong