## Sheet1
# | Team | Days in current maturity level | Next L-gate date | Name | Maturity level | Initiative owner | Weekly status | Plan L1 | Plan L2 | Plan L3 | Plan L4 | Plan L5 | Total lifecycle Savings (Plan) | SPDC - Total lifecycle Savings (Plan) | SNEPCO - Total lifecycle Savings (Plan) | Total lifecycle FCF USD (Plan) | SPDC - Total lifecycle FCF USD (Plan) | SNEPCO - Total lifecycle FCF USD (Plan) | Total lifecycle Invest USD (Plan) | Total lifecycle Inventory reduction (Plan) | Total lifecycle Production increase (Oil) (kb/d) (Plan) | Total lifecycle Production increase (Gas) (MMscf/d) (Plan) | Total lifecycle FTE (Plan) | Total lifecycle Savings (Actual) | SPDC - Total lifecycle Savings (Actual) | SNEPCO - Total lifecycle Savings (Actual) | Total lifecycle FCF USD (Actual) | SPDC - Total lifecycle FCF USD (Actual) | SNEPCO - Total lifecycle FCF USD (Actual) | Total lifecycle Invest USD (Actual) | Total lifecycle Inventory reduction (Actual) | Total lifecycle Production increase (Oil) (kb/d) (Actual) | Total lifecycle Production increase (Gas) (MMscf/d) (Actual) | Total lifecycle FTE (Actual) | Total current year Savings (Plan) | SPDC - Total current year Savings (Plan) | SNEPCO - Total current year Savings (Plan) | Total current year FCF USD (Plan) | SPDC - Total current year FCF USD (Plan) | SNEPCO - Total current year FCF USD (Plan) | Total current year Invest USD (Plan) | Total current year Inventory reduction (Plan) | Total current year Production increase (Oil) (kb/d) (Plan) | Total current year Production increase (Gas) (MMscf/d) (Plan) | Total current year FTE (Plan) | Total current year Savings (Actual) | SPDC - Total current year Savings (Actual) | SNEPCO - Total current year Savings (Actual) | Total current year FCF USD (Actual) | SPDC - Total current year FCF USD (Actual) | Remark | 2019-03-28 | Comments
12684 | CENTRAL | 212 | 2019-10-31 | Initial completion of KOCR 41 and laying of flowlines | L2: Feasibility proven, prioritized for planning | Cordelia Ikpera | On track | 2018-09-30 | 2019-04-30 | 2019-10-31 | 2021-09-30 | 2021-12-16 | [39 empty] | Close out TA2 document Review comments | L3,L4 and L5 change aligned with emerging STDWS
12685 | CENTRAL | 212 | 2019-10-31 | Initial completion of GBAR 03 and laying of flowlines by Oct 2019 | L2: Feasibility proven, prioritized for planning | Cordelia Ikpera | On track | 2018-09-30 | 2019-04-30 | 2019-10-31 | 2021-01-31 | 2021-04-03 | [39 empty] | 1. Provide agreed delivery plan | L3,L4 and L5 change aligned with emerging STDWS
12686 | CENTRAL | 212 | 2019-10-31 | Initial completion of GBAR 27 and laying of flowlines | L2: Feasibility proven, prioritized for planning | Cordelia Ikpera | On track | 2018-09-30 | 2019-04-30 | 2019-10-31 | 2021-04-30 | 2021-07-01 | [39 empty] | 1. Provide agreed delivery plan | L3,L4 and L5 change aligned with emerging STDWS
12687 | CENTRAL |  |  | Initial completion of EPU 05 and laying of flowlines | L0: Idea registered | Cordelia Ikpera | On track | [43 empty] | Now with PTD |  | Removed, transfred to PTD
12713 | CENTRAL | 130 | 2019-11-30 | Install 6-inch Bulk-Line, install PBV and hook up BONT002L and 002S by NOV 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-07-01 | 2018-07-31 | 2018-12-08 | 2019-11-30 | 2021-12-31 |  |  |  | 2632.66 | 2632.66 | [20 empty] | 2632.66 | [13 empty] | 1.Provide agreed delivery plan in view of BNAG debottlenecking | On track
12714 | CENTRAL | 330 | 2019-08-20 | Lay flowline & install CCU on BONN030T by August 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-12-15 | 2018-01-18 | 2018-12-14 | 2019-08-20 | 2019-09-17 |  |  |  | 2.847 | 2.847 |  |  |  | 4.55 | [16 empty] | 1.095 |  |  |  |  | 1.75 | [8 empty] | 1. Confirm CWI readiness
16203 | CENTRAL | 20 |  | NOG: Bonny NAG debottlenecking to increase production by 100MMscf/d by June 2019 | L0: Idea registered | Cordelia Ikpera | On track | [45 empty] | Removed, manged by Asset Integrity
12700 | CENTRAL | 62 | 2019-10-30 | Integrity Workover of NUN RIVER 007 | L2: Feasibility proven, prioritized for planning | Cordelia Ikpera | On track | 2019-01-25 | 2019-03-28 | 2020-10-30 | 2021-05-15 | 2021-07-30 | [39 empty] | 1.Provide agreed delivery plan in alignment with new sequence 2. Update proposal post Well Endorsement
12701 | CENTRAL | 248 | 2019-09-30 | Integrity Workover of NUN RIVER 006 | L1: High level estimate | Cordelia Ikpera | On track | 2019-01-25 | 2019-09-30 | 2020-03-25 | 2021-07-30 | 2021-09-30 | [39 empty] | 1.Provide agreed delivery plan | Feasibility being investigated
15891 | CENTRAL | 522 | 2019-09-30 | NUNR-013T DEWAXING, SAND CLEANOUT & SAND CONSOLIDATION TO SAFEGUARD 1.05MMSTB AND RESTORE 400BOPD BY JULY 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-01-19 | 2018-02-09 | 2018-04-26 | 2019-09-30 | 2019-10-31 |  |  |  | 1202.7 | 1202.7 |  |  |  | 7.6 | [16 empty] | 443.1 |  |  |  |  | 2.8 | [8 empty] | 1. Confirm CWI readiness | L4/5 date changed due to availability of CWI Barge (Activity yet to be executed but well opened up and flowing at 2000bopd. under observation - opportunity in OP18 for 2019 delivery)
15892 | CENTRAL | 151 | 2019-09-30 | NUNR 003L TUBING LEAK INVESTIGATION AND REPAIR TO SAFEGUARD 0.47MMSTB BY JUNE 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-01-28 | 2018-06-28 | 2018-08-28 | 2019-09-30 | 2019-11-30 |  |  |  | 2868.43 | 2868.43 |  |  |  | 7.6 | [16 empty] | 1056.79 |  |  |  |  | 2.8 | [8 empty] | 1. Confirm CWI readiness | L4/5 date changed due to availability of CWI Barge - Activity yet to be executed. Opportunity in OP18 for 2019 delivery
15893 | CENTRAL | 0 | 2019-04-30 | NUNR-010T WATER SHUT OFF & RE-PERFORATION OPPORTUNITY TO OPTIMIZE PRODUCTION BY JUNE 2019 | L1: High level estimate | Cordelia Ikpera | On track | 2018-12-10 | [7 empty] | 5910.9 | 5910.9 |  |  |  | 15.2 | [16 empty] | 2177.7 |  |  |  |  | 5.6 | [8 empty] | 1. Provide agreed delivery plan | To be removed, Activity yet to be executed. Opportunity not in OP18 or OP19
|  | 55 | 2019-09-30 | NUNR 015S WHM and FLLR BY JUNE 2019 | L3: Solution known -approved for implementation | On track | On track | 2019-03-28 | 2019-04-15 | 2019-05-10 | 2019-09-30 | 2019-11-30 | [40 empty] | L4/5 date changed due to availability of CWI Barge and completion of FL by Asset Engr - Activity yet to be executed Opportunity in OP18 for 2019 delivery
15894 | CENTRAL | 50 | 2019-10-14 | DBUC-015 Water Shut-off & reperforation to restore production of 950bopd and safeguard 1.47MMstb | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2019-01-20 | 2019-03-13 | 2019-05-02 | 2019-10-14 | 2019-12-13 |  |  |  | 1387 | 1387 |  |  |  | 5.7 | [16 empty] | 511 |  |  |  |  | 2.1 | [8 empty] | 1. Confirm CWI readiness
16204 | CENTRAL | 244 | 2019-07-30 | NOG: Etelebou-001 workover to deliver 700 bopd | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2016-11-28 | 2017-12-28 | 2018-11-28 | 2019-07-30 | 2019-09-30 | [39 empty] | 1. Provide agreed delivery plan | Mobilisation for Well cleanup/test ongoing.
12671 | LE | 20 | 2019-03-22 | Retrieve Plug & NRV on AGBA034S by May 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track |  | 2019-01-18 | 2019-02-22 | 2019-03-22 | 2019-04-30 |  |  |  | 692.44 | 692.44 |  |  |  | 1.75 | [16 empty] | 692.44 | 692.44 |  |  |  | 1.75
12672 | LE | 13 | 2019-04-30 | Sand Clean-out & fishing on AGBA044L by May | L3: Solution known -approved for implementation | Cordelia Ikpera | On track |  | 2019-02-14 | 2019-02-21 | 2019-04-30 | 2019-12-31 |  |  |  | 733.53 | 733.53 |  |  |  | 2.1 | [16 empty] | 733.53 | 733.53 |  |  |  | 2.1
12673 | LE | 20 | 2019-03-23 | Change out faulty ScSSSV for AGBD041L by May 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track |  | 2018-12-28 | 2019-02-21 | 2019-03-23 | 2019-06-01 |  |  |  | 1100.56 | 1100.56 |  |  |  | 2.8 | [16 empty] | 1100.56 | 1100.56 |  |  |  | 2.8
12674 | LE | 20 | 2019-04-25 | Carry out wellhead equipment repair on AGBA018L by Q2, 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-08-20 | 2019-01-18 | 2019-02-28 | 2019-04-25 | 2019-05-31 |  |  |  | 392 | 392 |  |  |  | 1.2 | [16 empty] | 392 | 392 |  |  |  | 1.2
12675 | LE | 20 | 2019-04-30 | Carry out wellhead equipment repair on AGBA054L by Q2, 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-08-20 | 2019-01-18 | 2019-02-22 | 2019-04-30 | 2019-05-31 |  |  |  | 257.6 | 257.6 |  |  |  | 0.7 | [16 empty] | 257.6 | 257.6 |  |  |  | 0.7
12676 | LE | 13 | 2019-03-20 | Carry out wellhead equipment repair on AGBA054S by April 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-08-20 | 2019-01-18 | 2019-01-31 | 2019-03-20 | 2019-04-01 |  |  |  | 342.27 | 342.27 |  |  |  | 0.9 | [16 empty] | 342.27 | 342.27 |  |  |  | 0.9
12677 | LE | 20 | 2019-04-30 | Carry out wellhead equipment repair on AGBA018S by May 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-08-20 | 2019-01-18 | 2019-02-22 | 2019-04-30 | 2019-05-31 |  |  |  | 392 | 392 |  |  |  | 1.2 | [16 empty] | 392 | 392 |  |  |  | 1.2
12678 | LE | 20 | 2019-04-30 | Carry out wellhead equipment repair on AGBA013L by Q2, 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-08-20 | 2019-01-18 | 2019-02-22 | 2019-04-30 | 2019-06-01 |  |  |  | 118.86 | 118.86 |  |  |  | 0.7 | [16 empty] | 118.86 | 118.86 |  |  |  | 0.7
12679 | LE | 20 | 2019-04-30 | Carry out wellhead equipment repair on AGBA013S by Q2 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-08-20 | 2019-01-18 | 2019-02-22 | 2019-04-30 | 2019-06-01 |  |  |  | 564.2 | 564.2 |  |  |  | 1.75 | [16 empty] | 564.2 | 564.2 |  |  |  | 1.75
12680 | LE | 20 | 2019-06-14 | Carry out wellhead equipment repair on AGBA056L to unlock 250 bopd by Q2 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-08-20 | 2019-01-18 | 2019-02-22 | 2019-06-14 | 2019-07-01 |  |  |  | 715.96 | 715.96 |  |  |  | 1.75 | [16 empty] | 715.96 | 715.96 |  |  |  | 1.75
12681 | LE | 20 | 2019-03-30 | Carry out wellhead equipment repair/lay flowine for IMOH036L | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-08-20 | 2019-01-18 | 2019-02-22 | 2019-03-30 | 2019-06-30 |  |  |  | 710.76 | 710.76 |  |  |  | 1.8 | [16 empty] | 710.76 | 710.76 |  |  |  | 1.8
12682 | LE | 20 | 2019-05-31 | Lay flowline for IMOR033L to unlock 180 bopd in Q2, 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-08-20 | 2019-01-18 | 2019-02-22 | 2019-05-31 | 2019-06-01 |  |  |  | 333.78 | 333.78 |  |  |  | 1.08 | [16 empty] | 333.78 | 333.78 |  |  |  | 1.08
12683 | LE | 20 | 2019-05-10 | Lay flowline for IMOR056L by Q2 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-08-20 | 2019-01-18 | 2019-02-28 | 2019-05-10 | 2019-05-31 |  |  |  | 233.04 | 233.04 |  |  |  | 0.96 | [16 empty] | 233.04 | 233.04 |  |  |  | 0.96
13641 | LE | 54 | 2018-12-28 | AGBD011T Bean Up Opportunity to unlocked 255 bopd Potential | L5: Value realized | Cordelia Ikpera | Archived | 2018-09-21 | 2018-09-28 | 2018-10-19 | 2018-11-30 | 2018-12-31 |  |  |  | 551.7658 | 551.7658 |  |  |  | 6.885 | [16 empty] | 236.5511 | 236.5511 |  |  |  | 3.06
13646 | LE | 54 | 2018-12-28 | AGBD070L Bean Up Opportunity to unlocked 740 bopd Potential | L5: Value realized | Cordelia Ikpera | Archived | 2018-09-21 | 2018-09-28 | 2018-10-15 | 2018-10-31 | 2019-12-31 |  |  |  | 1545.0092 | 1545.0092 |  |  |  | 19.98 | [16 empty] | 686.4618 | 686.4618 |  |  |  | 8.88
13673 | LE | 54 | 2018-12-28 | UMUE015S Bean up Opportunity to unlock 300 bopd Potential | L5: Value realized | Ehidiamhen Alikah | Archived | 2018-09-21 | 2018-09-28 | 2018-10-20 | 2018-12-07 | 2018-12-31 |  |  |  | 649.6033 | 649.6033 |  |  |  | 8.4 | [16 empty] | 278.292 | 278.292 |  |  |  | 3.6
12585 | NOV | 54 | 2018-12-28 | NOV: Rigless Perforation extension of Well UBIE-OSHI-08 | L5: Value realized | Cordelia Ikpera | Archived | 2018-07-26 | 2018-08-03 | 2018-08-20 | 2018-11-14 | 2019-12-31 |  |  |  | 400.8877 | 400.8877 |  |  |  | 3.85 | 2.4136 |  |  |  |  | 25.88 | 25.88 |  |  |  | 0.307 | [5 empty] | 367.3772 | 367.3772 |  |  |  | 3.3 | 2.0688
12606 | NOV | 20 | 2019-03-31 | NOV: Reperforation/Nitrogen Lift of Well UBIE-OSHI-02 by April 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-07-31 | 2018-08-03 | 2019-02-05 | 2019-03-31 | 2019-12-31 |  |  |  | 808.47 | 808.47 |  |  |  | 1.44 | 24.3 | [15 empty] | 808.47 | 808.47 |  |  |  | 1.44 | 24.3
12616 | NOV | 20 | 2019-03-31 | NOV: Rigless Perforation extension of Well UBIE-OSHI-04 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-07-26 | 2018-08-03 | 2019-02-05 | 2019-03-31 | 2019-12-31 |  |  |  | 315.72 | 315.72 |  |  |  | 0.63 | 9 | [15 empty] | 315.72 | 315.72 |  |  |  | 0.63 | 9
12627 | NOV | 54 | 2018-12-28 | NOV: Rigless Perforation extension of Well UBIE-OSHI-06 | L5: Value realized | Cordelia Ikpera | Archived | 2018-07-27 | 2018-08-03 | 2018-08-20 | 2018-12-05 | 2019-01-18 |  |  |  | 217.9738 | 217.9738 |  |  |  | 1.26 | 2.4136 |  |  |  |  | 48.59 | 48.59 |  |  |  | 0.545 | [5 empty] | 195.7618 | 195.7618 |  |  |  | 1.08 | 2.0688
12661 | NOV | 54 | 2018-12-28 | NOV: Rigless Perforation extension of Well UBIE-OSHI-15 | L5: Value realized | Cordelia Ikpera | Archived | 2018-07-27 | 2018-08-03 | 2018-08-20 | 2018-11-22 | 2019-01-18 |  |  |  | 371.4372 | 371.4372 |  |  |  | 3.575 | 2.2412 |  |  |  |  | 121.93 | 121.93 |  |  |  | 1.313 | [5 empty] | 367.3772 | 367.3772 |  |  |  | 3.3 | 2.0688
12708 | NOV | 13 | 2019-03-31 | NOV: Reperforation/Nitrogen Lift on AKRI-10 Well by April 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-08-14 | 2018-09-04 | 2019-02-05 | 2019-03-31 | 2019-12-31 |  |  |  | 1368.18 | 1368.18 |  |  |  | 3.06 | 18 | [15 empty] | 1368.18 | 1368.18 |  |  |  | 3.06 | 18
12709 | NOV | 54 | 2018-12-28 | NOV: Water Shut off/Nitrogen Lift on Well TEBIDABA 9S | L5: Value realized | Cordelia Ikpera | Archived | 2018-08-14 | 2018-09-18 | 2018-09-21 | 2018-12-15 | 2019-12-31 |  |  |  | 141.6949 | 141.6949 |  |  |  | 1.875 | [5 empty] | 32.51 | 32.51 |  |  |  | 0.3428 | [5 empty] | 69.5738 | 69.5738 |  |  |  | 0.9
12710 | NOV | 20 | 2019-03-31 | NOV: Water Shut off/Nitrogen Lift on Well by UBIE-OSHI-04L | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-08-14 | 2018-08-20 | 2019-02-05 | 2019-03-31 | 2021-09-30 |  |  |  | 291.96 | 291.96 |  |  |  | 0.63 | 6.3 | [15 empty] | 291.96 | 291.96 |  |  |  | 0.63 | 6.3
12711 | NOV | 18 | 2019-02-28 | NOV: Workover of UBIE-OSHI-13 by March 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-08-14 | 2019-01-18 | 2019-02-05 | 2019-02-28 | 2019-04-30 |  |  |  | 1965.24 | 1965.24 |  |  |  | 4.095 | 81.9 | [15 empty] | 1965.24 | 1965.24 |  |  |  | 4.095 | 81.9
12712 | NOV | 163 | 2019-03-30 | NOV: Acid Stimulation of Well UBIE-OSHI-12 | L3: Solution known -approved for implementation | Cordelia Ikpera | Archived | 2018-07-24 | 2018-09-04 | 2018-09-21 | 2019-03-30 | 2019-12-31 |  |  |  | 205.1881 | 205.1881 |  |  |  | 1.17 | 2.2413 |  |  |  |  | 36.57 | 36.57 |  |  |  | 0.325 | [5 empty] | 195.7618 | 195.7618 |  |  |  | 1.08 | 2.0689
16308 | NOV | 12 | 2019-02-12 | NOV: Deliver 1600 bopd from Ubie-Oshi existing wells following field unitization | L1: High level estimate | Cordelia Ikpera | On track | 2019-02-08 | 2019-02-12 | 2019-02-13 | 2019-02-28 | 2021-02-07
16345 | NOV | 13 | 2019-02-21 | NOV: Open up and ramp up production from Uzere East field to 3200 bopd by April 2019 | L1: High level estimate | Cordelia Ikpera | On track |  | 2019-02-21 | 2019-03-29 | 2019-04-30 | 2022-12-01
12688 | SW /EA | 209 |  | Sidetrack FORC025T | L0: Idea registered | Cordelia Ikpera | On track
12689 | SW /EA | 209 |  | Sidetrack FORC001 | L0: Idea registered | Cordelia Ikpera | On track
12690 | SW /EA | 209 |  | Sidetrack FORC038 | L0: Idea registered | Cordelia Ikpera | On track
12691 | SW /EA | 209 |  | Workover FORC026 | L0: Idea registered | Cordelia Ikpera | On track
13803 | SW /EA | 54 | 2018-12-28 | EA021 STOG Opportunity to unlock 50 bopd Potential by increasing the gaslift injection rate and well performance modelling | L5: Value realized | Ehidiamhen Alikah | Archived | 2018-10-15 | 2018-10-26 | 2018-11-19 | 2018-11-23 | 2018-12-31 |  |  |  | 11.6274 | 11.6274 |  |  |  | 0.15 | [5 empty] | 43 | 43 | [9 empty] | 0 | 0 |  |  |  | 0
13804 | SW /EA | 20 | 2019-02-28 | EA023 STOG Opportunity to unlock 50 bopd Potential | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-10-16 | 2018-10-19 | 2019-02-04 | 2019-02-28 | 2020-01-05 |  |  |  | 212.2 | 212.2 |  |  |  | 0.5 | [16 empty] | 212.2 | 212.2 |  |  |  | 0.5
13805 | SW /EA | 54 | 2018-12-28 | EA030 STOG Opportunity to unlock 200 bopd Potential | L5: Value realized | Cordelia Ikpera | Archived | 2018-10-15 | 2018-10-19 | 2018-10-24 | 2018-12-14 | 2018-12-31 |  |  |  | 62.012 | 62.012 |  |  |  | 0.8 | [5 empty] | 170.793 | 170.793 |  |  |  | 0.005 | [5 empty] | 0 | 0 |  |  |  | 0
13806 | SW /EA | 54 | 2018-12-28 | EA045 STOG Opportunity to unlock 50 bopd Potential | L5: Value realized | Cordelia Ikpera | Archived | 2018-10-19 | 2018-10-23 | 2018-10-30 | 2018-12-15 | 2018-12-31 |  |  |  | 11.625 | 11.625 |  |  |  | 0.15 | [16 empty] | 0 | 0 |  |  |  | 0
13807 | SW /EA | 54 | 2018-12-28 | EA046 STOG Opportunity to unlock 50 bopd Potential | L5: Value realized | Cordelia Ikpera | Archived | 2018-10-05 | 2018-10-15 | 2018-10-19 | 2018-12-12 | 2018-12-31 |  |  |  | 11.6274 | 11.6274 |  |  |  | 0.15 | [16 empty] | 0 | 0 |  |  |  | 0
13808 | SW /EA | 54 | 2018-12-28 | EA047 STOG Opportunity to unlock 50 bopd Potential | L5: Value realized | Cordelia Ikpera | Archived | 2018-10-05 | 2018-10-15 | 2018-10-26 | 2018-12-22 | 2018-12-29 |  |  |  | 11.6274 | 11.6274 |  |  |  | 0.15 | [16 empty] | 0 | 0 |  |  |  | 0
13809 | SW /EA | 54 | 2018-12-28 | EA048 STOG Opportunity to unlock 50 bopd Potential | L5: Value realized | Cordelia Ikpera | Archived | 2018-10-05 | 2018-10-15 | 2018-10-28 | 2018-12-28 | 2019-12-31 |  |  |  | 11.6274 | 11.6274 |  |  |  | 0.15 | [16 empty] | 0 | 0 |  |  |  | 0
13816 | SW /EA | 54 | 2018-12-28 | EA049 STOG Opportunity to unlock 200 bopd Potential | L5: Value realized | Cordelia Ikpera | Archived | 2018-10-05 | 2018-10-15 | 2018-10-29 | 2018-12-28 | 2019-03-03 |  |  |  | 46.5096 | 46.5096 |  |  |  | 0.6 | [5 empty] | 114.81 | 114.81 |  |  |  | 0.19 | [5 empty] | 0 | 0 |  |  |  | 0
14573 | SW /EA | 104 | 2019-02-28 | Installation of 6inch flowline, well head hook up and fittings for ALELE-01 to unlock 4300 bopd | L0: Idea registered | Cordelia Ikpera | On track | 2019-02-28 | 2019-06-30 | 2019-07-31 | 2019-08-31 | 2019-11-30
14574 | SW /EA | 104 | 2019-02-28 | Completion of well, Installation of flow line, well head hook up and fittings for ANGA-03 to unlock 3400bopd | L0: Idea registered | Cordelia Ikpera | On track | 2019-02-28 | 2019-06-30 | 2019-08-30
14575 | SW /EA | 104 | 2019-02-28 | Completion of well, Installation of flow line, well head hook up and fittings for ANGA-05 to unlock 3400bopd | L0: Idea registered | Cordelia Ikpera | On track | 2019-02-28 | 2019-04-30 | 2019-06-30
14595 | SW /EA | 20 | 2019-03-30 | EA024 Beanup Opportunity by April 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-11-22 | 2018-12-15 | 2019-02-28 | 2019-03-30 | 2020-12-31 |  |  |  | 457.74 | 457.74 |  |  |  | 1.08 | [16 empty] | 457.74 | 457.74 |  |  |  | 1.08
14599 | SW /EA | 20 | 2019-03-31 | EA035 Beanup Opportunity by April 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-11-22 | 2018-12-15 | 2019-02-28 | 2019-03-31 | 2019-04-30 |  |  |  | 190.71 | 190.71 |  |  |  | 0.45 | [16 empty] | 190.71 | 190.71 |  |  |  | 0.45
14603 | SW /EA | 20 | 2019-04-12 | EA043 Beanup Opportunity by April 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-11-22 | 2018-12-15 | 2019-02-28 | 2019-04-12 | 2021-06-30 |  |  |  | 305.19 | 305.19 |  |  |  | 0.72 | [16 empty] | 305.19 | 305.19 |  |  |  | 0.72
14607 | SW /EA | 14 | 2019-03-31 | EJA007 Beanup Opportunity to unlock 25 by April 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2018-11-22 | 2019-02-28 | 2019-02-20 | 2019-03-31 | 2019-04-30 |  |  |  | 95.4 | 95.4 |  |  |  | 0.225 | [16 empty] | 95.4 | 95.4 |  |  |  | 0.225
14862 | SW /EA | 14 | 2019-10-31 | EA028 STOG Opportunity to unlock 400 bopd Potential by September 2019 | L3: Solution known -approved for implementation | Cordelia Ikpera | On track | 2019-01-31 |  | 2019-03-08 | 2019-10-31 | 2019-12-24 |  |  |  | 131.24 | 131.24 |  |  |  | 1.6 | [16 empty] | 131.24 | 131.24 |  |  |  | 1.6
14866 | SW /EA | 27 |  | EA042 STOG Opportunity to unlock 600 bopd Potential by September 2019 | L1: High level estimate | Cordelia Ikpera | On track | 2019-01-28 | [7 empty] | 1616 | 1616 |  |  |  | 9.6 | [16 empty] | 404 | 404 |  |  |  | 2.4
16210 | SW /EA | 20 |  | NOG: Forcados Workover Offshore to deliver 3000 bopd | L0: Idea registered | Cordelia Ikpera | On track
16218 | SW /EA | 20 |  | NOG: FYIIP Step1B to deliver 330 MMscf/d | L0: Idea registered | Cordelia Ikpera | On track
16219 | SW /EA | 20 |  | NOG: Ogbotobo re-entry to deliver 8000 bopd by June 2019 | L0: Idea registered | Cordelia Ikpera | On track
16220 | SW /EA | 20 |  | NOG: Southern Swamp AGS plus STEP1 to realise 150 MMscf/d by Oct 2019 | L0: Idea registered | Cordelia Ikpera | On track
16276 | SW /EA | 14 | 2019-02-13 | FORC049T Bean OPTIMIZATION – Gain of 200 bopd by End February 2019 | L1: High level estimate | Cordelia Ikpera | On track | 2019-02-11 | 2019-02-13 | 2019-02-19 | 2019-02-28 | 2020-01-31
16287 | SW /EA | 14 | 2019-02-14 | FORC031S Bean OPTIMIZATION – Gain of 150 bopd by End February 2019 | L1: High level estimate | Cordelia Ikpera | On track | 2019-02-11 | 2019-02-14 | 2019-02-14 | 2019-02-22 | 2019-12-31
16294 | SW /EA | 14 | 2019-02-19 | FORC048S Bean OPTIMIZATION – Gain of 150 bopd by End February 2019 | L1: High level estimate | Cordelia Ikpera | On track | 2019-02-11 | 2019-02-19 | 2019-02-22 | 2019-02-28 | 2019-12-31
|  |  |  | DBUC-015 Water Shut-off & reperforation to restore production of 950bopd and safeguard 1.47MMstb | L1: High level estimate
Note on C1: Enya, Dolapo D SPDC-UPO/G/DNC: next maturity level date-last maturaty level date
Note on K16: Ebeh, Chioma SPDC-UPO/G/UVC: Well clean up proposal