## Slide 1
Business Case/objectives:
This production optimization opportunity involves the review and possible removal of restriction orifice plates in the well flowlines at the inlet manifold in Tunu flowstation, Opukushi flowstation and Benisede flowstation. These orifice plates have varying sizes of the openings ranging from 0.5" to 1.5" for the different well flowline. The intent of the orifice plates in the flowlines is to create the required differential pressure across them for production universe and real time operations for well performance monitoring. The sizes of the orifice plates are to be reviewed against the current well pressures and rates as the well pressure declines over time, to prevent the orifice plates causing restrictions to the declining wells. The review of the orifice plates size will result to less back pressures to the wells and increase rates from the well to the facility. There is potential gains of circa 500bopd increment from review of these plates without any process safety risks and risk to current operations.
Objective:
To review the orifice plate sizes in Tunu Node flowlines for production increase of about 1000bopd.
Project Scope/Actions (With start and end dates and action par
Joint Facility Review – Mar 2022
Risk Assessment – April 2022
Field trial – April 2022
MOC approval – April 2022
Field implementation – April 2022
Well testing for all the wells. – May 2022
Well test validation by the Programmer – June 2022
Input High-level Timeline:
L0-L1
L2: Impacts fully identified and FCF calculated
L3: When to get approval for implementation
L4: When to complete all major actions implementation
L5: Initiative End
Critical Success Factors.
Validation of the well test results before and after the removal of the orifice plates.
Potential Benefits & Measurement:
Additional oil production of 1000bopd at almost zero implementation cost.
  Project Sponsor: Busari Abiodun
  Implementation Lead - Osephode Destiny/Oyedele, Oyebode
  Project Team:
Adomokhai Segun, Ikedilo Nonso, Umaru Jimmai, Taro Onajite, Bille Soye, Taiwo Agbaje
Potential Benefits & Measurement:
Project Milestones /Actions:
Critical Success Factors:
Project Team/Sponsor:
Tunu Node Flowline Orifice plate review for additional 1000bopd by June 2022
Business Case/Objectives
High-Level Timeline: