## WCM-FY Node
FY NODE KEY EQUIPMENT VULNERABILITIES DASHBOARD OCTOBER 2024
LEGEND |  | AVAILABLE
AVAILABLE (WITH ISSUES)
DOWN
WATERCUT METER VULNERABILITIES DASHBOARD
FACILITY | EQUIPMENT | EQUIPMENT TAG | OPS PHLSPHY (N) | REDUNDANCY
NORTHBANK STATION | WATERCUT METER | 03-2411-QIT-001 | 1 | N+0
SOUTHBANK STATION |  | TBA | 1 | N+0
YOKRI STATION |  | 03-2411-QiT-001 | 1 | N+0
WATERCUT METER RESTORATION PLAN - FY NODE
EQUIPMENT | AVAILABILITY | STATUS @ 08.10.2024 | LEC FOR RESTORATION | NEXT STEPS | ACTION PARTY
NORTHBANK STATION | DOWN | 1. Watercut meter faulty/damage beyond repair. 2. New WCM to be ordered for replacement. | Q1,2025 | 1. Secure Asset/Finance support to place order for new WCM for NBK station -LEC: 25th Oct. 2024. 2. Raise PR/PO request through SEPRA. LEC. 31st Oct. 2024. 3. Issue PO for new WCM. LEC 15th Nov. 2024. 4. Take delivery of new WCM. LEC-Q2, 2024. 5. Issue PO, secure CTS and mobilse OEM rep to site for instlaation and commissioning. LEC- Q2, 2025. | Asuku/Alaba
YOKRI STATION | AVAILABLE (WITH ISSUES) | 1. Operating Sub-optimally. 2. Require spares for Troubleshooting/Repair and Calibration. | 30th Dec 2024 | 1. Obtain service quote for new OEM rep for site inspection- 18th Oct 2024. 2. Secure C&P support, CLP approval for OEM Rep mobilization EDD: 31st Oct 2024. 3. Issue PO to vendor - 7th Nov. 2024. 4. Secure CTS Approvals - EDD: 29th Nov 2024 5. Mobilize OEM Rep to site to verify spares required for repairs and calibation from TUNU node: Dec.2024.
SOUTHBANK STATION | DOWN | 1. Watercut meter faulty. 2. Require spares for Troubleshooting/Repair and Calibration. | 30th Dec 2024 | 1. Obtain service quote for new OEM rep for site inspection- 18th Oct 2024. 2. Secure C&P support, CLP approval for OEM Rep mobilization EDD: 31st Oct 2024. 3. Issue PO to vendor - 7th Nov. 2024. 4. Secure CTS Approvals - EDD: 29th Nov 2024 5. Mobilize OEM Rep to site to verify spares required for repairs and calibation from TUNU node: Dec.2024.