## Fit4_PSO List
| Hub | Date Identified | Activity Type | CATEGORY: OPTZ or DEF or LIP | Facility - Node | Well ID | Description | Expected Gains (Boepd) | Target Date | Est. no of producing days till end year | Total Est. Volume to year end bbl | Instant. Gain (Boepd) | WRFM Actual Gains CYC (Boepd) | No of producing days from Jan. To date (Aug.) | Expected Volume for 365 days | Actual Total Vol YTD bbl | Action Parties | Status | Date Acheived | Remarks/Actions
1 | West | 2024-02-27 | PSO | OPTZ | TUNU/1 | TUNU013T | Bean down from BN 24 to BN 20 to comply with TAR | 0 | 2024-03-10 |  | 0 |  | 12.49 | 244 | 3647.08 | 3047.56 | Ops | Closed | 2024-02-15 | Done and tested well.
2 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | ESCB011S | Bean up from BN 20 to BN 24 | 50 | 2024-02-29 |  | 0 |  | 13.06 | 244 | 3813.52 | 3186.64 | Ops | Closed | 2024-03-15 | Done and tested well.
3 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | ESCB015L | Bean up from BN 44 to BN 48 | 50 | 2024-02-29 |  | 0 |  | 61.76 | 244 | 18033.92 | 15069.44 | Ops | Closed | 2024-03-15 | Done and tested well.
4 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | OTUM030L | Bean up from BN 36 to BN 40 | 50 | 2024-02-29 |  | 0 |  | 9.23 | 244 | 2695.16 | 2252.12 | Ops | Closed | 2024-03-01 | Implemented and tested post community issues
5 | West | 2024-02-16 | PSO | OPTZ | FORC/3 | FORC047S | Bean up from BN 40 to BN 42 | 215 | 2024-03-10 |  | 0 |  | 16.88 | 244 | 4928.96 | 4118.72 | Ops | Closed | 2024-03-01 | Done and tested well.
6 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | ESCB002L | Bean up from BN 16 to BN 24 | 50 | 2024-02-29 |  | 0 |  | 105.42 | 244 | 30782.64 | 25722.48 | Ops | Closed | 2024-04-15 | Implemented post community crisis & flare management
7 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | AFRE010L | Bean up from BN 20 to BN 24 | 50 | 2024-02-29 |  | 0 |  | 112.55 | 244 | 32864.6 | 27462.2 | Ops | Closed | 2024-04-15 | Implemented post community crisis & flare mgt
8 | West | 2024-02-16 | PSO | OPTZ | FORC/2 | FORC074T | Bean up from BN 24 to BN 26 | 215 | 2024-03-10 |  | 0 |  | 105.1 | 244 | 30689.2 | 25644.4 | Ops | Closed | 2024-04-15 | Done and tested well.
9 | West | 2024-02-16 | PSO | OPTZ | FORC/2 | FORC139T | Bean up from BN 24 to BN 28 | 215 | 2024-03-10 |  | 0 |  | 43.23 | 244 | 12623.16 | 10548.12 | Ops | Closed | 2024-04-15 | Done and tested well.
10 | West | 2024-02-16 | PSO | OPTZ | FORC/2 | FORC148T | Bean up from BN 18 to BN 20 | 215 | 2024-03-10 |  | 0 |  | 113.5 | 244 | 33142 | 27694 | Ops | Closed | 2024-04-15 | Done and tested well.
11 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA025T | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 74.19 | 244 | 21663.48 | 18102.36 | Ops | Closed | 2024-04-15 | Done and tested well.
12 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA036T | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 315.53 | 244 | 92134.76 | 76989.32 | Ops | Closed | 2024-04-15 | Done and tested well.
13 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA046T | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 352.35 | 244 | 102886.2 | 85973.4 | Ops | Closed | 2024-04-15 | Done and tested well.
14 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA054T | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 148.32 | 244 | 43309.44 | 36190.08 | Ops | Closed | 2024-04-15 | Done and tested well.
15 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA056T | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 172.6 | 244 | 50399.2 | 42114.4 | Ops | Closed | 2024-04-15 | Done and tested well.
16 | West | 2024-02-21 | PSO | OPTZ | BENS/1 | BENS011S | Bean up from BN 30 to BN 32 to close gap between Net and TAR | 50 | 2024-06-15 |  | 0 |  | 20.86 | 244 | 6091.12 | 5089.84 | Ops | Open | 2024-05-15 | Bean up implemented, but closed in for flare management due to AGC1 & AGC2 outages
17 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA021 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 2.24 | 244 | 654.08 | 546.56 | Ops | Closed | 2024-06-24 | Done and tested well.
18 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA023 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 37.32 | 244 | 10897.44 | 9106.08 | Ops | Closed | 2024-06-24 | Done and tested well.
19 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA045 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 18.75 | 244 | 5475 | 4575 | Ops | Closed | 2024-06-24 | Done and tested well.
20 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA047 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 80.13 | 244 | 23397.96 | 19551.72 | Ops | Closed | 2024-06-24 | Done and tested well.
21 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA051 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 41.57 | 244 | 12138.44 | 10143.08 | Ops | Closed | 2024-06-24 | Done and tested well.
22 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA024 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 5.76 | 244 | 1681.92 | 1405.44 | Ops | Closed | 2024-07-24 | Facilty trips, weather, operational issues resulting in the non-testing of the wells.
23 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA026 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 28.29 | 244 | 8260.68 | 6902.76 | Ops | Closed | 2024-04-15 | Facilty trips, weather, operational issues resulting in the non-testing of the wells.
24 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA055T | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 3.48 | 244 | 1016.16 | 849.12 | Ops | Closed | 2024-04-15 | Facilty trips, weather, operational issues resulting in the non-testing of the wells.
25 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA057S | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 25.03 | 244 | 7308.76 | 6107.32 | Ops | Closed | 2024-04-15 | Facilty trips, weather, operational issues resulting in the non-testing of the wells.
26 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC138T | Bean up from 24/64" to 28/64" | 185 | 2024-07-15 |  | 0 |  | 22.18 | 244 | 6476.56 | 5411.92 | Ops | Closed | 2024-07-01 | Done and tested
27 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC144T | Bean up from 28/64" to 32/64" | 140 | 2024-07-15 |  | 0 |  | 50.62 | 244 | 14781.04 | 12351.28 | Ops | Closed | 2024-07-01 | Done and tested
28 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC147T | Bean up from 28/64" to 32/64" | 145 | 2024-07-15 |  | 0 |  | 45.38 | 244 | 13250.96 | 11072.72 | Ops | Closed | 2024-07-01 | Done and tested
29 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC047L | Bean up from 28/64" to 32/64" | 45 | 2024-07-15 |  | 0 |  | 1.93 | 244 | 563.56 | 470.92 | Ops | Closed | 2024-07-01 | Done and tested
30 | West | 2024-07-30 | PSO | OPTZ | BENS/1 | BENS025S | Choke optimization | 45 | 2024-08-15 |  | 0 |  | 20.78 | 244 | 6067.76 | 5070.32 | Ops | Closed | 2024-08-01 | Done and tested
31 | West | 2024-07-30 | PSO | OPTZ | BENS/1 | BENS026T | Choke optimization | 45 | 2024-08-15 |  | 0 |  | 34.72 | 244 | 10138.24 | 8471.68 | Ops | Closed | 2024-08-01 | Done and tested
32 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC135L | Bean up from 20/64" to 24/64" | 104 | 2024-08-15 |  | 0 |  | 10.9004 | 244 | 3182.9195 | 2659.6999 | Ops | Closed | 2024-08-01 | Done and tested
33 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC143T | Bean up from 36/64" to 38/64" | 167 | 2024-08-15 |  | 0 |  | 7.0461 | 244 | 2057.4641 | 1719.2508 | Ops | Closed | 2024-08-01 | Done and tested
34 | West | 2024-07-30 | PSO | OPTZ | OGBO/1 | OGBO009T | Choke optimization | 45 | 2024-08-15 |  | 0 |  | 18.3268 | 244 | 5351.4219 | 4471.7361 | Ops | Closed | 2024-08-01 | Done and tested
35 | West | 2024-02-24 | PSO | OPTZ | OGBO/1 | OGBO017T | Bean up from BN 16 to BN 20 post removal of flare management restrictions | 50 | 2024-06-15 |  | 0 |  | 71.61 | 244 | 20910.12 | 17472.84 | Ops | Closed | 2024-08-24 | Done and tested well. Well was closed in for flare management due to AGC1 & AGC2 outages and subsequently re-opened
36 | West | 2024-07-30 | PSO | OPTZ | TUNU/1 | TUNU019S | Choke optimization | 45 | 2024-08-15 |  | 0 |  | 112.3552 | 244 | 32807.7214 | 27414.6713 | Ops | Closed | 2024-08-01 | Done and tested
37 | West | 2024-07-30 | PSO | OPTZ | TUNU/1 | TUNU019L | Choke optimization | 45 | 2024-08-15 |  | 0 |  | 5.1352 | 244 | 1499.4913 | 1252.9996 | Ops | Closed | 2024-08-01 | Done and tested
38 | West | 2024-07-30 | PSO | OPTZ | OPUK/1 | OPUK009T | Choke optimization | 45 | 2024-08-15 |  | 0 |  | 4.6511 | 244 | 1358.1231 | 1134.87 | Ops | Closed | 2024-08-01 | Done and tested
39 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | OTUM035S | Bean up from BN 44 to BN 48 | 45 | 2024-02-29 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Open |  | Implemented but resulted in a net loss. To be reversed to previous choke size
40 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | OTUM036L | Bean up from BN 52 to BN 56 | 45 | 2024-02-29 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Open |  | Implemented but resulted in a net loss. To be reversed to previous choke size
41 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA019S | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-04-15 | Done and tested well.
42 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA020 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-04-15 | Done and tested well.
43 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA050 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-04-15 | Done and tested well.
44 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA056 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Open | 2024-04-15 | Done and tested well.
45 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA057L | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  |  | 244 | 0 | 0 | Ops | Open | 2024-04-15 | Facilty trips, weather, operational issues resulting in the non-testing of the wells.
46 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA058L | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  |  | 244 | 0 | 0 | Ops | Open | 2024-04-15 | Facilty trips, weather, operational issues resulting in the non-testing of the wells.
47 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA058S | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  |  | 244 | 0 | 0 | Ops | Open | 2024-04-15 | Facilty trips, weather, operational issues resulting in the non-testing of the wells.
48 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC064T | Bean up from 30/64" to 34/64" | 130 | 2024-07-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-07-01 | Aborted due to high BSW, gains were eroded.
49 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC028S | Bean up from 56/64" to 60/64" | 265 | 2024-07-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-07-01 | Implemented, but no gain
50 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC131L | Bean up from 28/64" to 30/64" | 100 | 2024-07-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-07-01 | Implemented, but no gain
51 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC142S | Bean up from 20/64" to 24/64" | 120 | 2024-07-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-07-01 | Implemented, but no gain
52 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC148T | Bean up from 20/64" to 24/64" | 125 | 2024-07-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-07-01 | Implemented, but no gain
53 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC150T | Bean up from 28/64" to 32/64" | 180 | 2024-07-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-07-01 | Implemented, but no gain
54 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC028L | Bean up from 24/64" to 28/64" | 130 | 2024-07-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-07-01 | Implemented, but no gain
55 | West | 2024-05-28 | PSO | OPTZ | OTUM/1 | OTUMARA | Otumara Gas Lift Optimization. | 500 | 2024-11-30 | [5 empty] | 15000 | 0 | Onyi/Ops | Open |  | *Budget will be provided by the asset. *Identify & screen the candidate wells. *Share the gas lines sizes. *Set up a follow-up connect. *Incorporate the discussions on the gas compressor capacity
56 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC141L | Choke optimization | 500 | 2024-07-30 | [5 empty] | 22500 |  | Femi | Open |  | Review opportunity to see if opportunity still exists and quantify expected gains - Femi
57 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC022T | Bean up from 36/64" to 40/64" | 200 | 2024-07-30 | [5 empty] | 18000 | 0 | Ops | Open | 2024-08-01 | Implemented, yet to be banked
58 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC152T | Bean up from 40/64" to 42/64" | 118 | 2024-07-30 | [5 empty] | 10620 | 0 | Ops | Open |  | Bean fabrication ongoing
59 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC037L | Bean up from 28/64" to 32/64" | 105 | 2024-07-30 | [5 empty] | 9450 | 0 | Ops | Open | 2024-08-01 | Implemented, awaiting testing & sampling
60 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC073L | Bean up from 28/64" to 30/64" | 100 | 2024-07-30 | [5 empty] | 6000 | 0 | Ops | Open |  | Well is currently down, suspect SSSV, Awaiting resolution
61 | West | 2023-08-10 | PSO | OPTZ | FORC/4 | FC Cluster 31 | Cluster 31 Well re-alignment for 4 strings (FORC031S, 048L, 048S & 049T) | 750 | 2024-10-30 | [5 empty] | 33750 | 0 | Femi/ Magdalene | Open |  | Focused session planned for review of 31S (3rd week in May). Put on hold until 31S is back on stream. Revalidate opportunity and the associated gains.
62 | West | 2023-08-10 | PSO | OPTZ | FORC/4 | FORCADOS | Reduction of New Yokri FS HP static pressure, to help with draw-down of wells | 100 | [6 empty] | 6000 | 0 | Ops | Open |  | Review opportunity & provide timeline (Femi & Aisha)
63 | West | 2023-08-10 | PSO | OPTZ | FORC/2 | FC Cluster 5 | Cluster 5 Optimization - Well re-alignment for possible gains | 200 | [6 empty] | 12000 | 0 | Ops | Open |  | Review opportunity & provide timeline (Femi & Aisha)
64 | West | 2024-02-22 | PSO | OPTZ | BENS/1 | BENS018L | Bean up from BN 20 to BN 24 to close gap between Net and TAR | 50 | 2024-06-15 | [5 empty] | 3000 | 0 | Ops | Open |  | Bean up implemented, but closed in for flare management due to AGC1 & AGC2 outages. AGC2 expected to be back-up within the week. Leak on LP line, currently using the line to to produce the LP wells.
65 | West | 2024-02-23 | PSO | OPTZ | BENS/1 | BENS024L | Bean up from BN 16 to BN 18 to comply with TAR | 50 | 2024-06-15 | [5 empty] | 3000 | 0 | Ops | Open |  | Closed in for flare management due to AGC1 & AGC2 outages. Leak on LP line, currently using the line to to produce the LP wells. AGC2 expected to be back-up within the week. Leak on LP line, currently using the line to to produce the LP wells.
66 | West | 2024-02-23 | PSO | OPTZ | BENS/1 | BENS022T | Bean up from BN 20 to BN 24 to comply with TAR | 50 | 2024-06-15 | [5 empty] | 3000 | 0 | Ops | Open |  | Bean up, but not tested due to unavailability of test facility. Well was awaiting completion of MER testing, then it was creamed off for flare management due to AGC1 & AGC2 outages.
67 | West | 2023-08-10 | PSO | OPTZ | FORC/4 | Yokri | Yokri Lift Gas Optimization using ultrasonic clamp-on gas metering. | 1000 | 2025-03-30 | [5 empty] | 0 | 0 | Hamzat | Open |  | *Set up a call to work the details. *Bulking constraints in Yokri to be considered in the bigger picture.
68 | East | 2024-07-30 | PSO | OPTZ | GBAR/KC | ZARA013T | Bean up from 36/64” to 38/64” | 400 | 2024-08-15 |  | 0 |  | 11.7585 | 244 | 3433.4832 | 2869.075 | Ops | Closed | 2024-08-01 | Done and tested
69 | East | 2024-06-24 | PSO | OPTZ | GBAR/KC | GBAR022T | Choke optimization - Choke internals constraining the production (Gas well) | 1700 | 2024-10-30 | [5 empty] | 51000 |  |  | Open |  | Engaging the OEM for a quote
70 | East | 2024-08-24 | PSO | OPTZ | GBAR/KC | ZARA013T | Bean up well from 28/64” to 32/64“. | 400 | 2024-10-15 | [5 empty] | 18000 |  | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
71 | East | 2022-12-01 | PSO | OPTZ | GBAR/KC | ETEL012T | Bean up well from 28/64” to 32/64“. Test well on bean 32/64". Take wellhead samples for watercut and sandcut analysis. | 370 | 2024-10-15 | [5 empty] | 16650 |  | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
72 | East | 2022-12-01 | PSO | OPTZ | GBAR/KC | ZARA012S | Bean up well from 44/64” to 48/64“. Test well on bean 32/64". Take wellhead samples for watercut and sandcut analysis. | 285 | 2024-10-15 | [5 empty] | 12825 |  | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
76 | East | 2022-12-01 | PSO | OPTZ | GBAR/KC | KOCR025T | Bean up well from 24/64” to 28/64“. Test well on bean 28/64". Take wellhead samples for watercut and sandcut analysis. | 170 | 2024-10-15 | [5 empty] | 7650 |  | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
74 | East | 2022-12-01 | PSO | OPTZ | GBAR/KC | GBAR019T | Bean up well from 24/64” to 28/64“. Test well on bean 28/64". Take wellhead samples for watercut and sandcut analysis. | 120 | 2024-10-15 | [5 empty] | 5400 |  | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
72 | East | 2022-12-01 | PSO | OPTZ | GBAR/KC | GBAR009T | Bean-up well. (Constrained by TAR) Carry-out MER test. Request for upward review of NUPRC TAR. Implement bean-up opportunity, as advised by PT. | 100 | 2024-10-30 | [5 empty] | 4500 |  | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
73 | East | 2022-12-01 | PSO | OPTZ | GBAR/KC | GBAR023T | Bean-up well. (Constrained by TAR) Carry-out MER test. Request for upward review of NUPRC TAR. Implement bean-up opportunity, as advised by PT. | 100 | 2024-10-30 | [5 empty] | 4500 |  | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
75 | East | 2022-12-01 | PSO | OPTZ | GBAR/KC | KOCR020T | Bean-up well (Constrained by TAR) Carry-out MER test. Request for upward review of NUPRC TAR. Implement bean-up opportunity, as advised by PT. | 100 | 2024-10-30 | [5 empty] | 4500 |  | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
[8 empty] | 11819 |  |  | 0 |  | 2337.0334 |  | 949758.7445 | 570236.1427
Parking Lot
1 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | AFRE013S | Bean up from BN 20 to BN 24 | 50 | 2024-02-29 |  | 0 |  |  | 244 |  | 0 | Ops | Open |  | High annulus pressure, compressor capacity, HGOR well. Fix well integrity issue and review opportunity. Plan is to fix the integrity issue and use a swing gas production. This will require more NGC capacity to realise any additional oil gain.

## Back Up_Fit4_PSO List
S/N | Hub | Date Identified | Activity Type | CATEGORY: OPTZ or DEF or LIP | Facility - Node | Well ID | Description | Expected Gains (Boepd) | Target Date | Est. no of producing days till end year | Total Est. Volume to year end bbl | Instant. Gain (Boepd) | WRFM Actual Gains CYC (Boepd) | No of producing days from Jan. To date (Aug.) | Expected Volume for 365 days | Actual Total Vol YTD bbl | Action Parties | Status | Date Acheived | Remarks/Actions
1 | West | 2024-02-27 | PSO | OPTZ | TUNU/1 | TUNU013T | Bean down from BN 24 to BN 20 to comply with TAR | 0 | 2024-03-10 |  | 0 |  | 12.49 | 244 | 4558.85 | 3047.56 | Ops | Closed | 2024-02-15 | Done and tested well.
2 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | ESCB011S | Bean up from BN 20 to BN 24 | 50 | 2024-02-29 |  | 0 |  | 13.06 | 244 | 4766.9 | 3186.64 | Ops | Closed | 2024-03-15 | Done and tested well.
3 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | ESCB015L | Bean up from BN 44 to BN 48 | 50 | 2024-02-29 |  | 0 |  | 61.76 | 244 | 22542.4 | 15069.44 | Ops | Closed | 2024-03-15 | Done and tested well.
4 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | OTUM030L | Bean up from BN 36 to BN 40 | 50 | 2024-02-29 |  | 0 |  | 9.23 | 244 | 3368.95 | 2252.12 | Ops | Closed | 2024-03-01 | Implemented and tested post community issues
5 | West | 2024-02-16 | PSO | OPTZ | FORC/3 | FORC047S | Bean up from BN 40 to BN 42 | 215 | 2024-03-10 |  | 0 |  | 16.88 | 244 | 6161.2 | 4118.72 | Ops | Closed | 2024-03-01 | Done and tested well.
6 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | ESCB002L | Bean up from BN 16 to BN 24 | 50 | 2024-02-29 |  | 0 |  | 105.42 | 244 | 38478.3 | 25722.48 | Ops | Closed | 2024-04-15 | Implemented post community crisis & flare management
7 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | AFRE010L | Bean up from BN 20 to BN 24 | 50 | 2024-02-29 |  | 0 |  | 112.55 | 244 | 41080.75 | 27462.2 | Ops | Closed | 2024-04-15 | Implemented post community crisis & flare mgt
8 | West | 2024-02-16 | PSO | OPTZ | FORC/2 | FORC074T | Bean up from BN 24 to BN 26 | 215 | 2024-03-10 |  | 0 |  | 105.1 | 244 | 38361.5 | 25644.4 | Ops | Closed | 2024-04-15 | Done and tested well.
9 | West | 2024-02-16 | PSO | OPTZ | FORC/2 | FORC139T | Bean up from BN 24 to BN 28 | 215 | 2024-03-10 |  | 0 |  | 43.23 | 244 | 15778.95 | 10548.12 | Ops | Closed | 2024-04-15 | Done and tested well.
10 | West | 2024-02-16 | PSO | OPTZ | FORC/2 | FORC148T | Bean up from BN 18 to BN 20 | 215 | 2024-03-10 |  | 0 |  | 113.5 | 244 | 41427.5 | 27694 | Ops | Closed | 2024-04-15 | Done and tested well.
11 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA025T | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 74.19 | 244 | 27079.35 | 18102.36 | Ops | Closed | 2024-04-15 | Done and tested well.
12 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA036T | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 315.53 | 244 | 115168.45 | 76989.32 | Ops | Closed | 2024-04-15 | Done and tested well.
13 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA046T | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 352.35 | 244 | 128607.75 | 85973.4 | Ops | Closed | 2024-04-15 | Done and tested well.
14 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA054T | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 148.32 | 244 | 54136.8 | 36190.08 | Ops | Closed | 2024-04-15 | Done and tested well.
15 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA056T | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 172.6 | 244 | 62999 | 42114.4 | Ops | Closed | 2024-04-15 | Done and tested well.
16 | West | 2024-02-21 | PSO | OPTZ | BENS/1 | BENS011S | Bean up from BN 30 to BN 32 to close gap between Net and TAR | 50 | 2024-06-15 |  | 0 |  | 20.86 | 244 | 7613.9 | 5089.84 | Ops | Open | 2024-05-15 | Bean up implemented, but closed in for flare management due to AGC1 & AGC2 outages
17 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA021 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 2.24 | 244 | 817.6 | 546.56 | Ops | Closed | 2024-06-24 | Done and tested well.
18 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA023 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 37.32 | 244 | 13621.8 | 9106.08 | Ops | Closed | 2024-06-24 | Done and tested well.
19 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA045 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 18.75 | 244 | 6843.75 | 4575 | Ops | Closed | 2024-06-24 | Done and tested well.
20 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA047 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 80.13 | 244 | 29247.45 | 19551.72 | Ops | Closed | 2024-06-24 | Done and tested well.
21 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA051 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 41.57 | 244 | 15173.05 | 10143.08 | Ops | Closed | 2024-06-24 | Done and tested well.
22 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA024 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 5.76 | 244 | 2102.4 | 1405.44 | Ops | Closed | 2024-07-24 | Facilty trips, weather, operational issues resulting in the non-testing of the wells.
23 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA026 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 28.29 | 244 | 10325.85 | 6902.76 | Ops | Closed | 2024-04-15 | Facilty trips, weather, operational issues resulting in the non-testing of the wells.
24 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA055T | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 3.48 | 244 | 1270.2 | 849.12 | Ops | Closed | 2024-04-15 | Facilty trips, weather, operational issues resulting in the non-testing of the wells.
25 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA057S | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 25.03 | 244 | 9135.95 | 6107.32 | Ops | Closed | 2024-04-15 | Facilty trips, weather, operational issues resulting in the non-testing of the wells.
26 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC138T | Bean up from 24/64" to 28/64" | 185 | 2024-07-15 |  | 0 |  | 22.18 | 244 | 8095.7 | 5411.92 | Ops | Closed | 2024-07-01 | Done and tested
27 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC144T | Bean up from 28/64" to 32/64" | 140 | 2024-07-15 |  | 0 |  | 50.62 | 244 | 18476.3 | 12351.28 | Ops | Closed | 2024-07-01 | Done and tested
28 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC147T | Bean up from 28/64" to 32/64" | 145 | 2024-07-15 |  | 0 |  | 45.38 | 244 | 16563.7 | 11072.72 | Ops | Closed | 2024-07-01 | Done and tested
29 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC047L | Bean up from 28/64" to 32/64" | 45 | 2024-07-15 |  | 0 |  | 1.93 | 244 | 704.45 | 470.92 | Ops | Closed | 2024-07-01 | Done and tested
30 | West | 2024-07-30 | PSO | OPTZ | BENS/1 | BENS025S | Choke optimization | 45 | 2024-08-15 |  | 0 |  | 20.78 | 244 | 7584.7 | 5070.32 | Ops | Closed | 2024-08-01 | Done and tested
31 | West | 2024-07-30 | PSO | OPTZ | BENS/1 | BENS026T | Choke optimization | 45 | 2024-08-15 |  | 0 |  | 34.72 | 244 | 12672.8 | 8471.68 | Ops | Closed | 2024-08-01 | Done and tested
32 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC135L | Bean up from 20/64" to 24/64" | 104 | 2024-08-15 |  | 0 |  | 10.9004 | 244 | 3978.6494 | 2659.6999 | Ops | Closed | 2024-08-01 | Done and tested
33 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC143T | Bean up from 36/64" to 38/64" | 167 | 2024-08-15 |  | 0 |  | 7.0461 | 244 | 2571.8301 | 1719.2508 | Ops | Closed | 2024-08-01 | Done and tested
34 | West | 2024-07-30 | PSO | OPTZ | OGBO/1 | OGBO009T | Choke optimization | 45 | 2024-08-15 |  | 0 |  | 18.3268 | 244 | 6689.2774 | 4471.7361 | Ops | Closed | 2024-08-01 | Done and tested
35 | West | 2024-02-24 | PSO | OPTZ | OGBO/1 | OGBO017T | Bean up from BN 16 to BN 20 post removal of flare management restrictions | 50 | 2024-06-15 |  | 0 |  | 71.61 | 244 | 26137.65 | 17472.84 | Ops | Closed | 2024-08-24 | Done and tested well. Well was closed in for flare management due to AGC1 & AGC2 outages and subsequently re-opened
36 | West | 2024-07-30 | PSO | OPTZ | TUNU/1 | TUNU019S | Choke optimization | 45 | 2024-08-15 |  | 0 |  | 112.3552 | 244 | 41009.6517 | 27414.6713 | Ops | Closed | 2024-08-01 | Done and tested
37 | West | 2024-07-30 | PSO | OPTZ | TUNU/1 | TUNU019L | Choke optimization | 45 | 2024-08-15 |  | 0 |  | 5.1352 | 244 | 1874.3641 | 1252.9996 | Ops | Closed | 2024-08-01 | Done and tested
38 | West | 2024-07-30 | PSO | OPTZ | OPUK/1 | OPUK009T | Choke optimization | 45 | 2024-08-15 |  | 0 |  | 4.6511 | 244 | 1697.6539 | 1134.87 | Ops | Closed | 2024-08-01 | Done and tested
39 | West | 2024-07-30 | PSO | OPTZ | GBAR/KC | ZARA013T | Bean up from 36/64” to 38/64” | 400 | 2024-08-15 |  | 0 |  | 11.7585 | 244 | 4291.854 | 2869.075 | Ops | Closed | 2024-08-01 | Done and tested
40 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | OTUM035S | Bean up from BN 44 to BN 48 | 45 | 2024-02-29 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Open |  | Implemented but resulted in a net loss. To be reversed to previous choke size
41 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | OTUM036L | Bean up from BN 52 to BN 56 | 45 | 2024-02-29 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Open |  | Implemented but resulted in a net loss. To be reversed to previous choke size
42 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA019S | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-04-15 | Done and tested well.
43 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA020 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-04-15 | Done and tested well.
44 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA050 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-04-15 | Done and tested well.
45 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA056 | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Open | 2024-04-15 | Done and tested well.
46 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA057L | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  |  | 244 | 0 | 0 | Ops | Open | 2024-04-15 | Facilty trips, weather, operational issues resulting in the non-testing of the wells.
47 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA058L | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  |  | 244 | 0 | 0 | Ops | Open | 2024-04-15 | Facilty trips, weather, operational issues resulting in the non-testing of the wells.
48 | West | 2024-01-17 | PSO | OPTZ | EA/EJA | EA058S | Facility PSO: FL Descaling | 45 | 2024-03-30 |  | 0 |  |  | 244 | 0 | 0 | Ops | Open | 2024-04-15 | Facilty trips, weather, operational issues resulting in the non-testing of the wells.
49 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC064T | Bean up from 30/64" to 34/64" | 130 | 2024-07-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-07-01 | Aborted due to high BSW, gains were eroded.
50 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC028S | Bean up from 56/64" to 60/64" | 265 | 2024-07-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-07-01 | Implemented, but no gain
51 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC131L | Bean up from 28/64" to 30/64" | 100 | 2024-07-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-07-01 | Implemented, but no gain
52 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC142S | Bean up from 20/64" to 24/64" | 120 | 2024-07-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-07-01 | Implemented, but no gain
53 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC148T | Bean up from 20/64" to 24/64" | 125 | 2024-07-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-07-01 | Implemented, but no gain
54 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC150T | Bean up from 28/64" to 32/64" | 180 | 2024-07-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-07-01 | Implemented, but no gain
55 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC028L | Bean up from 24/64" to 28/64" | 130 | 2024-07-30 |  | 0 |  | 0 | 244 | 0 | 0 | Ops | Closed | 2024-07-01 | Implemented, but no gain
56 | West | 2024-05-28 | PSO | OPTZ | OTUM/1 | OTUMARA | Otumara Gas Lift Optimization. | 500 | 2024-11-30 | [6 empty] | 0 | Onyi/Ops | Open |  | *Budget will be provided by the asset. *Identify & screen the candidate wells. *Share the gas lines sizes. *Set up a follow-up connect. *Incorporate the discussions on the gas compressor capacity
57 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC141L | Choke optimization | 500 | 2024-07-30 | [7 empty] | Femi | Open |  | Review opportunity to see if opportunity still exists and quantify expected gains - Femi
58 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC022T | Bean up from 36/64" to 40/64" | 200 | 2024-07-30 | [6 empty] | 0 | Ops | Open | 2024-08-01 | Implemented, yet to be banked
59 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC152T | Bean up from 40/64" to 42/64" | 118 | 2024-07-30 | [6 empty] | 0 | Ops | Open |  | Bean fabrication ongoing
60 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC037L | Bean up from 28/64" to 32/64" | 105 | 2024-07-30 | [6 empty] | 0 | Ops | Open | 2024-08-01 | Implemented, awaiting testing & sampling
61 | West | 2024-06-27 | PSO | OPTZ | FORC | FORC073L | Bean up from 28/64" to 30/64" | 100 | 2024-07-30 | [6 empty] | 0 | Ops | Open |  | Well is currently down, suspect SSSV, Awaiting resolution
62 | West | 2023-08-10 | PSO | OPTZ | FORC/4 | FC Cluster 31 | Cluster 31 Well re-alignment for 4 strings (FORC031S, 048L, 048S & 049T) | 750 | 2024-10-30 | [6 empty] | 0 | Femi/ Magdalene | Open |  | Focused session planned for review of 31S (3rd week in May). Put on hold until 31S is back on stream. Revalidate opportunity and the associated gains.
63 | West | 2023-08-10 | PSO | OPTZ | FORC/4 | FORCADOS | Reduction of New Yokri FS HP static pressure, to help with draw-down of wells | 100 | [7 empty] | 0 | Ops | Open |  | Review opportunity & provide timeline (Femi & Aisha)
64 | West | 2023-08-10 | PSO | OPTZ | FORC/2 | FC Cluster 5 | Cluster 5 Optimization - Well re-alignment for possible gains | 200 | [7 empty] | 0 | Ops | Open |  | Review opportunity & provide timeline (Femi & Aisha)
65 | West | 2024-02-22 | PSO | OPTZ | BENS/1 | BENS018L | Bean up from BN 20 to BN 24 to close gap between Net and TAR | 50 | 2024-06-15 | [6 empty] | 0 | Ops | Open |  | Bean up implemented, but closed in for flare management due to AGC1 & AGC2 outages. AGC2 expected to be back-up within the week. Leak on LP line, currently using the line to to produce the LP wells.
66 | West | 2024-02-23 | PSO | OPTZ | BENS/1 | BENS024L | Bean up from BN 16 to BN 18 to comply with TAR | 50 | 2024-06-15 | [6 empty] | 0 | Ops | Open |  | Closed in for flare management due to AGC1 & AGC2 outages. Leak on LP line, currently using the line to to produce the LP wells. AGC2 expected to be back-up within the week. Leak on LP line, currently using the line to to produce the LP wells.
67 | West | 2024-02-23 | PSO | OPTZ | BENS/1 | BENS022T | Bean up from BN 20 to BN 24 to comply with TAR | 50 | 2024-06-15 | [6 empty] | 0 | Ops | Open |  | Bean up, but not tested due to unavailability of test facility. Well was awaiting completion of MER testing, then it was creamed off for flare management due to AGC1 & AGC2 outages.
68 | West | 2023-08-10 | PSO | OPTZ | FORC/4 | Yokri | Yokri Lift Gas Optimization using ultrasonic clamp-on gas metering. | 1000 | 2025-03-30 | [6 empty] | 0 | Hamzat | Open |  | *Set up a call to work the details. *Bulking constraints in Yokri to be considered in the bigger picture.
69 | East | 2024-06-24 | PSO | OPTZ | GBAR/KC | GBAR022T | Choke optimization - Choke internals constraining the production (Gas well) | 1700 | 2024-10-30 | [8 empty] | Open |  | Engaging the OEM for a quote
70 | East | 2024-08-24 | PSO | OPTZ | GBAR/KC | ZARA013T | Bean up well from 28/64” to 32/64“. | 400 | 2024-10-15 | [7 empty] | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
71 | East | 2022-12-01 | PSO | OPTZ | GBAR/KC | ETEL012T | Bean up well from 28/64” to 32/64“. Test well on bean 32/64". Take wellhead samples for watercut and sandcut analysis. | 370 | 2024-10-15 | [7 empty] | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
72 | East | 2022-12-01 | PSO | OPTZ | GBAR/KC | ZARA012S | Bean up well from 44/64” to 48/64“. Test well on bean 32/64". Take wellhead samples for watercut and sandcut analysis. | 285 | 2024-10-15 | [7 empty] | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
76 | East | 2022-12-01 | PSO | OPTZ | GBAR/KC | KOCR025T | Bean up well from 24/64” to 28/64“. Test well on bean 28/64". Take wellhead samples for watercut and sandcut analysis. | 170 | 2024-10-15 | [7 empty] | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
74 | East | 2022-12-01 | PSO | OPTZ | GBAR/KC | GBAR019T | Bean up well from 24/64” to 28/64“. Test well on bean 28/64". Take wellhead samples for watercut and sandcut analysis. | 120 | 2024-10-15 | [7 empty] | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
72 | East | 2022-12-01 | PSO | OPTZ | GBAR/KC | GBAR009T | Bean-up well. (Constrained by TAR) Carry-out MER test. Request for upward review of NUPRC TAR. Implement bean-up opportunity, as advised by PT. | 100 | 2024-10-30 | [7 empty] | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
73 | East | 2022-12-01 | PSO | OPTZ | GBAR/KC | GBAR023T | Bean-up well. (Constrained by TAR) Carry-out MER test. Request for upward review of NUPRC TAR. Implement bean-up opportunity, as advised by PT. | 100 | 2024-10-30 | [7 empty] | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
75 | East | 2022-12-01 | PSO | OPTZ | GBAR/KC | KOCR020T | Bean-up well (Constrained by TAR) Carry-out MER test. Request for upward review of NUPRC TAR. Implement bean-up opportunity, as advised by PT. | 100 | 2024-10-30 | [7 empty] | PT/Programmer/Prod Ops | Open |  | Stable TNP (choke available)
[8 empty] | 11819 |  |  | 0 |  | 2337.0334 |  | 853017.1807 | 570236.1427
Parking Lot
1 | West | 2024-02-16 | PSO | OPTZ | OTUM/1 | AFRE013S | Bean up from BN 20 to BN 24 | 50 | 2024-02-29 |  | 0 |  |  | 244 |  | 0 | Ops | Open |  | High annulus pressure, compressor capacity, HGOR well. Fix well integrity issue and review opportunity. Plan is to fix the integrity issue and use a swing gas production. This will require more NGC capacity to realise any additional oil gain.