## Sheet1
These underlisted should granular actions that will dovetail into achieving the major actions required to actualise optimisation of TA
| Periods | Facilities | Potential savings/day | oil (bopd) | gas (MscfPD) | oil(kbopd) | gas(MMscfpd) | FCF(oil) | FCF (gas) | Total FCF ('000 USD) | Turnaround End Date | Major Actions Required To Actualize Optimization of TA | Major Actions Required To Actualize Optimization Plan/ Facility | Action Start Date | Action End Date | Action Party
| QI | Soku GP | 1 | 27000 | 650000 | 27 | 650 | 171.07 | 218.44 | 389.51 | 2022-03-13 | 1. Turnaround Scope Development. 2. Complete Detailed Turnaround Planning 3. Pre-Turnaround Works 4. Turnaround Execution. | 1. Turnaround Scope Development. 1a. Scope challenge/optimization workshop. 1b. Scope freeze/Scope change management. (Total sum of scope changes between Scope Freeze date and the T/A should not be more than 5%) 2. Complete Detailed Turnaround Planning 2a. Develop integrated execution schedule (Including Pre-Turnaround work) 2b. Schedule optimization workshop. 3. Pre-Turnaround Work 3a. Carry out shut down on Paper/What-if Analysis. 3b. Mobilization of all resources (labour, equipment and materials) to site. 3c. Close out of ALL readiness criteria. 4. Turnaround Execution 4a. Progress monitoring and control. | 15/1/2022 06/2/2022 02/3/2022 06/3/2022 | 15/1/2022 06/2/2022 02/3/2022 13/3/2022 | Unachukwu Ifeanyichukwu Nketah Victor Nnogo Christopher/Afuba Paul Azibator Festus/Onabajo Abiodun
|  | Adibawa | 1 | 2500 | 750 | 2.5 | 0.75 | 15.84 | 0.25 | 16.09 | 2022-02-27 | 1. Turnaround Scope Development. 2. Complete Detailed Turnaround Planning 3. Pre-Turnaround Works 4. Turnaround Execution. | 1. Carry out optimization workshop 2. Confirm all resources (materials and labour/workforce) are on site before event start date. 3. Turnaround personnel being on site to supervise near critical and critical path activities to ensure schedule compliance and maximum manhour and resource utilization. 4. Monitor HOTT during execution and provide support to secure extra work hours/ night shifts where applicable. 5. Ensure (N+1) availability of all equipments for critical path activities in the event of failure/breakdown 6. Monitor Turnaround Risk register and ensure all identified risks are closed out/placed with adequate contingency before the event start date. (Eg FTO/CTS secured against community interference. 7. Safety and Goal Zero Consciousness during execution to prevent incident. 8. Review Lessons learned register to obtain lessons from past turnarounds 9. Ensure Strict adherence to Turnaround Milestone Plans during planning of turnarounds. | 20/1/2022 23/1/2022 12/2/2022 16/2/2022 | 20/1/2022 23/1/2022 12/2/2022 27/2/2022 | Unachukwu Ifeanyichukwu Nketah Victor Nnogo Christopher/Afuba Paul Akinlolu Haruna
| Q2 | BNAG | 1 | 0 | 0 | 0 | 90 | 0 | 30.25 | 30.25 | 2022-04-01 | 1. Turnaround Scope Development. 2. Complete Detailed Turnaround Planning 3. Pre-Turnaround Works 4. Turnaround Execution. | 1. Carry out optimization workshop 2. Confirm all resources (materials and labour/workforce) are on site before event start date. 3. Turnaround personnel being on site to supervise near critical and critical path activities to ensure schedule compliance and maximum manhour and resource utilization. 4. Monitor HOTT during execution and provide support to secure extra work hours/ night shifts where applicable. 5. Ensure (N+1) availability of all equipments for critical path activities in the event of failure/breakdown 6. Monitor Turnaround Risk register and ensure all identified risks are closed out/placed with adequate contingency before the event start date. (Eg FTO/CTS secured against community interference. 7. Safety and Goal Zero Consciousness during execution to prevent incident. 8. Review Lessons learned register to obtain lessons from past turnarounds 9. Ensure Strict adherence to Turnaround Milestone Plans during planning of turnarounds. | 03/02/2022 25/2/2022 21/3/2022 25/3/2022 | 03/02/2022 25/2/2022 21/3/2022 01/04/2022 | Unachukwu Ifeanyichukwu Nketah Victor Nnogo Christopher/Afuba Paul Emetulu Raymond
| Q3 | Ubie FS | 1 | 1000 | 0 | 1 | 0 | 6.34 | 0 | 6.34 | 2022-07-17 | 1. Turnaround Scope Development. 2. Complete Detailed Turnaround Planning 3. Pre-Turnaround Works 4. Turnaround Execution. | 1. Carry out optimization workshop 2. Confirm all resources (materials and labour/workforce) are on site before event start date. 3. Turnaround personnel being on site to supervise near critical and critical path activities to ensure schedule compliance and maximum manhour and resource utilization. 4. Monitor HOTT during execution and provide support to secure extra work hours/ night shifts where applicable. 5. Ensure (N+1) availability of all equipments for critical path activities in the event of failure/breakdown 6. Monitor Turnaround Risk register and ensure all identified risks are closed out/placed with adequate contingency before the event start date. (Eg FTO/CTS secured against community interference. 7. Safety and Goal Zero Consciousness during execution to prevent incident. 8. Review Lessons learned register to obtain lessons from past turnarounds 9. Ensure Strict adherence to Turnaround Milestone Plans during planning of turnarounds. | 23/5/2022 14/6/2022 8/7/2022 12/7/2022 | 23/5/2022 14/6/2022 8/7/2022 17/7/2022 | Unachukwu Ifeanyichukwu Nketah Victor Nnogo Christopher/Afuba Paul Oniwo Abraham
|  | Ahia FS | 1 | 3000 | 0 | 3 | 0 | 19.01 | 0 | 19.01 | 2022-07-19 | 1. Turnaround Scope Development. 2. Complete Detailed Turnaround Planning 3. Pre-Turnaround Works 4. Turnaround Execution. | 1. Carry out optimization workshop 2. Confirm all resources (materials and labour/workforce) are on site before event start date. 3. Turnaround personnel being on site to supervise near critical and critical path activities to ensure schedule compliance and maximum manhour and resource utilization. 4. Monitor HOTT during execution and provide support to secure extra work hours/ night shifts where applicable. 5. Ensure (N+1) availability of all equipments for critical path activities in the event of failure/breakdown 6. Monitor Turnaround Risk register and ensure all identified risks are closed out/placed with adequate contingency before the event start date. (Eg FTO/CTS secured against community interference. 7. Safety and Goal Zero Consciousness during execution to prevent incident. 8. Review Lessons learned register to obtain lessons from past turnarounds 9. Ensure Strict adherence to Turnaround Milestone Plans during planning of turnarounds. | 24/5/2022 15/6/2022 9/7/2022 13/7/2022 | 24/5/2022 15/6/2022 9/7/2022 19/7/2022 | Unachukwu Ifeanyichukwu Nketah Victor Nnogo Christopher/Afuba Paul Joshua Oluwononi
|  | Diebu Creek FS | 1 | 1000 | 0 | 1 | 0 | 6.34 | 0 | 6.34 | 2022-07-22 | 1. Turnaround Scope Development. 2. Complete Detailed Turnaround Planning 3. Pre-Turnaround Works 4. Turnaround Execution. | 1. Carry out optimization workshop 2. Confirm all resources (materials and labour/workforce) are on site before event start date. 3. Turnaround personnel being on site to supervise near critical and critical path activities to ensure schedule compliance and maximum manhour and resource utilization. 4. Monitor HOTT during execution and provide support to secure extra work hours/ night shifts where applicable. 5. Ensure (N+1) availability of all equipments for critical path activities in the event of failure/breakdown 6. Monitor Turnaround Risk register and ensure all identified risks are closed out/placed with adequate contingency before the event start date. (Eg FTO/CTS secured against community interference. 7. Safety and Goal Zero Consciousness during execution to prevent incident. 8. Review Lessons learned register to obtain lessons from past turnarounds 9. Ensure Strict adherence to Turnaround Milestone Plans during planning of turnarounds. | 28/5/2022 19/6/2022 13/7/2022 17/7/2022 | 28/5/2022 19/6/2022 13/7/2022 22/7/2022 | Unachukwu Ifeanyichukwu Nketah Victor Nnogo Christopher/Afuba Paul Uzozie Victor/Ebieto Hendrix
|  | Etelebou FS | 1 | 320 |  | 0.32 | 0 | 2.03 | 0 | 2.03 | 2022-08-28 | 1. Turnaround Scope Development. 2. Complete Detailed Turnaround Planning 3. Pre-Turnaround Works 4. Turnaround Execution. | 1. Carry out optimization workshop 2. Confirm all resources (materials and labour/workforce) are on site before event start date. 3. Turnaround personnel being on site to supervise near critical and critical path activities to ensure schedule compliance and maximum manhour and resource utilization. 4. Monitor HOTT during execution and provide support to secure extra work hours/ night shifts where applicable. 5. Ensure (N+1) availability of all equipments for critical path activities in the event of failure/breakdown 6. Monitor Turnaround Risk register and ensure all identified risks are closed out/placed with adequate contingency before the event start date. (Eg FTO/CTS secured against community interference. 7. Safety and Goal Zero Consciousness during execution to prevent incident. 8. Review Lessons learned register to obtain lessons from past turnarounds 9. Ensure Strict adherence to Turnaround Milestone Plans during planning of turnarounds. | 20/6/2022 12/7/2022 5/8/2022 09/08/2022 | 20/6/2022 12/7/2022 5/8/2022 28/08/2022 | Unachukwu Ifeanyichukwu Nketah Victor Nnogo Christopher/Afuba Paul Ovoh Anthony/Saheed Ibraham
|  | Soku GP | 1 | 27000 | 650000 | 27 | 650 | 171.07 | 218.44 | 389.51 | 2022-09-20 | 1. Turnaround Scope Development. 2. Complete Detailed Turnaround Planning 3. Pre-Turnaround Works 4. Turnaround Execution. | 1. Carry out optimization workshop 2. Confirm all resources (materials and labour/workforce) are on site before event start date. 3. Turnaround personnel being on site to supervise near critical and critical path activities to ensure schedule compliance and maximum manhour and resource utilization. 4. Monitor HOTT during execution and provide support to secure extra work hours/ night shifts where applicable. 5. Ensure (N+1) availability of all equipments for critical path activities in the event of failure/breakdown 6. Monitor Turnaround Risk register and ensure all identified risks are closed out/placed with adequate contingency before the event start date. (Eg FTO/CTS secured against community interference. 7. Safety and Goal Zero Consciousness during execution to prevent incident. 8. Review Lessons learned register to obtain lessons from past turnarounds 9. Ensure Strict adherence to Turnaround Milestone Plans during planning of turnarounds. | 03/07/2022 25/07/2022 18/08/2022 22/08/2022 | 03/07/2022 25/07/2022 18/08/2022 20/09/2022 | Unachukwu Ifeanyichukwu Nketah Victor Nnogo Christopher/Afuba Paul Festus Azibator/Onibajo Abiodun
Soku FS |  | Soku FS | 1 | 672 | 550 | 0.672 | 0.55 | 4.26 | 0.18 | 4.44 | 2022-09-12 | 1. Turnaround Scope Development. 2. Complete Detailed Turnaround Planning 3. Pre-Turnaround Works 4. Turnaround Execution. | 1. Carry out optimization workshop 2. Confirm all resources (materials and labour/workforce) are on site before event start date. 3. Turnaround personnel being on site to supervise near critical and critical path activities to ensure schedule compliance and maximum manhour and resource utilization. 4. Monitor HOTT during execution and provide support to secure extra work hours/ night shifts where applicable. 5. Ensure (N+1) availability of all equipments for critical path activities in the event of failure/breakdown 6. Monitor Turnaround Risk register and ensure all identified risks are closed out/placed with adequate contingency before the event start date. (Eg FTO/CTS secured against community interference. 7. Safety and Goal Zero Consciousness during execution to prevent incident. 8. Review Lessons learned register to obtain lessons from past turnarounds 9. Ensure Strict adherence to Turnaround Milestone Plans during planning of turnarounds. | 03/07/2022 25/07/2022 18/08/2022 22/08/2022 | 03/07/2022 25/07/2022 18/08/2022 12/09/2022 | Unachukwu Ifeanyichukwu Nketah Victor Nnogo Christopher/Afuba Paul Festus Azibator/Onabajo Abiodun
|  | Gbaran | 1 | 15000 | 900000 | 15 | 900 | 95.04 | 302.46 | 397.5 | 2022-09-12 | 1. Turnaround Scope Development. 2. Complete Detailed Turnaround Planning 3. Pre-Turnaround Works 4. Turnaround Execution. | 1. Carry out optimization workshop 2. Confirm all resources (materials and labour/workforce) are on site before event start date. 3. Turnaround personnel being on site to supervise near critical and critical path activities to ensure schedule compliance and maximum manhour and resource utilization. 4. Monitor HOTT during execution and provide support to secure extra work hours/ night shifts where applicable. 5. Ensure (N+1) availability of all equipments for critical path activities in the event of failure/breakdown 6. Monitor Turnaround Risk register and ensure all identified risks are closed out/placed with adequate contingency before the event start date. (Eg FTO/CTS secured against community interference. 7. Safety and Goal Zero Consciousness during execution to prevent incident. 8. Review Lessons learned register to obtain lessons from past turnarounds 9. Ensure Strict adherence to Turnaround Milestone Plans during planning of turnarounds. | 03/07/2022 25/07/2022 18/08/2022 22/08/2022 | 03/07/2022 25/07/2022 18/08/2022 12/09/2022 | Unachukwu Ifeanyichukwu Nketah Victor Nnogo Christopher/Afuba Paul Mohammed Abdul
|  | Southbank | 1 | 30000 | 6500 | 30 | 6.5 | 190.08 | 2.18 | 192.26 | 2022-09-23 | 1. Turnaround Scope Development. 2. Complete Detailed Turnaround Planning 3. Pre-Turnaround Works 4. Turnaround Execution. | 1. Carry out optimization workshop 2. Confirm all resources (materials and labour/workforce) are on site before event start date. 3. Turnaround personnel being on site to supervise near critical and critical path activities to ensure schedule compliance and maximum manhour and resource utilization. 4. Monitor HOTT during execution and provide support to secure extra work hours/ night shifts where applicable. 5. Ensure (N+1) availability of all equipments for critical path activities in the event of failure/breakdown 6. Monitor Turnaround Risk register and ensure all identified risks are closed out/placed with adequate contingency before the event start date. (Eg FTO/CTS secured against community interference. 7. Safety and Goal Zero Consciousness during execution to prevent incident. 8. Review Lessons learned register to obtain lessons from past turnarounds 9. Ensure Strict adherence to Turnaround Milestone Plans during planning of turnarounds. | 27/07/2022 18/08/2022 11/9/2022 15/9/2022 | 27/07/2022 18/08/2022 11/9/2022 23/9/2022 | Anya Victor Nketah Victor Nnogo Christopher/Afuba Paul Anya Victor
| Q4 | ImoR AGG | 1 | - | - |  | 12 | 0 | 4.03 | 4.03 | 2022-11-26 | 1. Turnaround Scope Development. 2. Complete Detailed Turnaround Planning 3. Pre-Turnaround Works 4. Turnaround Execution. | 1. Carry out optimization workshop 2. Confirm all resources (materials and labour/workforce) are on site before event start date. 3. Turnaround personnel being on site to supervise near critical and critical path activities to ensure schedule compliance and maximum manhour and resource utilization. 4. Monitor HOTT during execution and provide support to secure extra work hours/ night shifts where applicable. 5. Ensure (N+1) availability of all equipments for critical path activities in the event of failure/breakdown 6. Monitor Turnaround Risk register and ensure all identified risks are closed out/placed with adequate contingency before the event start date. (Eg FTO/CTS secured against community interference. 7. Safety and Goal Zero Consciousness during execution to prevent incident. 8. Review Lessons learned register to obtain lessons from past turnarounds 9. Ensure Strict adherence to Turnaround Milestone Plans during planning of turnarounds. | 2/10/2022 24/10/2022 17/11/2022 21/11/2022 | 2/10/2022 24/10/2022 17/11/2022 26/11/2022 | Unachukwu Ifeanyichukwu Nketah Victor Nnogo Christopher/Afuba Paul Elizabeth Okoye/Abiodun Oginni
|  | Bonny F/S | 1 |  |  | 3.5 | 0 | 22.18 |  | 22.18 | 2022-11-26 | 1. Turnaround Scope Development. 2. Complete Detailed Turnaround Planning 3. Pre-Turnaround Works 4. Turnaround Execution. | 1. Carry out optimization workshop 2. Confirm all resources (materials and labour/workforce) are on site before event start date. 3. Turnaround personnel being on site to supervise near critical and critical path activities to ensure schedule compliance and maximum manhour and resource utilization. 4. Monitor HOTT during execution and provide support to secure extra work hours/ night shifts where applicable. 5. Ensure (N+1) availability of all equipments for critical path activities in the event of failure/breakdown 6. Monitor Turnaround Risk register and ensure all identified risks are closed out/placed with adequate contingency before the event start date. (Eg FTO/CTS secured against community interference. 7. Safety and Goal Zero Consciousness during execution to prevent incident. 8. Review Lessons learned register to obtain lessons from past turnarounds 9. Ensure Strict adherence to Turnaround Milestone Plans during planning of turnarounds. | 03/10/2022 25/10/2022 18/11/2022 22/11/2022 | 03/10/2022 25/10/2022 18/11/2022 27/11/2022 | Unachukwu Ifeanyichukwu Nketah Victor Nnogo Christopher/Afuba Paul Unachukwu Ifeanyichukwu
[9 empty] | Periods | Total FCF (USD)
[9 empty] | Q1 | 405600
[9 empty] | Q2 | 30250
[9 empty] | Q3 | 1021870
[9 empty] | Q4 | 26210
[9 empty] | Total | 1483930

## Sheet2
Soku | 1. Carry out optimization workshop 1a. Review critical path for turnaround. 1b. Ensure commitment from execution vendor after optimized schedule. 2. Confirm all materials are on site before event start date.