## Sheet1
Task | Duration (working days) | Start | Finish | % Completed
Data Gathering / Field Visit with all relevant disciplines |  | 2017-10-09 | 2017-10-30 | 100%
Optimization/Conceptual study/ORN |  | 2017-11-01 | 2017-11-24 | 100%
Initiate MoC and obtain approval |  | 2017-11-10 | 2017-11-24 | 100%
Design, HAZOP, Design Documentations |  | 2017-11-25 | 2018-08-31 | 50%
Procurement of LLIs/ Materials |  | 2018-09-01 | 2018-12-30
Mobilization to site, Construction |  | 2019-02-01 | 2019-03-23
Commissioning and start-up |  | 2019-03-24 | 2019-03-26