## Slide 1: Reduce Bonny Terminal Demurrage Cost from US$2.8m in 2019 to US$1.8m by Dec. 2020
L1 date
Initiative lead
Brossa Isaac
Current stage gate
L0
Initiative sponsor
Ireti Omotoso
L2 date
20th August
7th August
Problem statement
  Between 2015 and 2019 BOGT spent an average of US$2.29m on demurrage charges reaching a peak of US$2.88m in 2018, ideally the demurrage should be $0.
  Demurrage is the amount of money paid as compensation to the owner of a vessel or third party for detaining the vessel beyond the agreed lay time for loading cargo. Whenever the terminal exceed the stipulated lay time, the terminal is liable for demurrage per running hour. This is basically any delay to the loading of the vessel (bottlenecks in production prior, during and after vessel loading activities) over which the terminal operator has control that prevents the vessel loading within its agreed laytime
Initiative description
  This initiative seeks to reduce demurrage cost by $1m from 2019 cost, by identifying and implementing steps to reduce the overall time taken to perform loading offtake.
  Key areas of focus are to reduce delays in:
  Internal clearance duration
  Berthing process (mooring & hose connection)
  Processing and delivery of post loading document
  Cargo preparation
  Resolving Ship/Shore Volume Difference
Estimate impact
Wave ID
Location(s)
SPDC – Production Asset
Workstream
Opex
Key stakeholders
Decisions needed to mature
What does success look like at the end of the 3 weeks sprint
  High level assumptions – US$1m savings from 2020 expenditure on demurrage and further reduce US$0.5m by Dec 2021
  Project Sponsor: Ireti Omotoso
  Implementation Lead: Brossa Isaac
  Project Team: Shipping and Export, Asset, Logistics teams and Finance
  (Bob-Manuel Iroloye, Callum Finlayson, Ofovwe Kevwe, Aliyu Mohammed, Muraina Olakunle, Ibrahim Ismaila, Akinyemi Olabisi).
    Formal agreement with Government Agencies on internal clearance Representatives and duration.
    Start laytime after vessel internal clearance by Government agencies
    Use of security vessel to deliver post loading document offshore
  Get all key stakeholders to understand and buy-in to demurrage cost reduction
  Agree laytime reduction options: (Start laytime after vessel internal clearance by Government agencies and specific duration for vessel clearance with Government agencies)
  Identify all contributors and prioritize key contributors for post sprint resolutions.
  Progress from L0 to L3
Chart: 
| 2016 | 2017 | 2018 | 2019 | 2020
Demurrage Cost ($'000) Open | 1646.055 | 1933.231 | 2712.92 | 2880.324 | 1107.152
Demurrage Cost ($'000) Closed | 0 | 0 | 0 | 0 | 289.35

## Slide 2: Cost lever tree – Bonny 2020YTD Demurrage
DRIVER TREE: DEMURRAGE
Awaiting Cargo (70%)
Awaiting Berthing
(18%)
Categories
Drivers
Rope/Line Entanglement
Clearances Delay
Ship/Tanker Schedule
Low Production Rate
Trunk Line outage
Slow Loading request
  YTD demurrage/2020 Target
  Total – $1.2m/ $1.8m Target
Awaiting Shore Readiness
(12%)
Operations
Maintenance (Equipment Failure)
Dehydration issue
Ship/Shore Differences
Awaiting day time
10,547
199,568
105,069
6,814
27,255
704,884
43,685
78,321
139,138
210,115
826,890
Slow loading request from the lifter for a preferred Bill of Laden date
Berthing, Hose handling, Document delivery & signing only carried out in the day
Tank readiness & Fiscalisation delays
OPEC Restriction

## Slide 3: Cost lever tree – Bonny 2016-2019 Demurrage
DRIVER TREE: DEMURRAGE
Awaiting Cargo (69%)
Awaiting Berthing
(15%)
Categories
Drivers
Rope/Line Entanglement
Clearances Delay
Ship Schedule
Low Production Rate
Trunk Line outage
Slow Loading request
  TOTAL demurrage 2016-2019
  ~$8.8M
Awaiting Shore Readiness
(16%)
Operations
Maintenance (Equipment Failure)
Dehydration issue
Ship/Shore Differences
Awaiting day time
425,887
860,470
1,267,366
51,370
122,195
1,404,089
1,497,888
3,212,267
1,440,931
1,286,357
6,114,244
Slow loading request from the lifter (offtaker) for a preferred Bill of Laden date
Berthing, Hose handling, Document delivery & signing only carried out in the day
Pump Failure, Tank readiness, Fiscalisation delays, etc
Ships waiting to load based on offtake program