## Summary
S/N | Wave ID (if available) | Asset | Initiative Title | Brief Description | Owner | Expected Date of Realisation | Potential Value to be Realized ($'Mln) | Value Realized to Date ($'Mln) | Current Status | Next Steps
1 |  | Central East | Optimize Maintenance Activities | Risk-based execution of maintenance activities following the deviation process as appropriate. | Osita/Terfa | 31st Dec 2020 | 4 | 1 | Ongoing. 1 flowline replacement activity following MOC process. | Track progress and savings.
2 |  | Central East | Defer Belema Re-entry | Defer re-entry pending improvement in fiscal conditions. | Valentine O | 31st Dec 2020 | 3.2 |  | Re-entry activities currently suspended
3 |  | Central East | Reduction in Field Allowances | Lower BMM allowances due to reduced manning levels across the Asset. | Terfa I. | 31st Oct 2020 | 1.1 |  | Latest timesheets submitted for April month. | Track actual against plan for April for baseline.
4 |  | Central East | Chemicals Optimization | Optimize chemical use in light of lower production and following bulkline/flowline inspection regimes | Okahia V. | 30th Nov 2020 | 0.9 |  | Expecting results of inspections to implement recommendations. | Track progress and savings
5 | 23331 | West | Reduction of 2 Security Vessels | Reduce infield security vessels fleet from 9 to 7 within the West. | Chris/Arthur | 30th April 2020 | 6.5 | 6.5 | Vessels dropped. | Track savings & mitigate exposures.
6 | 23338 | West | Reduction of Expats within the West and Upskilling of Local Manpower | Upskill 10 nos. of loca Manpower to optimize on expats callout. | Chris/Arthur | 30th May 2020 | 1.3 | 1.3 | Replacement locals Identified, gap assessment ongoing. | Ascertain cost of upskilling and expected value to be realized
7 |  | West | Sea Watchers Contracts Reduction | Reduce sea watchers contracts across the nodes. | Ada/Uche | 30th June 2020 | 0.375 |  | Scope optimisation review with Security & ER ongoing. | Conclude scope optimisation review with Security & ER ongoing.
8 | 23344 | West | Recertification of Bulk Chemical Tanks | Recertify bulk chemical tanks to eliminate hiring of 9nos chemical tanks in EA, | Chris | 30th June 2020 | 0.33 |  | Tanks identified, commercial discussions concluded, and budget secured, | Finalize contracting modalities: BMM vs Intels; PO for recertification to follow.
9 | 20554 | Land | Achieve 5% Savings on OPEX Budget by Nov. 2020 | 1. Cut down AGO consumption by 40% by fixing G/gen in the facilities to ensure reliability and availability at Agbada/Obigbo PU. 2. Monitor and align Agbada/Obigbo quarterly chemical requests within $150K using Asset Optimization meeting. 3. Optimize chemical consumption by carrying out proper utilization campaign @ Imor/Okoloma & Rumuahia PUs. | Ebere Onoh | 30th Dec 2020 | 1.25 |  | L3: Solution known -approved for implementation. | Continue the review of transaction listings and chargebacks in view of the minimum manning for the month of April and calculate the savings achieved.
10 | 20774 | Land | Optimize Afam-VI OPEX cost to save $450k by Dec 2020 (10%) | 1. Challenge the cost reimbursable of spares from NETCO DIETSMANN COMPANY LTD. | Folarin Vincent | 31st Dec 2020 | 0.45 |  | L3: Solution known -approved for implementation | ATE review process is ongoing
11 | 20781 | Land | Reconcile O&M Contract Payables for 2015 to 2019 at AFAM-VI Power Plant to Realise $350K by April 2020 | The contract rates associated with this contract are reviewed after every contract year but the new rates don't get loaded in SAP on time by the C&P team so the old rates continue to be used. Over time, this practice has resulted in over-payments to the contractor. This anomaly has been identified and addressed with the contractor; contractor has agreed to issue credit notes to refund the over-payments. | Folarin Vincent | 30th May 2020 | 0.35 | 0.4 | L5: Value realized | Closed
|  |  | Total |  |  |  | 19.755 | 9.2