## Overall plan
SOKU AGG IMPROVEMENT (#18)
SN | ACTIVITY | Start | Finish | Remarks | 2017 | [11 empty] | 2018 | [11 empty] | Legend
[5 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | Done
LP NAG (SPECIFIC) | [28 empty] | In Progress
1 | Carryout 8K inspection | [27 empty] | Yet to start | bar: 2017 O
2 | Issue PO to /Exterran GKN for PT changeout | bar: 2017 O
3 | Carryout 4k inspection | bar: 2018 A
4 | Remove AG3 PT and do other pre-works | bar: 2017 N
5 | Carryout PT changeout | bar: 2017 N to 2017 D
AG-2 (SPECIFIC)
1 | Carryout 8K inspection | bar: 2017 O
2 | Order and receive Astrocell filters | bar: 2017 N
3 | Carryout pre-startup checks | bar: 2017 N
4 | Install filters and startup unit | bar: 2017 N
5 | Stabilise AG-2 | bar: 2017 D to 2018 F
6 | Carryout 4k inspection | bar: 2018 A
COMPETENCE |  |  |  | 1. Improve Response time to failure 2. Early identification of imminent failures and taking proactive measures. 3. Improve competence and confidence of Soku personnel.
1 | Field Operators FLM competence development and Equipment Ownership | 2017-05-02 | 2017-05-31 | bar: 2017 M
2 | Field Technicians O & M competence development with Solar FSR | 2017-06-01 | 2017-06-27 | bar: 2017 J; 2017 N to 2018 F
2 | Field Technicians O & M competence development with GKN FSR | 2017-06-01 | 2017-06-27 | bar: 2017 D; 2018 A
SPARES/CONSUMABLES |  |  |  | Improve response time after equipment failure (reduce MTTR)
1 | Review and order turbine consumables | bar: 2017 N
2 | Review and order turbine critical spares | bar: 2017 N
3 | Review of Ancillaries Maitenance Plans | bar: 2017 O to 2018 M
4 | Set up min/max values in SAP for consumables | bar: 2017 N
5 | Place order for 2018 overhaul spares | bar: 2018 J
6 | Code spares without SAP numbers | bar: 2017 N to 2018 M
7 | Follow-up on ordered materials | bar: 2017 N to 2018 J
8 | Receive ordered spares | bar: 2018 M to 2018 J
ON/OFF SKID INSTRUMENTATION AND ANCILLARY REFURBISHMENT |  |  |  | Improve availability and increase MTBF
1 | Compile list of items to be changed-out | bar: 2018 F
2 | Put a contract in place for instrumentation upgrade | bar: 2018 A
3 | Changeout old/unreliable items | bar: 2018 J
TECHNICAL SUPPORT |  |  |  | 1. Improve FLM on the equipment 2. Improve response time after equipment failure (reduce MTTR)
1 | Deploy two AGG Tech to support Asset team | bar: 2017 M
2 | Put 2 GKN FSRs on 'hot standby' | bar: 2018 J
3 | Get GKN and Siemens FSRs to do healthchecks | bar: 2018 J
4 | Obtain contract for GKN quick support | bar: 2018 J
HANDOVER TO ASSET
1 | Develop a Roles/Responsibilities “RASCI” document signed-off jointly by Asset and MRTA leadership | bar: 2018 J to 2018 F
2 | Handover consumables and critical spares to Asset | bar: 2018 J

## Chart (hidden)
SOKU AGG IMPROVEMENT (#18)
SN | ACTIVITY | Plan | Actual |  |  | 2017 | [11 empty] | 2018
[6 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
1 | Carryout 8K inspection | 1 | 1 | bar: 2017 O
2 | Issue PO to /Exterran GKN for PT changeout | 1 | 1 | bar: 2017 O
3 | Carryout 4k inspection | bar: 2018 A
4 | Remove AG3 PT and do other pre-works | 1 | 1 | bar: 2017 N
5 | Carryout PT changeout | 1 | 1 | bar: 2017 N to 2017 D
1 | Carryout 8K inspection | 1 | 1 | bar: 2017 O
2 | Order and receive Astrocell filters | 1 | 1 | bar: 2017 N
3 | Carryout pre-startup checks | 1 | 1 | bar: 2017 N
4 | Install filters and startup unit | 1 | 1 | bar: 2017 N
5 | Carryout 4k inspection | bar: 2018 A
6 | Order on-skid and off-skid valves | bar: 2018 F
7 | Changeout on-skid and off-skid valves | 1 | 1 | bar: 2018 M
1 | Field Operators FLM competence development and Equipment Ownership | 1 | 1 | bar: 2017 M
2 | Field Technicians O & M competence development with FSR | 1 | 1 | bar: 2017 J; 2017 N to 2018 J
1 | Review and order turbine consumables | 1 | 1 | bar: 2017 N
2 | Review and order turbine critical spares | 1 | 1 | bar: 2017 N
3 | Review of Ancillaries Maitenance Plans | 1 | 1 | bar: 2017 O to 2018 M
4 | Set up min/max values in SAP for consumables | 1 | 1 | bar: 2017 N
5 | Code spares without SAP numbers | 1 | 1 | bar: 2017 N to 2018 M
6 | Follow-up on ordered materials | 1 | 1 | bar: 2017 N to 2018 J
1 | Deploy two AGG Tech to support Asset team | 1 | 1 | bar: 2017 M
2 | Put 2 GKN FSRs on 'hot standby' | 1 | 1 | bar: 2018 J
3 | Get GKN and Siemens FSRs to do healthchecks | 1 | 1 | bar: 2018 J
4 | Obtain contract for GKN quick support | 1 | 1 | bar: 2018 J
Legend
Done
In Progress
Yet to start
|  |  |  | Plan | Actual
|  |  |  | 1 | 1
|  |  |  | 2 | 2
|  |  |  | 2 | 2
|  |  |  | 3 | 3
|  |  |  | 4 | 4
|  |  |  | 5 | 5
|  |  |  | 6 | 6
|  |  |  | 7 | 7
|  |  |  | 8 | 8
|  |  |  | 8 | 8
|  |  |  | 8 | 8
|  |  |  | 9 | 9
|  |  |  | 10 | 10
|  |  |  | 11 | 11
|  |  |  | 12 | 12
|  |  |  | 13 | 13
|  |  |  | 14 | 14
|  |  |  | 15 | 15
|  |  |  | 16 | 16
|  |  |  | 17 | 17
|  |  |  | 18 | 18
|  |  |  | 19 | 19
|  |  |  | 20 | 20
|  |  |  | 21 | 21