## Sheet1
| Activity Category | Activity | Start Date | End Date | Lead time | Action Party | Comments
| Assessment of GC installations |  | 2017-05-10 | 2017-07-05
|  | Arrange for emergency barge movement to Soku to deliver GC (if required) |  | 2017-05-10
|  | Book AOS Orwell FSR to field |  | 2017-05-15
|  | Issue PO for Welker probe |  | 2017-05-10
|  | Issue PO for to AOS Orwellfor Lagging |  | 2017-05-10
|  | Share PIP for the GCs |  | 2017-05-24
|  | Produce GC assessment report |  | 2017-06-07
|  | Soku |  | 2017-06-07
|  | Gbaran |  | 2017-06-07
|  | EA |  | 2017-06-07
|  | BNAG |  | 2017-06-07
|  | Spares Assessment |  | 2017-06-28
|  | Assessment of contract support |  | 2017-06-28
|  | Produce GC Installations gap report |  | 2017-07-05
| Close Hardware gaps in GC installations |  | 2017-07-05 | 2017-10-03
|  | Place order for required spares |  | 2017-10-03
|  | Correct hardware gaps |  | 2017-09-03
|  | Code material in SAP |  | 2017-08-04
|  | Order to stock |  | 2017-09-24
|  | Procure consumables |  | 2017-11-08
| Restore Soku GC Installation |  | 2017-04-28 | 2017-05-05
|  | Confirm Availability of Carrier Gas at Soku |  | 2017-05-05
|  | Confirm Availibility of Calibration Gas in Soku |  | 2017-05-05
|  | Contact Okoloma /Gbaran for Calibration Gas if not available at Soku (Plan B) |  | 2017-05-05
|  | Raise MoC for installation (confirm requirement) |  | 2017-05-12
|  | Order New Calibration Gas Soku |  | 2017-09-02
|  | New GCs on site |  | 2017-05-15
|  | Wekker Probes |  | 2017-05-19
|  | Mobilize contract to site for installation |  | 19/05/2017
|  | Installation |  | 2017-05-29
|  | Commissioning |  | 2017-05-31
|  | Training & Handover |  | 2017-06-02
|  | Develop Calibration / Validation Procedure |  | 2017-06-16
|  | Hand Holding (FLM) |  | 2017-06-23
|  | Hand Holding (4 Calibrations) |  | 2017-08-15
|  | Update As-built |  | 2017-09-14
| Improve FLM Check sheets & Implement |  | 2017-05-24 | 2017-06-21
|  | Review existing Checksheet based on new installation |  | 2017-06-21
|  | Coduct training |  | 2017-07-12
|  | BNAG |  | 2017-07-12
|  | EA |  | 2017-07-12
|  | Gbaran |  | 2017-07-12
| Renew contract for GC support | Raise Part A |  | 2017-07-12
| Renew contract for GC support | Award Contract |  | 2017-07-26
| Review GC Mtc & Validation procedures |  | 2017-05-24 | 2017-06-07
|  | Make existing procedures site specific |  | 2017-06-07
|  | Train operators |  | 2017-06-14
|  | BNAG |  | 2017-06-14
|  | EA |  | 2017-06-14
|  | Gbaran |  | 2017-06-14
Last Week
| Activity | Status | Lessons Learnt
| Complete cadence tracking sheet & set up project in WAVE | Project Plan developed. Project not loaded in WAVE
| Follow up on materials on order for Soku GC installation. | GC in country with contractor, awaiting OEM documentation before delivery SPDC Weeker Probe delivery confirmed for 12th May | Difficulty tieing vendors down to a delivery date
| Set up team for GC installations assessment across NLNG Supply facilities | Decision taken to use Metering Techs in asset to conduct assessment | Consult Subject Matter Expert
| Develop GC assessment template based on Position Improvement Plan by CMD | Not required according to CMD: GC assessment report produced for each asset adequate | Consult Subject Matter Expert
Next Week
| Activity Category | Activity | Start Date | End Date | Lead time | Action Party
| Set Up Project | Attend WAVE training & load project in WAVE
Phase 1 | Complete Soku GC Installation | Confirm Availability of Carrier Gas at Soku | 2017-04-28 | 2017-05-05 | 7 days | Solomon / Alabuja | Carrier Gas available on site
Phase 1 |  | Confirm Availibility of Calibration Gas in Soku | 2017-04-28 | 2017-05-05 | 7 days | Solomon / Alabuja | 3 bottles available in PH. To be shipped with GC to Soku
Phase 1 |  | Contact Okoloma /Gbaran for Calibration Gas if not available at Soku (Plan B) | 2017-04-28 | 2017-05-05 | 7 days | Arash | not required
Phase 1 |  | Raise MoC for installation (confirm requirement) | 2017-04-28 | 2017-05-12 | 14 days | Alabuja / Chimuanya/Yisa | request made to asset to raise MoC
Phase 1 |  | Order New Calibration Gas Soku | 2017-05-05 | 2017-09-02 | 120 days | Solomon | Enquiry made to vendor
Phase 1 |  | New GCs on site | 2017-05-10 | 2017-05-15 | 5 days | Solomon | on course for delivery by 12th
Phase 1 | Assessment of GC installations | Share PIP for the GCs with team | 2017-05-10 | 2017-05-24 | 14 days | Arash
Help Required
Formulas:
End Date = [Start Date]+7

## Next Week
| Activity Category | Activity | Start Date | End Date | Lead time | Action Party
Phase 1 | Complete Soku GC Installation | Confirm Availability of Carrier Gas at Soku | 2017-04-28 | 2017-05-05 | 7 days | Solomon / Alabuja
Phase 1 |  | Confirm Availibility of Calibration Gas in Soku | 2017-04-28 | 2017-05-05 | 7 days | Solomon / Alabuja
Phase 1 |  | Contact Okoloma /Gbaran for Calibration Gas if not available at Soku (Plan B) | 2017-04-28 | 2017-05-05 | 7 days | Arash
Phase 1 |  | Raise MoC for installation (confirm requirement) | 2017-04-28 | 2017-05-12 | 14 days | Alabuja / Chimuanya/Yisa
Phase 1 |  | Order New Calibration Gas Soku | 2017-05-05 | 2017-09-02 | 120 days | Solomon
Phase 1 |  | New GCs on site | 2017-05-10 | 2017-05-15 | 5 days | Solomon
Phase 1 | Assessment of GC installations | Share PIP for the GCs | 2017-05-10 | 2017-05-24 | 14 days | Arash
Formulas:
End Date = [Start Date]+7

## Sheet3
Complete cadence tracking sheet & set up project in WAVE
Follow up on materials on order for Soku GC installation.
Set up team for GC installations assessment across NLNG Supply facilities
Develop GC assessment template based on Position Improvement Plan by CMD