## Slide 1: Project title : Gas Chromatography (GC) Availability Improvement
Cadence Weekly Review 2017
Project Lead: Dada Olayinka

## Slide 2: Gas Chromatography (GC) PROJECT BACKGROUND
  Problem Statement: SPDC loses circa $4m/month (Gbaran = $3m/mth, BNAG =$67k/mth, Soku = $1m/mth Est) whenever GCs are out & we revert to keypad values on the NLNG supply chain.
  Plan is to improve and sustain the availability of Gas Chromatography Systems in the NLNG supply chain at similar level as EA (95%) by end 2017
  PHASE 1: Restore Performance
    Assessment of GC installation against PIP (Position Improvement Plan by CMD) to identify gaps
    Restore units that are out of service (Soku)
    Close hardware gaps identified in the installations.
  PHASE 2: Sustain Performance
    Retrain staff on operations and maintenance routines to
      Improve quality of Frontline Maintenance (FLM) practices
      Improve quality of Routine Maintenance and Validation activities
    Ensure availability of spares & consumables
    Provide Specialist Operations and Support contract.
  PHASE 3: Upgrade GC (Not in scope of Cadence)

## Slide 3: Project Timeline
Activity | Apr’17 | May’17 | Jun’17 | Jul’17 | Aug’17 | Sep‘17 | Oct’17 | Nov’17 | Dec’17 | Remarks
Complete Soku GC Installation |  |  |  |  |  |  |  |  |  | 
Assessment of GC installations |  |  |  |  |  |  |  |  |  | 
Close Hardware gaps in GC installations |  |  |  |  |  |  |  |  |  | 
Improve FLM Check sheets & Implement |  |  |  |  |  |  |  |  |  | 
Review GC Mtc & Validation routines & implement. |  |  |  |  |  |  |  |  |  | 
Renew contract for GC support |  |  |  |  |  |  |  |  |  | 
On site staff retraining on routines |  |  |  |  |  |  |  |  |  | 

## Slide 4: Deliverables for Last Week
Obtain Corporate Metering Support for plan (concluded)
Follow up on materials on order for Soku GC installation. (Delivery of new Soku GCs 5th May 2017)
Develop Cadence Tracking Sheet (started)

## Slide 5: Deliverables for Next Week
Complete cadence tracking sheet & set up project in WAVE
Follow up on materials on order for Soku GC installation.
Set up team for GC installations assessment across NLNG Supply facilities
Develop GC assessment template based on Position Improvement Plan by CMD

## Slide 6: SUPPORT REQUIRED
Access to WAVE & training
Hub Support: budget for gap closure where needed
Hub support: Staff availability for training.

## Slide 8: GC Availability
 | Availability (%) |  | 
 | 2015 | 2016 | 2017 YTD
EA | 97% | 95% | 100%
Gbaran GP | NA | 46% | 98%
BNAG | NA | NA | NA
Soku | NA | NA | NA

## Slide 9: BNAG Daily GHV (MJ/sm3) Trend March 2016
Keypad GHV = 37.18mj/sm3
Ave. GHV With GC restored = 37.61mj/sm3
% Gain by Restoring GC = 1.2%
This translates to 1.2% gain in Energy and Subsequent gain in revenue
Chart: BNAG Daily GHV (MJ/sm3) Trend March 2016
| 42430 | 42431 | 42432 | 42433 | 42434 | 42435 | 42436 | 42437 | 42438 | 42439 | 42440 | 42441 | 42442 | 42443 | 42444 | 42445 | 42446 | 42447 | 42448 | 42449 | 42450 | 42451 | 42452 | 42453 | 42454 | 42455 | 42456 | 42457 | 42458 | 42459 | 42460
Daily GHV (MJ/sm3) | 37.2732 | 37.2782 | 37.1273 | 37.2132 | 37.1517 | 37.2053 | 37.2014 | 36.9366 | 37.1622 | 37.2011 | 37.1959 | 37.1643 | 37.2107 | 37.207 | 37.2096 | 37.1987 | 37.1726 | 37.2244 | 37.2315 | 37.4922 | 37.6447 | 37.6484 | 37.7888 | 37.7557 | 37.6203 | 37.622 | 37.5652 | 37.6165 | 37.6053 | 37.5224 | 37.4784

## Slide 10: GU Feb 2017 Daily GHV Trend
Chart: 
| 42767 | 42768 | 42769 | 42770 | 42771 | 42772 | 42773 | 42774 | 42775 | 42776 | 42777 | 42778 | 42779 | 42780 | 42781 | 42782 | 42783 | 42784 | 42785 | 42786 | 42787 | 42788 | 42789 | 42790 | 42791 | 42792 | 42793 | 42794
 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.5222 | 40.522 | 40.7302 | 41.262 | 41.7668 | 42.2709 | 42.1522 | 42.2662 | 42.3424
GU ON KEYPAD COMPOSITION VALIE (KEYPAD)- GC Offline
GU GC restored: GHV now based on dynamic composition value
Keypad GHV = 40.52mj/sm3
Ave. GHV With GC restored = 42.01mj/sm3
% Gain by Restoring GC = 3.7%
This translates to 3.7% gain in Energy and Subsequent gain in revenue