## Sustain NLNG GC
Sustain Availability of GC on NLNG Supply Network
Production Gain | Wildly Important Goal: Sustain Availability of GC on NLNG Supply Network
Target Condition: Sustain Availability of 95% by end 2017
Progress Graph 1: Improve plan stability from 34% to 90% by Dec17 |  | Steps
|  | KEY DELIVERABLES | ACTIVITIES | STATUS/COMMENTS |  |  | A | S | O | N | D | J | F | M | A | J | J
|  | Procedures & Work Practices | Confirm all GCs are in SAP | List of GCs in SAP | 2017-09-04 | Godfrey
|  |  | Confirm Maintenance Plan atached to GCs in SAP | List of Maintenance plans on GCs | 2017-09-04 | Godfrey
|  |  | Ensure work procedures are Fit-for-purpose. Review & update | Review MJRs | 2017-10-05 | Godfrey
|  |  | Upload reviewed procedures and MJRs in SAP |  | 2017-11-11 | Dada
|  |  | Confirm activities in RACI feed into work process of responsible parties. | Full utilization of SAP, Healthchecks and Audit | 2017-11-05 | Godfrey
Progress Graph 2: Reduce number of activities not executed due to logistics/MM inability to meet demand to zero |  | Clear roles & Responsibilities | DevelopRACI for Operations & Maintenance of GC | RACI Chart | 2017-10-05 | Godfrey
|  |  | Approve RACI | Signed-off document | 2017-10-30 | Godfrey
|  |  | Communicate RACI | Presentation pack and communication plan | 2017-11-07 | Godfrey
|  | Make Spares Availble | Review spares list | Position Improvement Paper
Propose Stock levels
Code in SAP
|  |  | Make spares available onsite visible to other locations | List ofspares available with CMD | 2017-09-30 | Dada
|  |  | Issue PO for the procurement of stock items for GC |  | 2017-08-31 | Dada
|  |  | Raise WO for Consumables per location | reconsiderd on site stocking | 2017-09-15 | Dada
|  | Make Contracts Available | Identify gaps in contracts required to ensure GC availability | No gaps. support contracts available
|  |  | Close gaps in contracts | Not reqd
|  | Make Competent Staff Available | GC Level 1 and Level 2 maintenance training at the OEM facility | Gbaran / BNAG planned for Q1 2018 - Soku Q2 2018
|  |  | GC competencies reflected in IDP for 2018 | Do mail to PUM to raise GC competence issues in IDP discussion | 2017-11-30 | Dada
|  |  | Publish training plan from L&D to close competence Gap in 2018 | Train staff from 2018 | 2017-12-15 | Dada
|  |  | Develop Check Sheet & include in training Pack |  | 2017-09-30 | Godfrey
|  |  | Develop Operations/Validation Procedure Soku (Siemens) |  | 2017-09-30 | Godfrey
|  |  | Develop Operations/Validation Procedure Soku (Emerson) |  | 2017-09-30 | Godfrey
Training pack - Basic Troubleshooting & Maintenance (Soku)
Training pack - Basic Troubleshooting & Maintenance (Gbaran)
Training pack - Basic Troubleshooting & Maintenance (BNAG)
|  |  | Develop plan for monthly "Handholding" site visit by CMD | Visit initiated.
|  | Resolve existing hardware issues | Produce GC assessment report
Review of Assessment report with asset
Develop close out plan for Hardware issues
|  |  | Report HVAC availability and effectiveness to CMD for escalation |  | 2017-09-30 | Godfrey