## UPS IMPLEMENTATION PLAN
UPS IMPLIMENTATION PLAN
Disconnection of cable Terminal and Tag
Disconnection of Old UPS Machines
Removing of Old UPS from the base
Positioning of New UPS machines
Cable Laying
Installation of Control Systems
Termination
Battery Integrity Test
UPS Testing
COmmissioning & Handover
Pre commissiong checks
Battery paralled Voltage checks
Switching Checks
UPS Start Up
Voltage Checks
Output Checks
Power Autonomy Checks
Demobilization & Site Cleean Up
SoF Sign off
Commissioning & Handover
Demobilization & Site Cleean Up