## FCF
September - October
OIL | 2019 |  | Export Gas | 2019 |  | DOMGAS | 2019
Oil Impact |  |  | Oil Impact |  |  | Oil Impact
Capex | 0
Capital Allwce | 0
Oil price | 66.247 | Based on the BP price . | Gas price | 1.637 | Based on the BP price . | Gas price | 2.53 | Based on the BP price .
No of days | 61 |  | No of days | 61 |  | No of days | 61
Production in Kboe/d | 0.6 | Based on BP Target | Production in Kboe/d | 1.5517 | Based on BP Target | Production in Kboe/d |  | Based on BP Target
Total Oil production (bbls) | 36600 |  | Total gas production (bbls) | 94655.1724 |  | Total gas production (bbls) | 0
Impact on revenue ($) | 2424640.2 |  | Impact on revenue ($) | 898713 |  | Impact on revenue ($) | 0
Royalties on Oil | -484928.04 | Based on 20% royalty rate for oil. | Royalties on Gas | -62909.91 | Based on 7% royalty rate for Gas. | Royalties on Gas | 0 | Based on 7% royalty rate for Gas.
Cost | -17000 |  | Cost | 0 |  | Cost | 0
Ullage revenue |  |  | Ullage revenue |  |  | Ullage revenue
Depreciation |  |  | Depreciation |  |  | Depreciation | 0
Pre-Tax impact | 1922712.16 |  | Pre-Tax impact | 835803.09 |  | Pre-Tax impact | 0
Tax impact on Oil production | -245145.8004 | Based on SPDC Minimum tax rate of 12.75% | Tax impact on Gas production | -250740.927 |  | Tax impact on Gas production | 0
NIBIAT Impact (After Tax) in $ | 1677566.3596 |  | NIBIAT Impact (After Tax) in $ | 585062.163 |  | NIBIAT Impact (After Tax) in $ | 0
CSD Impact( Nibiat + depreciation) | 1677566.3596 | (help) | CSD Impact( Nibiat + depreciation) | 585062.163 | (help) | CSD Impact( Nibiat + depreciation) | 0 | (help)
Capex
Capital Allwce tax shield | 0
FCF 100% | 1677566.3596
FCF SS | 503269.9079 |  | CSD Impact( SS) | 175518.6489 |  | CSD SS | 0
Total (Oil + Gas) SS | 678788.5568
Monthly for Sept and Oct | 339394.2784
November - December
OIL | 2019 |  | Export Gas | 2019 |  | DOMGAS | 2019
Oil Impact |  |  | Oil Impact |  |  | Oil Impact
Capex | 0
Capital Allwce | 0
Oil price | 66.247 | Based on the BP price . | Gas price | 1.637 | Based on the BP price . | Gas price | 2.53 | Based on the BP price .
No of days | 61 |  | No of days | 61 |  | No of days | 61
Production in Kboe/d | 2 | Based on BP Target | Production in Kboe/d | 5.1724 | Based on BP Target | Production in Kboe/d |  | Based on BP Target
Total Oil production (bbls) | 122000 |  | Total gas production (bbls) | 315517.2414 |  | Total gas production (bbls) | 0
Impact on revenue ($) | 8082134 |  | Impact on revenue ($) | 2995710 |  | Impact on revenue ($) | 0
Royalties on Oil | -1616426.8 | Based on 20% royalty rate for oil. | Royalties on Gas | -209699.7 | Based on 7% royalty rate for Gas. | Royalties on Gas | 0 | Based on 7% royalty rate for Gas.
Cost | -181000 |  | Cost | 0 |  | Cost | 0
Ullage revenue |  |  | Ullage revenue |  |  | Ullage revenue
Depreciation |  |  | Depreciation |  |  | Depreciation | 0
Pre-Tax impact | 6284707.2 |  | Pre-Tax impact | 2786010.3 |  | Pre-Tax impact | 0
Tax impact on Oil production | -801300.168 | Based on SPDC Minimum tax rate of 12.75% | Tax impact on Gas production | -835803.09 |  | Tax impact on Gas production | 0
NIBIAT Impact (After Tax) in $ | 5483407.032 |  | NIBIAT Impact (After Tax) in $ | 1950207.21 |  | NIBIAT Impact (After Tax) in $ | 0
CSD Impact( Nibiat + depreciation) | 5483407.032 | (help) | CSD Impact( Nibiat + depreciation) | 1950207.21 | (help) | CSD Impact( Nibiat + depreciation) | 0 | (help)
Capex
Capital Allwce tax shield | 0
FCF 100% | 5483407.032
FCF SS | 1645022.1096 |  | CSD Impact( SS) | 585062.163 |  | CSD SS | 0
Total (Oil + Gas) SS | 2230084.2726
Monthly for Nov and Dec | 1115042.1363

## Details
b | Project Title
(GD19) Increase K2S Production Availability from 85% to 95% by Q1 2020 by addressing Link and Power issues
Business Case:
Review of key Availability drivers of the Kolo Creek to Soku (K2S) Production stream conducted in April/May 2019 revealed ample opportunities to improve efficiencies in the power supply system and data communication link.
Expected Business Outcome
Increased Production Availability (30mmscfd + 2kbopd)
Lower OPEX year-on- year (reduced cost of intervention and restarts)
Waste (rework) Elimination
Cost of Execution: USD200,000
| L3 - | 31/8/2019
| L4 - | 31/01/2020
1 | List of wells involved and their production
S/N | Description | Start Date | Start Date | Cost of Execution (F$k) | Date spent/To be spent | Value realised or to be realised(Bopd) | Date at which value was realised | Cumm Oil Kbod | Cumm Gas MMScfd
1 | End-to-end review of system vulnerabilities | 2019-04-24 | 2019-05-28 | 1 | 2019-04-01 | 0
2 | Finalise CTR | 2019-07-31 | 2019-08-15 | 1 | 2019-07-01 | 0
3 | Fix Link/devices redundancy and fall-back issues | 2019-08-05 | 2019-09-30 | 10 | 2019-08-01 | 0.5 | Sept
4 | Enable remote diagnostics capability for data communication hardware | 2019-08-10 | 2019-09-30 | 5 | 2019-08-01 | 0.1 | Sept | 0.6 | 9
5 | Fix Power supply vulnerabilities (synchronization of MGG & SDG) | 2019-08-12 | 2019-10-30 | 60 | 2019-10-01 | 0.5 | Nov
6 | Configure alarms for communication link failure on Soku and Kolocreek PACO systems; optimize link outage time-out setting | 2019-08-12 | 2019-11-30 | 20 | 2019-10-01 | 0.2 | Nov
7 | Configure secondary OPC server to communicate with GSGW | 2019-08-31 | 2019-11-30 | 100 | 2019-10-01 | 0.7 | Nov | 2 | 30
8 | Conduct end-to-end systems test to verify that the desired performance standard has been met | 2019-12-01 | 2020-01-13 | 1 | 2019-12-01 | 0
2
2.3333
Business Case:
Review of key Availability drivers of the Kolo Creek to Soku (K2S) Production stream conducted in April/May 2019 revealed ample opportunities to improve efficiencies in the power supply system and data communication link.
Expected Business Outcome
Increased Production Availability (30mmscfd + 2kbopd)
Lower OPEX year-on- year (reduced cost of intervention and restarts)
Waste (rework) Elimination
Cost of Execution: USD200,000