## Estimate
| WBS report |  |  |  | Confidential
LP NAG to AG2_190218
Estimate Name: |  | LP NAG to AG2_190218 | Estimation Set: | Q4 2017 Upstream - EDM 2016 (2.3) |  | Estimate State: | Not approved
Type: |  | Type 2 | Cem Set: | CS (2.3) |  | Created At: | 19 Feb 2018
Project ORP Phase: |  | DG2 | Quantity Set: | QS (2.3) |  | Created By: | Okuboere R Diete-Spiff
Currency: |  | USD | Cost Data Set: | CDS Q4 2017 - EDM 2016 (2.3) |  | Last Modified At: | 19 Feb 2018
Order of Magnitude: |  | Millions | Cost Calculation Model: | 14 Steps Upstream [2.3] |  | Last Modified By: | Okuboere R Diete-Spiff
Measurement System: |  | Metric system | World Table: | LGSP WT |  | Imported At:
Office Location: |  | Port Harcourt | EDM Date: | 2016-12-31 |  | Imported By:
Business Type: |  | Upstream | Site location: | Nigeria
Prospect Name: |  | SPDC Onshore & Shallow Offshore | Cost Location: | Nigeria
Prospect Number: |  | PH-15-000240 | Final Investment Decision: | Apr 2018
|  |  | Ready For Startup: | Sep 2018
Estimate Number: |  | PH-US-18-001053
Project ID: |  |  | Accuracy (P10): | -20 %
Description: |  |  | Accuracy (P90): | 30 %
|  |  | Execution Strategy: | Brownfield
|  |  | Market Scenario: | CM
|  |  | Project category: | Onshore Upstream
|  |  | Project size: | < 100 mln USD (Material)

## Cost Summary
Cost Summary table for Scope Item: LP NAG to AG2_190218.
Description | Percentage | Cost (M USD)
Cost at location (EDM) |  | 0.26633
Freight & handling | 5.206% | 0.013866
Duties | 2.725% | 0.007635
EPC Base Estimate (EDM) |  | 0.28783
Market Escalation (USD based) | 0.4187% | 0.0012051
EPC Scope Base Estimate (EDM) |  | 0.28904
Contingency | 15% | 0.043356
EPC Scope P50 Estimate (EDM) |  | 0.3324
Owner's cost (Select and define) | 0% | 0
Owner's cost (Project execution team) | 0% | 0
Owner's cost (Detailed engineering) | 0% | 0
Owner's cost (Other) | 10% | 0.028904
Project P50 Estimate (EDM) |  | 0.3613
Inflation | 13.8% | 0.049854
Foreign exchange impact | -10.46% | -0.037797
Project P50 Estimate (MOD) |  | 0.37336

## WBS Report
WBS table for Scope Item: LP NAG to AG2_190218.
Scope Item | Effective count | Cost at Location (M USD)
LP NAG to AG2_190218 | 1 | 0.26633
Directly by LP NAG to AG2_190218 |  | 0
LP NAG to AG2 | 1 | 0.25383
Directly by LP NAG to AG2 |  | 0
Generic process system | 1 | 0.25101
Directly by Generic process system |  | 0.25101
Secondary power distribution | 1 | 0
Directly by Secondary power distribution |  | 0
DCS/SGS/FGS | 1 | 0.0028191
Directly by DCS/SGS/FGS |  | 0.0028191
Brownfield modification & Integration works | 1 | 0.0125
Directly by Brownfield modification & Integration works |  | 0.0125

## LP NAG to AG2
Routing of LP NAG to AG2
S/N | Equipment | Nos | Unit Cost, '000 | Total Cost, '000 | Assumption | assumed cost phasing
1 | 10" x 100m CS Pipeline/Piping | 1 | 29 | 29 | 2017 Cost premise (assumed 10" 600#) | 100% in one year
2 | Line pipe fittings including Control Valves/Shut Down Valves/Relief Valves |  |  | 15 | Assumed half of Piping/Pipeline cost
5 | Brownfield & Integration with Existing Facilities-assume 1% | 1 | 0.44 | 0.44
| Total |  |  | 44.44