## Slide 1: GMP Cadence June 2017
Initiative 163: Disposal of Soku Produced Water via Soku017 &
Initiative 1938: BNAG Optimisation
Udoka Onuoha
WRFM Lead Swamp East Hub

## Slide 2
Initiative #163: Disposal of Soku Produced Water via Soku017
NCTL
Water to Reinjection well
Soku NAG Plant
HH Water level
Condensate Storage Tank

## Slide 3: Soku Produced Water Project Status
Last Week’s actions and status
Recalculate CSD and progress to L3
CSD recalculated and project progressed to L3
Sign off BfD
BfD sign off awaiting Concept TA2 availability
Sign off proposal for sub-surface scope
Subsurface proposal sign off ongoing, awaiting one
signatory.
Engage and secure DPR approval for project
Shell DPR Liaison is following up on the approval,
daily phone calls, slow progress.
Next Week’s actions
Complete BfD Sign off
Complete Subsurface proposal sign off
Follow up DPR approval, secure engagement slot if required.
Project Milestones
Impacts

## Slide 4
Initiative #1938: BNAG Optimisation

## Slide 5: BNAG Optimisation Project Status
Last Week’s actions and status
Review the MRT interim report and decide need for testing of outstanding BONN029T & BONT03T
Review ongoing, deliverability test for BONN029T &
BONN023T planned to commence next week.
Agree window for testing BONN029T & BONT03T if required from PMC.
Deliverability tests for 29T & 23T planned to
commence next week, need for 29T & 3T MRT to be
determined after the deliverability test.
Handover Initiative leadership to Dev. Function nominee.
Awaiting nominee’s completion of Wave training.
Next Week’s actions
Continue 29T & 23T deliverability testing – completion timeline is two weeks.
Project Milestones
Impacts