## OBELE SPEC
OBELE FLOWSTATION: 2017 RE-ENTRY
Date Assessed :-
|  | System Number | No missing parts or components / All parts replaced | Jointing integrity check - balanced bolting, good & right gaskets and no galvanic corrosion | PEFS,UEFS,Isometrics, Well completions, line-walked & marked up. All Valves and logic line up (tracing), NRV in right direction, NONC, LOLC, LOTO is ok. | PEFS,UEFS line-walk - All guages (PG, TG & FI, Avometers) and sensors in place, tagged, certified and not leaking. | Supports, gratings, foundation bolts & Clearances ok | Alignment ok | Clean internals - Desanding, no blocked NRVs, orifices, valves etc | Isolation requirements checked ok - fuses, switch gears, spades, spectacles, blinds and removable spools | Content colour coding, Visual controls, flow direction marking, red spectacle painting etc done | All repaired items re-ceritfied (hydrotesting, radiography etc) | Integrity Inspection | Linear and rotary motion checks, barring - no free-wheeling, jerking nor jamming stuck of valves & engines | Flow, Pressure, Level and Temparature sensors are communicating with their controllers | Process controllers & control elements (PCVs, LCVs, FCVs, speed governor etc) detect parameters changes and responds as intended | No leaks (fluid, energy & data) - system leak tested, cable integrity, earthing check | Integrity Restoration | Safeguarding alarms and trips work at the correct set points (pressure, level, temp, flow and vibration) | Process safeguarding system - CCU/Ava, RBP & ESD loop/call points functional | F&G system functional | Safety shutoff valves (SCSSSV, MSDVs etc) certified - do not pass / positive shut off. BDVs & RVs not passing when closed. | Manual tight shutoff valves not passing (wellhead valves, inlet manifold valves, etc) | Other Assurance task / test executed, (P or F) | All vessels PV certified | All RVs certified | UT & LRUTdone | Ex-rating inspection done / valid | Earth bonding / Ignition control checks done, okay | Corporate TIV verified | SCE Assurance | Operating permits are valid (e.g. DPR allowable, diesel storage, bunkering, radioactive sources, radio frequency,sewage treatment etc) | Environmental Compliance Monitoring | Permits and Statutory Compliance | Access control facilities are in place (e.g. wellhead fenced, door locks for Switchgear rooms) | Clear, identified, lighted and signaged emergency escape route and muster points - tested okay. | Station Bill, Lay out Plan, HAC drawings, Noise map done and pasted | Caution and danger notices, Wellhead labels, ROW markers, ER Numbers, Resuscitation Notice, CPR and AED Procedure in place & pasted | Emergency doors fitted with one-way locks and panic bars | Adequate lighting for night operations | Process and emergency alarms and beacons audible and visible -line of sight okay | Proximity of fire fighting & life saving equipt checked okay (extinguishers, etc) | Vibration level acceptable | Equipment, piping and cable trays adequately supported and vibration damped | Clear fire breaks | Bund wall / collection pit in place, checked leak proof | Overal cleanliness, no drips, no leaks, good housekeeping etc | HSSE | Personnel required available (staff, attendants, prod support, etc) | Personnel trained and certified competent (normal & abnormal situations mgt, ER etc) | Manpower | Manufacturer (OEM) / Support contract in place | Any changes (equipment, configuration etc) passed thro MoC, registered and updated in CMMS e.g. Z6 raised | CMMS checked, updated and activated live in SAP | Lifting, hoisting and transfer equipment available and certified valid | Maintenance access (including ladders & platforms), working space and laydown area is integral and free | No red items in facility status report, all deviations approved, no expired MoCs etc | Maintenability & OEM Contracts | Inventory of consumable spares & materials checked and adequate or on order | Temporary equipment / repair registered & MoCed | Special tools & PPE available (beans, bean spanners, valve handles, megger, insulation mats etc) | Spares and Special Tools | Chemicals, lubes and consumables are above re-order levels or on order. | MSDS / SHOC cards in place for all chemicals | First-fill adequate for equipment (e.g sump level okay, day tank level ok etc) | Chemicals & Lubes | Tier-1 documentation reviewed, available and up-to-date | For changes; confirm - Marked up AFC drawings - PEFS, UEFS, GAs, Single Line, C&E, RATS, Instrument Data Sheets, Loop diagrams, block diagrams etc all available on site. | Pre-Start Up Checklist in place and executed | Start Up Procedure reviewed | FLM log, Fault Register and other operational control registers active | RFC Documentation (non-HC systems) | Tier-1 documentation reviewed, up-to-date and available on site | All first re-fills in place - lube oils, hydraulic oil, corrosion inhibitor, demulsifier etc | Pre-Start Up Checks done and Cat A items all closed | RFOs & RFSUs signed - Ops, mtc, IT, Pipelines and other support teams | SoF | RFSU & RFO Documentation | Cause and Effects verified by Emergency Shutdown (ESD) Test. | System Started and running | Operates as intended without a trip for 72 hours continous | Commissioned | By System
| Weighting (xx/100) |  | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 13 | 5 | 5 | 5 | 5 | 20 | 3 | 3 | 3 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 2 |  | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 0.5 | 1 | 2 | 1 | 2 | 14 | 2 | 2 | 4 | 2 | 2 | 2 | 1 | 0.5 | 2 | 9.5 | 0.5 | 0.5 | 1 | 2 | 0.5 | 1 | 0.5 | 2 | 1 | 1 | 1 | 0.5 | 0.5 | 4 | 0.5 | 0.5 | 2 | 1 | 1 | 5 | 0.5 | 1 | 1 | 2.5 | 100
WELLS | [12 empty] | 94.87% |  |  |  |  | 100% | [12 empty] | 100% |  |  | 100% | [13 empty] | 100% |  |  | 100% | [6 empty] | 100% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 50% | [5 empty] | 10% |  |  |  | 1% | 90.36%
| Obele 6T |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Obele 1L |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Obele 1S |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
FLOWLINES | [12 empty] | 100% |  |  |  |  | 100% | [12 empty] | 90.91% |  |  | 100% | [13 empty] | 100% |  |  | 100% | [6 empty] | 100% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 50% | [5 empty] | 10% |  |  |  | 1% | 89.03%
| Obele 6T |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Obele 1L |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Obele 1S |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
INLET MANIFOLD | [12 empty] | 56.41% |  |  |  |  | 62.5% | [12 empty] | 87.88% |  |  | 100% | [13 empty] | 64.29% |  |  | 100% | [6 empty] | 71.05% |  |  |  | 75% |  |  |  | 83.33% | [5 empty] | 41.67% | [5 empty] | 8.333% |  |  |  | 1% | 66.19%
| Plug valves |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 7 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Header piping |  | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 6 | 1 | 1 | 4 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Manual isolation valves |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 7 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Master Shutdown Valves |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 8 | 0 | 1 | 1 | 0 | 10 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 16 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 0 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Guages |  | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 10 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 25 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 0 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Inlet Header Relief valves |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 9 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 15 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
VESSELS | [12 empty] | 92.37% |  |  |  |  | 64.58% | [12 empty] | 91.13% |  |  | 97.5% | [13 empty] | 82.44% |  |  | 100% | [6 empty] | 69.47% |  |  |  | 93.33% |  |  |  | 100% | [5 empty] | 50% | [5 empty] | 10% |  |  |  | 1% | 75.46%
| HP Separator | [11 empty] | 93.59% |  |  |  |  | 66.67% | [12 empty] | 82.58% |  |  | 100% | [13 empty] | 91.67% |  |  | 100% | [6 empty] | 68.42% |  |  |  | 91.67% |  |  |  | 100% | [5 empty] | 50% | [5 empty] | 10% |  |  |  | 1% | 75.36%
| Manual isolation valves |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Level indicator, sight glass |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Level control valve |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Pressure guages |  | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 11 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 0 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| HP Sep Relief valves |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 11 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Other devices (ancillairies) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 20 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 11 | 1 | 1 | 2 | 11 | 1 | 1 | 11 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 28 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 0 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Test Separator | [11 empty] | 91.35% |  |  |  |  | 75% | [12 empty] | 86.36% |  |  | 87.5% | [13 empty] | 93.75% |  |  | 100% | [6 empty] | 71.05% |  |  |  | 93.75% |  |  |  | 100% | [5 empty] | 50% | [5 empty] | 10% |  |  |  | 1% | 77.9%
| Rotron meter |  | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 9 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Daniel Orifice Fitting |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Manual isolation valves |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Level indicator, sight glass |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Level control valve |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Pressure guages |  | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 11 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 0 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Test SepRelief valves |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 11 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Other Device |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 14 | 1 | 1 | 2 | 11 | 1 | 1 | 11 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 28 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 0 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| LP Separator | [11 empty] | 93.59% |  |  |  |  | 66.67% | [12 empty] | 100% |  |  | 100% | [13 empty] | 91.67% |  |  | 100% | [6 empty] | 68.42% |  |  |  | 91.67% |  |  |  | 100% | [5 empty] | 50% | [5 empty] | 10% |  |  |  | 1% | 79.19%
| Manual isolation valves |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Level indicator, sight glass |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Level control valve |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Pressure guages |  | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 11 | 11 | 1 | 1 | 1 | 1 | 0 | 1 | 40 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 11 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 0 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| LP Sep Relief valves |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 11 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Other devices (ancillairies) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 14 | 1 | 1 | 2 | 11 | 1 | 1 | 11 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 28 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 0 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Surge Vessel | [11 empty] | 94.87% |  |  |  |  | 58.33% | [12 empty] | 102.6% |  |  | 100% | [13 empty] | 69.05% |  |  | 100% | [6 empty] | 68.42% |  |  |  | 95.83% |  |  |  | 100% | [5 empty] | 50% | [5 empty] | 10% |  |  |  | 1% | 75.18%
| Manual isolation valves |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Level indicator, sight glass |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Level control valve |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Pressure guages |  | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 11 | 11 | 1 | 1 | 1 | 1 | 0 | 1 | 40 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 11 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 0 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| SV Relief valves |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 11 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| SV recirculation system |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Pump suction header |  | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 11 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 0 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| FLKO Vessel | [11 empty] | 88.46% |  |  |  |  | 56.25% | [12 empty] | 84.09% |  |  | 100% | [13 empty] | 66.07% |  |  | 100% | [6 empty] | 71.05% |  |  |  | 93.75% |  |  |  | 100% | [5 empty] | 50% | [5 empty] | 10% |  |  |  | 1% | 69.65%
| Manual isolation valves |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Level indicator, sight glass |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Level control valve |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Other devices-SDV |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 8 | 0 | 1 | 1 | 0 | 10 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 14 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 0 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Level Switches |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 1 | 0 | 0 | 0 |  | 0.05 | 0 | 0 | 0.025
EXPORT PUMPS & METERING | [12 empty] | 93.16% |  |  |  |  | 88.89% | [12 empty] | 74.24% |  |  | 100% | [13 empty] | 88.89% |  |  | 100% | [6 empty] | 90.64% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 61.11% | [5 empty] | 60% |  |  |  | 56% | 84.12%
| EP1 | [11 empty] | 100% |  |  |  |  | 100% | [12 empty] | 93.94% |  |  | 100% | [13 empty] | 100% |  |  | 100% | [6 empty] | 100% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 75% | [5 empty] | 100% |  |  |  | 100% | 97.67%
| Visual checks |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| EP1 Relief valves |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| Other checks |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| EP 2 | [11 empty] | 89.74% |  |  |  |  | 91.67% | [12 empty] | 65.15% |  |  | 100% | [13 empty] | 83.33% |  |  | 100% | [6 empty] | 85.96% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 58.33% | [5 empty] | 40% |  |  |  | 34% | 79.35%
| Visual checks |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| EP2 Relief valves |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 9 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 13 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Other checks |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 10 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| EP 3 | [11 empty] | 89.74% |  |  |  |  | 75% | [8 empty] | 1 |  |  |  | 63.64% |  |  | 100% | [13 empty] | 83.33% |  |  | 100% | [6 empty] | 85.96% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 50% | [5 empty] | 40% |  |  |  | 34% | 75.35%
| Visual checks |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 1 | 19 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| EP3 Relief valves |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 9 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 13 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Other checks-safeguarding devises on pump |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 10 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
EXPORT METERING | [12 empty] | 83.08% |  |  |  |  | 70% | [12 empty] | 92.73% |  |  | 90% | [13 empty] | 74.29% |  |  | 100% | [6 empty] | 72.63% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 75% | [5 empty] | 10% |  |  |  | 1% | 75.83%
| PD Meter 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 11 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 1 | 1 | 1 | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| PD Meter 2 |  | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 9 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 |  | 0 | 1 | 1 | 1 | 1 |  | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Manual Isolation valves |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 7 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 1 | 1 | 1 | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Water cut Meter |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 0 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 1 | 1 | 1 | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Pressure Recorder) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 1 | 1 | 1 | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
GAS HEADERS | [12 empty] | 64.62% |  |  |  |  | 50% | [12 empty] | 66.36% |  |  | 100% | [13 empty] | 64.29% |  |  | 100% | [6 empty] | 74.74% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 37.5% | [5 empty] | 10% |  |  |  | 1% | 61.12%
| HP PCV |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 1.5 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| HP Header manual valves |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 7 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 17 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 1.5 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| LP PCV |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 1.5 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| LP Header manual valves |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 7 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 17 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 1.5 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Flare line low point drain |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 1.5 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
FLARE | [12 empty] | 60.26% |  |  |  |  | 75% | [12 empty] | 90.15% |  |  | 100% | [13 empty] | 90.48% |  |  | 16.67% | [6 empty] | 67.54% |  |  |  | 83.33% |  |  |  | 83.33% | [5 empty] | 31.25% | [5 empty] | 8.333% |  |  |  | 1% | 69.44%
| Venturi |  | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 9 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 1.5 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Flare tip |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 1.5 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Piping |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 1.5 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| RIS & Pilot |  | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 8 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 1.5 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| USM |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 0 | 1 | 1 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 19 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Bundwall integrity |  | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 4 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
SAFEGUARDING SYSTEM | [12 empty] | 98.9% |  |  |  |  | 86.43% | [12 empty] | 77.92% |  |  | 100% | [13 empty] | 72.45% |  |  | 100% | [6 empty] | 78.95% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 42.86% | [5 empty] | 10% |  |  |  | 0.8571% | 77.16%
| Robertshaw Panel |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 11 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Amot / Trip switches | [11 empty] | 13 |  |  |  |  | 10 | [12 empty] | 18 |  |  | 2 | [13 empty] | 12 |  |  | 4 | [6 empty] | 7.5 |  |  |  | 2 |  |  |  | 2 | [5 empty] | 2 | [5 empty] | 0.5 |  |  |  | 0.025
| HP PSHH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| LP PSHH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| SV PSHH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Pumpline PSHH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Pumpline PSLL |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| IA PSLL |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Test Sep LSH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| LP Sep LSH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| HP Sep LSH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| SV LSHH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| FLKO LSHH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Fusible plugs |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| QAW valve - instrument gas |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| QAW valve - fuel gas_EP pumps |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| QAW valve - fuel gas_Gas set |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| ESD Call Points |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 11 | 70 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 19 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
INSTRUMENT AND FUEL GAS SYSTEM | [12 empty] | 85.58% |  |  |  |  | 71.88% | [12 empty] | 92.61% |  |  | 100% | [13 empty] | 78.57% |  |  | 100% | [6 empty] | 84.21% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 25% | [5 empty] | 21.25% |  |  |  | 68.13% | 78.64%
| Piping Checks |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 9 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Utility Gas Scrubber & Auto Drain |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Instrument Gas cooler |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 11 | 1 | 12.5
| Instrument Gas Scrubber & Auto Drain |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 1 | 1 | 6.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Instrument Gas Header & Distribution |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 7 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Instrument gas filter regulators |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 12 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 1 | 0 | 0 | 0.5
| Instr Gas Relief valves |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 9 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 17 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Fuel Gas Big Joes |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 12 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 1 | 0 | 0 | 0.5
POWER GENERATION & DISTRIBUTION | [12 empty] | 50% |  |  |  |  | 68.75% | [12 empty] | 68.18% |  |  | 100% | [13 empty] | 83.93% |  |  | 100% | [6 empty] | 94.74% |  |  |  | 62.5% |  |  |  | 100% | [5 empty] | 43.75% | [5 empty] | 0% |  |  |  | 1% | 67.03%
| Diesel Genset |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 9 | 1 | 1 | 1 | 1 | 20 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 17 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 11 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 0 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Gas Genset |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 12 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 12 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| LV Distribution Board |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 9 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 12 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 0 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Station Lighting & Photocell |  | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 6 | 1 | 1 | 1 | 0 | 15 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 11 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 12 | 1 | 1 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
DRAINS SYSTEM AND SAVER PIT | [12 empty] | 97.44% |  |  |  |  | 16.67% | [12 empty] | 93.94% |  |  | 100% | [13 empty] | 55.95% |  |  | 100% | [6 empty] | 77.19% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 50% | [5 empty] | 3.333% |  |  |  | 1% | 64.03%
| Open drains/Saver Pit |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 0 | 1 | 1 | 0 | 0 | 5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| CP Pumps |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 0 | 0 | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 9 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0.05 | 0 | 0 | 0.025
| Sampling point |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 22 | 1 | 1 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 5.5 | 1 | 1 | 4 | 1 | 0 | 1 | 1 | 1 | 1 | 7.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
CATHODIC PROTECTION | [12 empty] | 100% |  |  |  |  | 100% | [12 empty] | 100% |  |  | 100% | [13 empty] | 85.71% |  |  | 100% | [6 empty] | 100% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 50% | [5 empty] | 0% |  |  |  | 1% | 88.53%
| CP Transformer |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 12 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| CP cables and connections |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 12 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Ground bed |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 12 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
DELIVERY & TRUNKLINES | [12 empty] | 100% |  |  |  |  | 100% | [12 empty] | 100% |  |  | 75% | [13 empty] | 85.71% |  |  | 100% | [6 empty] | 100% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 100% | [5 empty] | 20% |  |  |  | 1% | 91.03%
| Pipeline integrity |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 22 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 12 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 0 | 1 | 0.05 | 0 | 0 | 0.025
| De-isolation status |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 12 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 0 | 1 | 0.05 | 0 | 0 | 0.025
CIVIL STRUCTURES | [12 empty] | 97.8% |  |  |  |  | 89.29% | [12 empty] | 100% |  |  | 100% | [13 empty] | 95.92% |  |  | 100% | [6 empty] | 100% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 100% | [5 empty] | 100% |  |  |  | 100% | 97%
| Guards hut & Toilets |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| Water tank and mains distribution |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| Pump House and Gantry Cranes |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 12 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| Generator House |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 0 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 12 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| Chemical Shed (N/A) |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| Fire Hut |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| Spill Response Caravan |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
IT & COMMUNICATION EQUIPMENT | [12 empty] | 100% |  |  |  |  | 100% | [12 empty] | 100% |  |  | 100% | [13 empty] | 100% |  |  | 100% | [6 empty] | 100% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 75% | [5 empty] | 100% |  |  |  | 1% | 96.53%
| IT checks |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 5 | 0.05 | 0 | 0 | 0.025
STATION ENVIRONMENT & FENCING | [12 empty] | 100% |  |  |  |  | 100% | [12 empty] | 100% |  |  | 100% | [13 empty] | 100% |  |  | 100% | [6 empty] | 100% |  |  |  | 100% |  |  |  | 100% | [5 empty] | 100% | [5 empty] | 100% |  |  |  | 100% | 100%
| Main Access road |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| Wellhead roads |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| In-plot roads |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| Grass cutting |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| Horticulture & trees |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| Station Fence & Access Control |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| Boards, notices, flags & signage |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
| Emergency escape gates |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 1 | 1 | 1 | 1 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 9.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2.5
INSTRUMENT AIR PROJECT | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| Project team assessment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| By Activity | [11 empty] | 81.92% |  |  |  |  | 74.67% | [12 empty] | 84.78% |  |  | 92.36% | [13 empty] | 79.05% |  |  | 89.81% | [6 empty] | 82.29% |  |  |  | 89.68% |  |  |  | 92.59% | [5 empty] | 54.62% | [5 empty] | 26.74% |  |  |  | 18.78% | 76.19%
Note on H14: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Will need Valve leak Testing
Note on H17: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: MSDVs not tagged
Note on H18: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Some inlet Manifold gauges missing/plugged off CP pump discharge PG faulty
Note on E27: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: HP Off Gas Flow Recorder
Note on U27: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: level controller alarm/shutdown not tested
Note on X27: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: MSDV not tested
Note on AA27: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: PV Not desanded not pressure tested
Note on AC27: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: UT Test not done on vessel and piping
Note on AQ27: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Level controller alarm/shutdown
Note on BI27: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Level controllers parts/kits
Note on Y29: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Meter Validation not done
Note on Z29: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Meter Validation not done
Note on E36: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: HP Off Gas Flow Recorder
Note on X36: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: MSDV not tested
Note on AA36: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: PV Not desanded not pressure tested
Note on AC36: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: UT Test not done on vessel and piping
Note on AQ36: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Level controller alarm/shutdown
Note on BI36: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Level controllers parts/kits
Note on E43: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: HP Off Gas Flow Recorder
Note on X43: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: MSDV not tested
Note on AA43: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: PV Not desanded not pressure tested
Note on AC43: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: UT Test not done on vessel and piping
Note on AQ43: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Level controller alarm/shutdown
Note on BI43: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Level controllers parts/kits
Note on H56: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: MSDVs not tagged
Note on B59: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Emply Bay
Note on AE64: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: SHIELDED IGNITION BATTERY AND INVERTER CASE ARE NOT EARTHED
Note on AE68: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: SHIELDED IGNITION BATTERY AND INVERTER CASE ARE NOT EARTHED
Note on Y73: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Meter Validation not done
Note on Z73: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Meter Validation not done
Note on H74: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Will need Valve leak Testing
Note on AE75: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: WATER CUT METER EX BOX IS NOT EARTHED
Note on H79: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Will need Valve leak Testing
Note on H81: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Will need Valve leak Testing
Note on AD88: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: USM LOCAL ON/OFF SWITCH EX-RATING IMPAIRED
Note on U99: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: level controller alarm/shutdown not tested
Note on U100: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: level controller alarm/shutdown not tested
Note on U101: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: level controller alarm/shutdown not tested
Note on E108: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: No call point for pump house
Note on H114: Dan-Nwaogu, Arthur C SPDC-UPO/G/PLR: Will need Valve leak Testing
Note on AH132: Wahua, Nkesi I SPDC-UIO/G/PNEL1: Clearance from pipline team required

## PMS
OBELE FLOWSTATION: 2017 RE-ENTRY
Date Assessed :-
|  | System Number | No missing parts or components / All parts replaced | Jointing integrity check - balanced bolting, good & right gaskets and no galvanic corrosion | PEFS,UEFS,Isometrics, Well completions, line-walked & marked up. All Valves and logic line up (tracing), NRV in right direction, NONC, LOLC, LOTO is ok. | PEFS,UEFS line-walk - All guages (PG, TG & FI, Avometers) and sensors in place, tagged, certified and not leaking. | Supports, gratings, foundation bolts & Clearances ok | Alignment ok | Clean internals - Desanding, no blocked NRVs, orifices, valves etc | Isolation requirements checked ok - fuses, switch gears, spades, spectacles, blinds and removable spools | Content colour coding, Visual controls, flow direction marking, red spectacle painting etc done | All repaired items re-ceritfied (hydrotesting, radiography etc) | Integrity Inspection | Linear and rotary motion checks, barring - no free-wheeling, jerking nor jamming stuck of valves & engines | Flow, Pressure, Level and Temparature sensors are communicating with their controllers | Process controllers & control elements (PCVs, LCVs, FCVs, speed governor etc) detect parameters changes and responds as intended | No leaks (fluid, energy & data) - system leak tested, cable integrity, earthing check | Integrity Restoration | Safeguarding alarms and trips work at the correct set points (pressure, level, temp, flow and vibration) | Process safeguarding system (RBP) & ESD call points functional | F&G system functional | Safety shutoff valves (SCSSSV, MSDVs etc) certified - do not pass / positive shut off. BDVs & RVs closed and not passing. | Other Assurance task / test executed, (P or F) | Qualification? | All vessels PV certified | All RVs certified | UT & LRUTdone | Ex-rating inspection done / valid | Hardware Barrier Assessment done / valid | Corporate TIV verified | SCE Assurance | Operating permits are valid (e.g. DPR allowable, diesel storage, bunkering, radioactive sources, radio frequency,sewage treatment etc) | Environmental Compliance Monitoring | Permits and Statutory Compliance | Access control facilities are in place (e.g. wellhead fenced, door locks for Switchgear rooms) | Clear, identified, lighted and signaged emergency escape route and muster points - tested okay. | Station Bill, Lay out Plan, HAC drawings, Noise map done and pasted | Caution and danger notices, ROW markers, ER Numbers, Resuscitation Notice, CPR and AR Procedure in place & pasted | Emergency doors fitted with one-way locks and panic bars | Adequate lighting for night operations | Process and emergency alarms and beacons audible and visible -line of sight okay | Proximity of fire fighting & life saving equipt checked okay (extinguishers, etc) | Vibration level acceptable | Equipment, piping and cable trays adequately supported and vibration damped | Clear fire breaks | Bund wall / collection pit in place, tested leak proof | Overal cleanliness, no drips, no leaks, good housekeeping etc | HSSE | Personnel required available (staff, attendants, prod support, etc) | Personnel trained and certified competent (normal & abnormal situations mgt, ER etc) | Manpower | Manufacturer (OEM) / Support contract in place | Any changes (equipment, configuration etc) passed thro MoC, registered and updated in CMMS e.g. Z6 raised | CMMS checked, updated and activated live in SAP | Lifting, hoisting and transfer equipment available and certified valid | Maintenance access (including ladders & platforms), working space and laydown area is integral and free | No red items in facility status report, all deviations approved, no expired MoCs etc | Maintenability & OEM Contracts | Inventory of consumable spares & materials checked and adequate or on order | Temporary equipment registered & MoCed | Special tools & PPE available (beans, bean spanners, valve handles, megger, insulation mats etc) | Spares and Special Tools | Chemicals, lubes and consumables are above re-order levels or on order. | MSDS / SHOC cards in place for all chemicals | First-fill adequate for equipment (e.g sump level okay, day tank level ok etc) | Chemicals & Lubes | Tier-1 documentation reviewed, available and up-to-date | For changes; confirm - Marked up AFC drawings - PEFS, UEFS, GAs, Single Line, C&E, RATS, Instrument Data Sheets, Loop diagrams, block diagrams etc all available on site. | Pre-Start Up Checklist in place and executed | Start Up Procedure reviewed | FLM log, Fault Register and other operational control registers active | RFC Documentation (non-HC systems) | Tier-1 documentation reviewed, up-to-date and available on site | All first re-fills in place - lube oils, hydraulic oil, corrosion inhibitor, demulsifier etc | Pre-Start Up Checks done and Cat A items all closed | RFOs & RFSUs signed - Ops, mtc, IT, Pipelines and other support teams | SoF | RFSU & RFO Documentation | Cause and Effects verified by Emergency Shutdown (ESD) Test. | System Started and running | Operates as intended without a trip for 72 hours continous | Commissioned | By System
| Weighting (xx/100) |  | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 13 | 7 | 5 | 7 | 6 | 25 | 3 | 3 | 3 | 2 | 1 |  | 2 | 2 | 1 | 1 | 1 | 3 | 22 | 1 | 1 | 2 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 10 | 2 | 2 | 4 | 2 | 2 | 2 | 1 | 0.5 | 2 | 9.5 | 0.5 | 0.5 | 1 | 2 | 0.5 | 1 | 0.5 | 2 | 1 | 1 | 1 | 0.5 | 0.5 | 4 | 0.5 | 0.5 | 1 | 1 | 1 | 4 | 0.5 | 1 | 1 | 2.5 | 100
WELLS | [12 empty] | 2.564% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.3583%
| Obele 6T |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Obele 1L |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Obele 1S |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
FLOWLINES | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| Obele 6T |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Obele 1L |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Obele 1S |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
INLET MANIFOLD | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| Plug valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Header piping |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Manual isolation valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Master Shutdown Valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Guages |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Relief valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
VESSELS | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 0.4% | 0.01%
| HP Separator | [11 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1%
| Manual isolation valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Level indicator, sight glass |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Level control valve |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025 | 0.0625%
| Pressure guages |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Relief valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Othe device |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Test Separator | [11 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1%
| Rotron meter |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Daniel Orifice Fitting |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Manual isolation valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Level indicator, sight glass |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025 | 0.0625%
| Level control valve |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Pressure guages |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025 | 0.0625%
| Relief valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Other Device |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| LP Separator | [11 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1%
| Manual isolation valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Level indicator, sight glass |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Level control valve |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Pressure guages |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Relief valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Othe device |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Surge Vessel | [11 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1%
| Manual isolation valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Level indicator, sight glass |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Level control valve |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Pressure guages |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Pump suction header |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Relief valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| SV recirculation system |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| FLKO Vessel | [11 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1%
| Manual isolation valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Level indicator, sight glass |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Level control valve |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Other device |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025 | 0.0625%
EXPORT PUMPS & METERING | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 0.4% | 0.01%
| EP1 | [11 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1%
| Visual checks |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Relief valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Other checks |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| EP 2 | [11 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1%
| Visual checks |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025 | 0.0625%
| Relief valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Other checks |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| EP 3 | [11 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| Visual checks |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Relief valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Other checks |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
EXPORT METERING | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| PD Meter 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| PD Meter 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Manual Isolation valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Water cut Meter |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Other device |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
CHEMICAL INJECTION | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| Injection pump and piping |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Chemical tank & stock |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
GAS HEADERS | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| HP PCV |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| HP Header manual valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025 | 0.0625%
| LP PCV |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| LP Header manual valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Flare line low point drain |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
FLARE | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| Venturi |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Flare tip |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Piping |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025 | 0.0625%
| Pilot |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| USM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Bundwall integrity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
SAFEGUARDING SYSTEM | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 0.1429% | 0.003571%
| Robertshaw Panel |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Amot / Trip switches | [11 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 0%
| HP PSHH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LP PSHH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SV PSHH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pumpline PSHH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pumpline PSLL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| IA PSLL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test Sep LSH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SV LSHH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FLKO LSHH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fusible plugs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| QAW valve - instrument gas |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| QAW valve - fuel gas_EP pumps |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| QAW valve - fuel gas_Gas set |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ESD Call Points |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INSTRUMENT AND FUEL GAS SYSTEM | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| Piping Check |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Utility Gas Scrubber |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Instrument Gas cooler |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Instrument Gas Scrubber |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Instrument Gas Header & Distribution |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Instrument gas filter regulators |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Relief valves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Fuel gas 'Big Joe's |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
POWER GENERATION & DISTRIBUTION | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| Diesel Genset |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Gas Genset |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| LV Distribution Board |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Station Lighting & Photocell |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
DRAINS SYSTEM AND SAVER PIT | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| Open drains |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Saver pit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| CP Pumps |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Sampling point |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
CATHODIC PROTECTION | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| CP Transformer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| CP cables and connections |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Ground bed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
DELIVERY & TRUNKLINES | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| Pipeline integrity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| De-isolation status |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
CIVIL STRUCTURES | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| Guards hut & Toilets |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Water tank and mains distribution |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Pump House and Gantry Cranes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Generator House |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Chemical Shed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Fire Hut |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Spill Response Caravan |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
IT & COMMUNICATION EQUIPMENT | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| IT checks |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
STATION ENVIRONMENT & FENCING | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| Main Access road |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Wellhead roads |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| In-plot roads |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Grass cutting |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Horticulture & trees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Station Fence & Access Control |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Boards, notices, flags & signage |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| Emergency escape gates |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
INSTRUMENT AIR PROJECT | [12 empty] | 0% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 1% | 0.025%
| Project team assessment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.025
| By Activity | [11 empty] | 0.135% |  |  |  |  | 0% | [12 empty] | 0% |  |  | 0% | [13 empty] | 0% |  |  | 0% | [6 empty] | 0% |  |  |  | 0% |  |  |  | 0% | [5 empty] | 0% | [5 empty] | 0% |  |  |  | 0.8917% | 0.03984%

## Site sheet
Unit: |  |  | Date:
| Site Checklist | Y or N | Score | Action Required
Integrity Inspection
No missing parts or components / All parts replaced
Jointing integrity check - balanced bolting, good & right gaskets and no galvanic corrosion
PEFS,UEFS,Isometrics, Well completions, line-walked & marked up. All Valves and logic line up (tracing), NRV in right direction, NONC, LOLC, LOTO is ok.
PEFS,UEFS line-walk - All guages (PG, TG & FI, Avometers) and sensors in place, tagged, certified and not leaking.
Supports, gratings, foundation bolts & Clearances ok
Alignment ok
Clean internals - Desanding, no blocked NRVs, orifices, valves etc
Isolation requirements checked ok - fuses, switch gears, spades, spectacles, blinds and removable spools
Content colour coding, Visual controls, flow direction marking, red spectacle painting etc done
All repaired items re-ceritfied (hydrotesting, radiography etc)
Integrity Restoration
Linear and rotary motion checks, barring - no free-wheeling, jerking nor jamming stuck of valves & engines
Flow, Pressure, Level and Temparature sensors are communicating with their controllers
Process controllers & control elements (PCVs, LCVs, FCVs, speed governor etc) detect parameters changes and responds as intended
No leaks (fluid, energy & data) - system leak tested, cable integrity, earthing check
SCE Assurance
Safeguarding alarms and trips work at the correct set points (pressure, level, temp, flow and vibration)
Process safeguarding system (RBP) & ESD call points functional
F&G system functional
Safety shutoff valves (SCSSSV, MSDVs etc) certified - do not pass / positive shut off. BDVs & RVs closed and not passing.
Other Assurance task / test executed, (P or F)
Qualification?
All vessels PV certified
All RVs certified
UT & LRUTdone
Ex-rating inspection done / valid
HSSE
Access control facilities are in place (e.g. wellhead fenced, door locks for Switchgear rooms)
Clear, identified, lighted and signaged emergency escape route and muster points - tested okay.
Station Bill, Lay out Plan, HAC drawings, Noise map done and pasted
Caution and danger notices, ROW markers, ER Numbers, Resuscitation Notice, CPR and AR Procedure in place & pasted
Emergency doors fitted with one-way locks and panic bars
Adequate lighting for night operations
Process and emergency alarms and beacons audible and visible -line of sight okay
Proximity of fire fighting & life saving equipt checked okay (extinguishers, etc)
Vibration level acceptable
Equipment, piping and cable trays adequately supported and vibration damped
Clear fire breaks
Bund wall / collection pit in place, tested leak proof
Overal cleanliness, no drips, no leaks, good housekeeping etc
Maintenability & OEM Contracts
Lifting, hoisting and transfer equipment available and certified valid
Maintenance access (including ladders & platforms), working space and laydown area is integral and free
Spares and Special Tools
Temporary equipment registered & MoCed
Special tools & PPE available (beans, bean spanners, valve handles, megger, insulation mats etc)
Chemicals & Lubes
Chemicals, lubes and consumables are above re-order levels or on order.
MSDS / SHOC cards in place for all chemicals
First-fill adequate for equipment (e.g sump level okay, day tank level ok etc)
RFC Documentation (non-HC systems)
For changes; confirm - Marked up AFC drawings - PEFS, UEFS,SLDs etc all available on site.
FLM log, Fault Register and other operational control registers active
RFSU & RFO Documentation
Pre-Start Up Checks done and Cat A items all closed

## Sheet1
System Number | No missing parts or components / All parts replaced | Jointing integrity check - balanced bolting, good & right gaskets and no galvanic corrosion | PEFS,UEFS,Isometrics, Well completions, line-walked & marked up. All Valves and logic line up (tracing), NRV in right direction, NONC, LOLC, LOTO is ok. | PEFS,UEFS line-walk - All guages (PG, TG & FI, Avometers) and sensors in place, tagged, certified and not leaking. | Supports, gratings, foundation bolts & Clearances ok | Alignment ok | Clean internals - Desanding, no blocked NRVs, orifices, valves etc | Isolation requirements checked ok - fuses, switch gears, spades, spectacles, blinds and removable spools | Content colour coding, Visual controls, flow direction marking, red spectacle painting etc done | All repaired items re-ceritfied (hydrotesting, radiography etc) | Integrity Inspection | Linear and rotary motion checks, barring - no free-wheeling, jerking nor jamming stuck of valves & engines | Flow, Pressure, Level and Temparature sensors are communicating with their controllers | Process controllers & control elements (PCVs, LCVs, FCVs, speed governor etc) detect parameters changes and responds as intended | No leaks (fluid, energy & data) - system leak tested, cable integrity, earthing check | Integrity Restoration | Safeguarding alarms and trips work at the correct set points (pressure, level, temp, flow and vibration) | Process safeguarding system (RBP) & ESD call points functional | F&G system functional | Safety shutoff valves (SCSSSV, MSDVs etc) certified - do not pass / positive shut off. BDVs & RVs closed and not passing. | Other Assurance task / test executed, (P or F) | Qualification? | All vessels PV certified | All RVs certified | UT & LRUTdone | Ex-rating inspection done / valid | Hardware Barrier Assessment done / valid | Corporate TIV verified | SCE Assurance | Operating permits are valid (e.g. DPR allowable, diesel storage, bunkering, radioactive sources, radio frequency,sewage treatment etc) | Environmental Compliance Monitoring | Permits and Statutory Compliance | Access control facilities are in place (e.g. wellhead fenced, door locks for Switchgear rooms) | Clear, identified, lighted and signaged emergency escape route and muster points - tested okay. | Station Bill, Lay out Plan, HAC drawings, Noise map done and pasted | Caution and danger notices, ROW markers, ER Numbers, Resuscitation Notice, CPR and AR Procedure in place & pasted | Emergency doors fitted with one-way locks and panic bars | Adequate lighting for night operations | Process and emergency alarms and beacons audible and visible -line of sight okay | Proximity of fire fighting & life saving equipt checked okay (extinguishers, etc) | Vibration level acceptable | Equipment, piping and cable trays adequately supported and vibration damped | Clear fire breaks | Bund wall / collection pit in place, tested leak proof | Overal cleanliness, no drips, no leaks, good housekeeping etc | HSSE | Personnel required available (staff, attendants, prod support, etc) | Personnel trained and certified competent (normal & abnormal situations mgt, ER etc) | Manpower | Manufacturer (OEM) / Support contract in place | Any changes (equipment, configuration etc) passed thro MoC, registered and updated in CMMS e.g. Z6 raised | CMMS checked, updated and activated live in SAP | Lifting, hoisting and transfer equipment available and certified valid | Maintenance access (including ladders & platforms), working space and laydown area is integral and free | No red items in facility status report, all deviations approved, no expired MoCs etc | Maintenability & OEM Contracts | Inventory of consumable spares & materials checked and adequate or on order | Temporary equipment registered & MoCed | Special tools & PPE available (beans, bean spanners, valve handles, megger, insulation mats etc) | Spares and Special Tools | Chemicals, lubes and consumables are above re-order levels or on order. | MSDS / SHOC cards in place for all chemicals | First-fill adequate for equipment (e.g sump level okay, day tank level ok etc) | Chemicals & Lubes | Tier-1 documentation reviewed, available and up-to-date | For changes; confirm - Marked up AFC drawings - PEFS, UEFS, GAs, Single Line, C&E, RATS, Instrument Data Sheets, Loop diagrams, block diagrams etc all available on site. | Pre-Start Up Checklist in place and executed | Start Up Procedure reviewed | FLM log, Fault Register and other operational control registers active | RFC Documentation (non-HC systems) | Tier-1 documentation reviewed, up-to-date and available on site | All first re-fills in place - lube oils, hydraulic oil, corrosion inhibitor, demulsifier etc | Pre-Start Up Checks done and Cat A items all closed | RFOs & RFSUs signed - Ops, mtc, IT, Pipelines and other support teams | SoF | RFSU & RFO Documentation | Cause and Effects verified by Emergency Shutdown (ESD) Test. | System Started and running | Operates as intended without a trip for 72 hours continous
WELLS
FLOWLINES
INLET MANIFOLD
VESSELS
EXPORT PUMPS & METERING
EXPORT METERING
CHEMICAL INJECTION
GAS HEADERS
FLARE
SAFEGUARDING SYSTEM
INSTRUMENT AND FUEL GAS SYSTEM
POWER GENERATION & DISTRIBUTION
DRAINS SYSTEM AND SAVER PIT
CATHODIC PROTECTION
DELIVERY & TRUNKLINES
CIVIL STRUCTURES
IT & COMMUNICATION EQUIPMENT
STATION ENVIRONMENT & FENCING
INSTRUMENT AIR PROJECT

## Sheet2
ASPECT | Weighting (xx/100) | COMMENT
WELLS
Obele 6T
Obele 1L
Obele 1S
FLOWLINES
Obele 6T
Obele 1L
Obele 1S
INLET MANIFOLD
Plug valves
Header piping
Manual isolation valves
Master Shutdown Valves
Guages
Relief valves
VESSELS
HP Separator
Manual isolation valves
Level indicator, sight glass
Level control valve
Pressure guages
Relief valves
Othe device
Test Separator
Rotron meter
Daniel Orifice Fitting
Manual isolation valves
Level indicator, sight glass
Level control valve
Pressure guages
Relief valves
Other Device
LP Separator
Manual isolation valves
Level indicator, sight glass
Level control valve
Pressure guages
Relief valves
Othe device
Surge Vessel
Manual isolation valves
Level indicator, sight glass
Level control valve
Pressure guages
Pump suction header
Relief valves
SV recirculation system
FLKO Vessel
Manual isolation valves
Level indicator, sight glass
Level control valve
Other device
EXPORT PUMPS & METERING
EP1
Visual checks
Relief valves
Other checks
EP 2
Visual checks
Relief valves
Other checks
EP 3
Visual checks
Relief valves
Other checks
EXPORT METERING
PD Meter 1
PD Meter 2
Manual Isolation valves
Water cut Meter
Other device
CHEMICAL INJECTION
Injection pump and piping
Chemical tank & stock
GAS HEADERS
HP PCV
HP Header manual valves
LP PCV
LP Header manual valves
Flare line low point drain
FLARE
Venturi
Flare tip
Piping
Pilot
USM
Bundwall integrity
SAFEGUARDING SYSTEM
Robertshaw Panel
Amot / Trip switches
HP PSHH
LP PSHH
SV PSHH
Pumpline PSHH
Pumpline PSLL
IA PSLL
Test Sep LSH
SV LSHH
FLKO LSHH
Fusible plugs
QAW valve - instrument gas
QAW valve - fuel gas_EP pumps
QAW valve - fuel gas_Gas set
ESD Call Points
INSTRUMENT AND FUEL GAS SYSTEM
Piping Check
Utility Gas Scrubber
Instrument Gas cooler
Instrument Gas Scrubber
Instrument Gas Header & Distribution
Instrument gas filter regulators
Relief valves
Fuel gas 'Big Joe's
POWER GENERATION & DISTRIBUTION
Diesel Genset
Gas Genset
LV Distribution Board
Station Lighting & Photocell
DRAINS SYSTEM AND SAVER PIT
Open drains
Saver pit
CP Pumps
Sampling point
CATHODIC PROTECTION
CP Transformer
CP cables and connections
Ground bed
DELIVERY & TRUNKLINES
Pipeline integrity
De-isolation status
CIVIL STRUCTURES
Guards hut & Toilets
Water tank and mains distribution
Pump House and Gantry Cranes
Generator House
Chemical Shed
Fire Hut
Spill Response Caravan
IT & COMMUNICATION EQUIPMENT
IT checks
STATION ENVIRONMENT & FENCING
Main Access road
Wellhead roads
In-plot roads
Grass cutting
Horticulture & trees
Station Fence & Access Control
Boards, notices, flags & signage
Emergency escape gates
INSTRUMENT AIR PROJECT
Project team assessment
By Activity