## Sheet1
Project Plan for NAG to AGG Rerouting
Technical studies, Reviews and approvals | Action Party | Date | Revised Date | Status
Site Visit by Project Ops Mgr & Asset team | Nkesi W/Esther W/Ovuru H/Ejirinde A | 30th Sept 2017 |  | Done
Site visit by process and asset teams | Alaka/ Linda A/ Esther W/Joshua O/Onumajuru C | 10th Nov 2017 |  | Done
Data gathering and Preliminary review/analysis | Alaka C./Esther W/Joshua O/Onumajur C/Ejirinde A | 4th January, 2018 |  | Done
Site visit by discipline eng & asset engineering teams | Alaka/Idio S/Famofo/Chibuzo O/Esther W | 13th February 2018 |  | Done
Raise engineering work request and obtain asset engineering support | Esther W | 16th February 2018 |  | Done
Concept Selection Review | Esther W | 28th March 2018 |  | Done
Technical safety review/ Risk assessment | Izu/Esther | 28th March 2018 |  | Done
Technical studies/Review feasibility report/sign off | Alaka | 13th April 2018 |  | Done
Engage Technical authorities and obtain buy-in | Alaka/Esther | 28th March 2018 |  | Done
Obtain approved MOC | Esther W/Alaka | 26th April 2018 |  | Done
Site visit by contractor | Famofo/Iki | 16th May 2018 |  | Done
Prepare detailed schedule for design and execution | Iki Dienagha | 23rd May 2018 |  | Done
Prepare detailed cost estimate for execution | Omonigho E/Iki Dienagha | 30th May 2018 |  | Done
Production of detailed design deliverables | Central Eng./Omonigho | 8th June 2018 | 31st July 2018
Secure Budget Approval | Sam Ezugworie/Adediran A./Nkesi | 11th June 2018 | 6th July 2018 | Done
Review and sign off detailed design deliverables | Central Eng./Omonigho | 14th June 2018 | 31st July 2018
Procurement of materials: (Place order) | Iki Dienagha/Omonigho | 14th June 2018 | 20th July 2018
PO to contractor | Omonigho E/Famofo | 15th June 2018 | 23rd July 2018
Community engagement/FTO | Alamina Boma/Amadi-Worlu C./Omonigho | 22nd June 2018 | 25th July 2018
Mobilization to site for early tie in works/demolition (Mech & Civil) | Omonigho E./Iki/Esther W/Joshua O/Franklin/Onumajuru C/Ejirinde A | 29th June 2018 | 31st July 2018
On-site intsallation of piping spools and valves at tie-in points | Omonigho E./Iki/Esther W/Joshua O/Franklin/Onumajuru C/Ejirinde A | 6th July 2018 | 15th September 2018
Construction/ modification activities: Civil works -foundation for vessel and pipe supports | Omonigho E./Iki/Esther W/Joshua O/Franklin/Onumajuru C/Ejirinde A | 13th July 2018 | 30th August 2018
Mechanical activities: Welding & yard fabrication | Iki Dienagha/Omonigho | 13th July 2018 | 15th September 2018
Mechanical: Installation & Hook up | Famofo/Omonigho E./Iki/Esther W/Joshua O/Franklin/Onumajuru C/Ejirinde A/Ovuru | 16th Aug 2018 | 30th September 2018
PACO activities: Excavation, Laying of cables from NAG to AGG, Installation & Termination of field devices | Omonigho E./Iki/Bolouwei W/Esther W/Joshua O/Franklin/Onumajuru C/Ejirinde A | 14th Sept 2018 | 15th October 2018
PACO: Control systems configuration & integration | Omonigho E./Iki/Bolouwei W/Esther W/Joshua O/Franklin/Onumajuru C/Ejirinde A | 19th Oct 2018 | 30th October 2018
Pre-commisioning activities | Alaka/ Omonigho/ Famofo/Iki/Esther W/Joshua O/Franklin/Onumajuru C/Ejirinde A | 26th Oct 2018 | 15th November 2018
Statement of Fitness Preparation & Approval | Omonigho E/Joshua O | 8th Nov 2018 | 30th November 2018
Commisioning and start-up | Famofo/Omonigho E./Iki/Esther W/Joshua O/Ovuru/Onumajuru C/Ejirinde A/Nkesi | 15th Nov 2018 | 30th November 2018
Include execution/contruction works in the 35days September 2018 IAP for Obigbo AGG