## Sheet1
| Project Name | REROUTING OF IMO RIVER-2 & 3 TO IMO RIVER 1 FLOWSTATION | [5 empty] | Contractor |  | PEACOT NIG LTD
| Status Date | 2018-04-16 | Start Date | 2017-11-20 |  | Target End Date |  | 2018-04-28 |  |  | Budget |  | Available
| HIGHLIGHT |  |  |  |  | HSE STATISTICS |  |  |  | LOOK AHEAD
| HIGHLIGHTS - - Yard Fabrication of Spools for gathering manifold installation on going - 100% Complete - Radiography of Spools for the Imo 2 & 3 S/D conpleted - Personne Mobilized to site on 21/11/2017 - Shutdown of Imo 1 f/S for Tie-In activity on 22/11 - Installation of 2 Nos 4 x 600# ball valves for Tie-In to LP1 & LP2 at Imo 1 F/S Completed. - Probing and test digging in progress - Dist covered 140m, Cum dist. Covered 1.1km1.1km completed - Excavation for the two line tie-in into LP1 and LP2 at Imo 1 from the new manifold at Imo gathering point - 100% completed - Excavation and Thrust boring for Lines going from Imo 3 to Imo 1 - 100% Completed - Excavation for new 6" Imo 2 bulkline - 38% Completed - Site opened after Xmas break on the 11/01/18 - Rerouting of Well 59T to Imo 3 - 100% Completed - Tie-In of the new 6" Bulk line welding in progress - 46% completed. - Tie-In of W43T at Imo 1 end completed. - Shutdown activities at Imo 3 on 21/02 -100% completed - Weld & Lay of Lines going to LP1 & LP2 hook-up - 81% Completed - Secured FTO to continue laying of 6" bulkline to Imo 2 on 26/02 - Cold cutting of disused pipes on the pipe rack at Imo1 f/s - 100% completed - Probing & Identification of W5L - 100% Completed. - Flushing of W5L completed. - Tie-In of W59T at Imo 1 end completed. - Removal of disused pipies at Imo 1 - 100% Completed - Stringing of 6" Line pipes along ROW to Imo 2 - 55% completed . Tie-in of W5L at the Gathering Manifold at Imo 1- 100% Completed - Hydrotest of modified tie-In 8" Extension Spools at Imo 2 - 100% Completed - Welding & Hydrotest of 2" relief line to header at Imo 2 - 100% Completed. - Boundary Reopening for the new bulkine to Imo 2 in progress - 100% completed - Hydrotest of 6" Line (W59T & W43T) Imo 3 to Imo 1 f/s in progress - 100% Completed - Sleeving of welded joints on going - Cum 58.2% Completed. - Lowering of Linepipes along ROW - 58.2% Completed - Installation & Bolt Up of Shutdown Spools for Imo 2 - 100% Completion - Installation of spools & Hook-Up of bulk lines to Inlet Manifold at Imo 3- 100% Completed - Backfilling of Imo 3 end - 100% Completed - Radiography of welded joints - 244 joints radiographed todate. 68% completed - Repair Works of Vandalized Section of W5L - 100% Completed - Hydrotest of Inlet line to LP1 & LP2 Header at Imo 1 Completed. - Re-Modification of LP1 & LP1 Hook Up Spools at Imo 1 - Completed - Installation of Inplot piping & Bulk Header Manifold at Imo 1 FS - 100% Completed - Hook Up of Bulkline Manifold to LP1 & LP2 - 100% Completed - Commisioning of Imo 3 Buliklines To Imo1 LP1 & LP2 Headers - Completed on 12/04/18 - Hydrotest of Test Line W5L Completed - Backfilling of Imo 1 end - 99% Completed. - Weld & Lay of Lines new 6" bulkline to Imo 2 - 58% Completed - Bush clearing along Imo 2 R.O.W - 50% Completed |  |  |  |  | Weld |  |  | 22411 | Continue with:
[6 empty] | POB |  |  | 25 | - Stringing of 6" PE coated Line pipes along Imo 1 to Imo 2 F/S - Radiography of welded joints - Sleeving of welded joints - Backfilling of Imo 1 end - Bush clearing of row for the new 6" bulk line - Weld & Lay of Flowlines to Imo 2
[6 empty] | UA/UC |  |  | 290
[6 empty] | NM |  | 0
| LOWLIGHTS: - All planned activities regretted due to community interuption at Imo 2 |  |  |  |  | FAC |  | -
[6 empty] | MTC/RWC |  | -
[6 empty] | LWC |  | -
[6 empty] | HIPO |  | -
| Percentage Work Completion: |  | 75.95% |  |  | FATALITY |  | -
[6 empty] | NAD |  | -
| WBS/Activity – O.NG.PAE.A1F.FAC.724FC |  |  | Unit | % Plan | % Complete | Target End Date
A | Imo River Rerouting Shutdown Activities |  |  |  | 18.37% | 100% | Start Date | End Date | Actual |  |  | Plan (Unit) | 49
1 | Yard Fabrication Tie-In Spools for Imo 1 f/s |  |  | 1 | 2.041% | 100% | 2017-11-21 | 2017-11-21 | 2017-11-21 |  |  | Completed (Unit) | 31
2 | Yard Fabrication Tie-In Spools for Imo 2 f/s |  |  | 1 | 2.041% | 100% | 2017-11-21 | 2017-11-21 | 2017-11-21 |  |  | In Progress (Unit) | 7
3 | Yard Fabrication Tie-In Spools for Imo 3 f/s |  |  | 1 | 2.041% | 100% | 2017-11-22 | 2017-11-24 | 2017-11-22 |  |  | Not Started (Unit) | 11
4 | Mobilization |  |  | 1 | 2.041% | 100% | 2017-12-18 | 2017-12-20 | 2017-11-22 |  |  | YTD Plan (%) | 98.98%
5 | Site HSE Induction |  |  | 1 | 2.041% | 100% | 2017-12-12 | 2017-12-14 | 2017-12-14 |  |  | YTD Actual (%) | 75.95%
6 | Tie-In of Imo River 1 F/S |  |  | 1 | 2.041% | 100% | 2017-11-20 | 2017-11-20 | 2017-11-20 |  |  | View S Curve
7 | Yard Fabrication Gathering Manifold Header for Imo 1 f/s |  |  | 1 | 2.041% | 100% | 2017-11-20 | 2017-11-20 | 2017-11-20
8 | Tie-In of Imo River 3 F/S |  |  | 1 | 2.041% | 100% | 2017-11-20 | 2018-03-03
9 | Tie-In of Imo River 2 F/S |  |  | 1 | 2.041% | 100% | 2017-12-13 | 2018-03-18
B | Imo River 3 To Imo River 1 F/S |  |  |  | 27.55% | 100% | 2017-12-08 | 2018-03-25
1 | Excavation of Imo 3 to Imo 1 Line 6" flowline |  |  | 1 | 2.041% | 100% | 2017-12-08 | 2017-12-08 | 2017-12-08
2 | Tie-back of W/5L to Imo 3 |  |  | 1 | 2.041% | 100% | 2018-03-07 | 2018-03-19 | 2018-04-14
3 | Lay & Weld of 6" Line Imo 3 to Imo 1 f/s |  |  | 2 | 4.082% | 100% | 2017-12-11 | 2018-01-29
4 | Radigraphy of 6" Line Imo 3 to Imo 1 f/s |  |  | 1 | 2.041% | 100% | 2017-12-13 | 2018-03-21
5 | Hydrotest of 6" Line (W59T & W43T) Imo 3 to Imo 1 f/s |  |  | 1 | 2.041% | 100% | 2017-12-13 | 2018-03-23
6 | Install Tie-in pieces and other shutdown works |  |  | 2 | 4.082% | 100% | 2018-03-09 | 2018-03-11
7 | Sleeving of Joints Imo 3 to Imo 1 f/s |  |  | 1 | 2.041% | 100% | 2017-12-13 | 2018-03-24
8 | Road Crossing From Imo 3 F/s to Gatering Manifold |  |  | 2 | 4.082% | 100% | 2017-12-10 | 2017-12-31
9 | Lowering of flowline From Imo 3 to Imo 1 F/S |  |  | 0.5 | 1.02% | 100% | 2017-12-13 | 2018-02-03
10 | Backfilling of flowline ROW |  |  | 0.5 | 1.02% | 100% | 2017-12-14 | 2018-03-25
11 | Locate 4" flowline (W/5L) to Imo 1 manifold |  |  | 0.5 | 1.02% | 100% | 2018-03-01 | 2018-03-04
12 | Tie-back 4" flowline to ex-59T ligaments |  |  | 1 | 2.041% | 100% | 2018-03-05 | 2018-03-10
C | Imo River 2 To Imo River 1 F/S |  |  |  | 26.53% | 40.18% | 2017-11-30 | 2018-04-27
1 | Excavation of Imo 2 to Imo 1 Line 6" flowline |  |  | 1 | 2.041% | 80% | 2017-12-12 | 2018-04-20
2 | Lay & Weld of 6" Bulk Line Imo 2 to Imo 1 f/s |  |  | 2 | 4.082% | 58% | 2017-11-30 | 2018-04-24
3 | Radigraphy of 6" Bulk line Line Imo 2 to Imo 1 f/s |  |  | 1 | 2.041% | 68% | 2017-12-04 | 2018-04-25
4 | Hydrotest of 6" Line Imo 2 to Imo 1 f/s |  |  | 1 | 2.041% | 0% | 2017-12-19 | 2018-04-14
5 | Sleeving of Joints Imo 2 to Imo 1 f/s |  |  | 1 | 2.041% | 58.2% | 2017-12-04 | 2018-04-27
6 | Road Crossing From Imo 2 F/s to Imo River 1 f/s |  |  | 1 | 2.041% | 50% | 2017-12-12 | 2018-04-20
7 | Lowering of flowline from Imo 2 to Imo 1 F/S |  |  | 0.5 | 1.02% | 58.2% | 2017-12-16 | 2018-04-26
8 | Backfilling of flowline ROW |  |  | 0.5 | 1.02% | 0% | 2017-12-20 | 2018-04-13
9 | Locate 4" flowlines (25L, 21S) |  |  | 0.5 | 1.02% | 50% | 2018-02-12 | 2018-04-22
10 | Tie-back 4" flowlines to Imo 2 |  |  | 0.5 | 1.02% | 0% | 2018-03-13 | 2018-04-23
11 | Install Tie-in pieces and other shutdown works |  |  | 2 | 4.082% | 100% | 2018-03-14 | 2018-03-21
12 | Tie-back 4" bulk lines to Imo 1 |  |  | 1 | 2.041% | 0% | 2018-03-14 | 2018-04-24
13 | Gas generator fuel gas line modification |  |  | 1 | 2.041% | 0% | 2018-03-17 | 2018-04-25
D | Imo River 1 Gathering Manifold |  |  |  | 19.39% | 99.89% | 2017-12-04 | 2018-04-20
1 | Installation of Bulk Header Manifold at Imo 1 FS |  |  | 2 | 4.082% | 100% | 2017-12-12 | 2018-03-25
2 | Tie-In of 2Nos Flowline From Imo River 3 F/S |  |  | 2 | 4.082% | 100% | 2017-12-13 | 2018-03-06
3 | Tie-In of 6" Bulk line from Imo River 2 F/S |  |  | 1 | 2.041% | 100% | 2017-12-13 | 2018-03-27
4 | Road Crossing of of Inlet Flowline to LP1 & LP2 Header Imo1 F/s |  |  | 1 | 2.041% | 100% | 2017-12-08 | 2017-12-15 | 2017-12-15
5 | Lay & Weld of Inlet F/L to LP & HP Header Imo1 f/s |  |  | 1 | 2.041% | 100% | 2017-12-04 | 2018-02-14
6 | Radigraphy of Inlet F/L to LP & HP Header Imo1 f/s |  |  | 1 | 2.041% | 100% | 2017-12-11 | 2018-03-28
7 | Hydrotest of Inlet F/L to LP & HP Header Imo1 f/s |  |  | 0.5 | 1.02% | 100% | 2017-12-18 | 2018-03-25
8 | Sleeving of Joints |  |  | 0.5 | 1.02% | 100% | 2017-12-16 | 2018-03-27
9 | Backfilling of flowline Road Crossing |  |  | 0.5 | 1.02% | 99% | 2017-12-20 | 2018-04-20
E | Demobilization & Site Cleean Up |  |  |  | 8.163% | 0% | 2017-12-25 | 2018-04-28
1 | SoF Sign off |  |  | 2 | 4.082% | 0% | 2017-12-25 | 2018-04-27
2 | Commissioning & Handover |  |  | 2 | 4.082% | 0% | 2017-12-25 | 2018-04-28
| Total |  |  | 49 | 100% | 75.95%
Formulas:
Contractor = MAX([Contractor, row below]:K38)