## Project
| Project Name | REROUTING OF IMO RIVER-2 & 3 TO IMO RIVER 1 FLOWSTATION | [5 empty] | Contractor |  | PEACOT NIG LTD
| Status Date | 2018-03-07 | Start Date | 2017-11-20 |  | Target End Date |  | 2018-03-23 |  |  | Budget |  | Available
| HIGHLIGHT |  |  |  |  | HSE STATISTICS |  |  |  | LOOK AHEAD
| HIGHLIGHTS - - Yard Fabrication of Spools for gathering manifold installation on going - 100% Complete - Radiography of Spools for the Imo 2 & 3 S/D conpleted - Personne Mobilized to site on 21/11/2017 - Shutdown of Imo 1 f/S for Tie-In activity on 22/11 - Installation of 2 Nos 4 x 600# ball valves for Tie-In to LP1 & LP2 at Imo 1 F/S Completed. - Boundary Reopening for the new bulkine in progress - 35% completed. - Stringing of 6" Line pipes along ROW - 13.2% completed - Probing and test digging in progress - Dist covered 140m, Cum dist. Covered 1.1km1.1km completed - Excavation for the two line tie-in into LP1 and LP2 at Imo 1 from the new manifold at Imo gathering point - 100% completed - Bush clearing along R.O.W - Dist. covered 223m, Cum dist.covered 1km - Excavation and Thrust boring for Lines going from Imo 3 to Imo 1 - 100% Completed - Excavation for new 6" Imo 2 bulkline - 38% Completed - Site opened after Xmas break on the 11/01/18 - Rerouting of Well 59T to Imo 3 - 100% Completed - Tie-In of the new 6" Bulk line welding in progress - 46% completed. - Tie-In of W43T at Imo 1 end completed. - Shutdown activities at Imo 3 on 21/02 -100% completed - Weld & Lay of Lines going to LP1 & LP2 hook-up - 81% Completed - Secured FTO to continue laying of 6" bulkline to Imo 2 on 26/02 - Cold cutting of disused pipes on the pipe rack at Imo1 f/s - 100% completed - Weld & Lay of Lines new 6" bulkline to Imo 2 - 49.5% Completed - Post Shutdown hook up activites for Imo 3 in progress. - 100% Completed - Completed Fabrication of Shutdown Spools for Imo 2- 100% Completed - Probing & Identification of W5L - 100% Completed. - Sleeving of welded joints on going - Cum 48% Completed. - Commenced flushing of W5L - Radiography of welded joints - 186 joints radiographed todate. 54% completed |  |  |  |  | CUM MH |  |  | 16659 | Continue with:
[6 empty] | POB |  |  | 20 | - Stringing of 6" PE coated Line pipes along Imo 1 to Imo 2 F/S - Boundary Reopening, line cutting/bush clearing of row for the new 6" bulk line - Welding of 6" B/L along ROW - Radiography of welded joints - Sleeving of welded joints - Bolt up of completed of spools for Imo3. - Installation of Shutdown Spools for Imo 2 - Tie-in of W5L at the Gathering Manifold at Imo 1 - Installation of IJ's at Imo 1 end
[6 empty] | UA/UC |  |  | 175
[6 empty] | NM |  | 0
| LOWLIGHTS: - Large volume of Crude slowing the flushing progress of in W5L |  |  |  |  | FAC |  | -
[6 empty] | MTC/RWC |  | -
[6 empty] | LWC |  | -
[6 empty] | HIPO |  | -
| Percentage Work Completion: |  | 36.89% |  |  | FATALITY |  | -
[6 empty] | NAD |  | -
| ACTIVITY PROGRESS | [9 empty] | ACTIVITY SUMMARY (YTD)
| WBS/Activity – O.NG.PAE.A1F.FAC.724FC |  |  | Unit | % Plan | % Complete | Target End Date | [6 empty] | DATE | %PLAN | %Cum (Plan) | %ACTUAL | %Cum (Actual) | DATE LINE
A | Imo River Rerouting Shutdown Activities |  |  |  | 17.48% | 15.53% | Start Date | End Date | Actual |  |  | Plan (Unit) | 51.5 | 2017-11-20 | 0% | 0% | 3.883% | 3.883%
1 | Yard Fabrication Tie-In Spools for Imo 1 f/s |  |  | 1 | 1.942% | 100% | 2017-11-21 | 2017-11-21 | 2017-11-21 |  |  | Completed (Unit) | 17 | 2017-11-21 | 0% | 0% | 3.883% | 7.767%
2 | Yard Fabrication Tie-In Spools for Imo 2 f/s |  |  | 1 | 1.942% | 100% | 2017-11-21 | 2017-11-21 | 2017-11-21 |  |  | In Progress (Unit) | 12 | 2017-11-22 | 0% | 0% | 3.883% | 11.65%
3 | Yard Fabrication Tie-In Spools for Imo 3 f/s |  |  | 1 | 1.942% | 100% | 2017-11-22 | 2017-11-24 | 2017-11-22 |  |  | Not Started (Unit) | 22.5 | 2017-11-23 | 0% | 0% | 0% | 11.65%
4 | Mobilization |  |  | 1 | 1.942% | 100% | 2017-12-18 | 2017-12-20 | 2017-11-22 |  |  | YTD Plan (%) | 49.51% | 2017-11-24 | 0% | 0% | 0% | 11.65%
5 | Site HSE Induction |  |  | 1 | 1.942% | 100% | 2017-12-12 | 2017-12-14 | 2017-12-14 |  |  | YTD Actual (%) | 36.89% | 2017-11-25 | 0% | 0% | 0% | 11.65%
6 | Tie-In of Imo River 1 F/S |  |  | 1 | 1.942% | 100% | 2017-11-20 | 2017-11-20 | 2017-11-20 |  |  | View S Curve |  | 2017-11-26 | 0% | 0% | 0% | 11.65%
7 | Yard Fabrication Gathering Manifold Header for Imo 1 f/s |  |  | 1 | 1.942% | 100% | 2017-11-20 | 2017-11-20 | 2017-11-20 |  |  |  |  | 2017-11-27 | 0% | 0% | 0% | 11.65%
8 | Tie-In of Imo River 3 F/S |  |  | 1 | 1.942% | 100% | 2017-11-20 | 2018-03-03 | [5 empty] | 2017-11-28 | 0% | 0% | 0% | 11.65%
9 | Tie-In of Imo River 2 F/S |  |  | 1 | 1.942% | 0% | 2017-12-13 | 2018-03-18 | [5 empty] | 2017-11-29 | 0% | 0% | 0% | 11.65%
B | Imo River 3 To Imo River 1 F/S |  |  |  | 27.18% | 17.48% | [7 empty] | 2017-11-30 | 0% | 0% | 0% | 11.65%
1 | Excavation of Imo 3 to Imo 1 Line 6" flowline |  |  | 1 | 1.942% | 100% | 2017-12-08 | 2017-12-08 | 2017-12-08 |  |  |  |  | 2017-12-01 | 0% | 0% | 0% | 11.65%
2 | Tie-back of W/5L to Imo 3 |  |  | 1 | 1.942% | 100% | 2018-03-07 | 2018-03-08
3 | Lay & Weld of 6" Line Imo 3 to Imo 1 f/s |  |  | 2 | 3.883% | 100% | 2017-12-11 | 2018-01-29 | [5 empty] | 2017-12-02 | 0% | 0% | 0% | 11.65%
4 | Radigraphy of 6" Line Imo 3 to Imo 1 f/s |  |  | 1 | 1.942% | 65% | 2017-12-13 | 2018-03-04 | [5 empty] | 2017-12-03 | 0% | 0% | 0% | 11.65%
5 | Hydrotest of 6" Line (W59T & W43T) Imo 3 to Imo 1 f/s |  |  | 1 | 1.942% | 0% | 2017-12-13 | 2018-03-06 | [5 empty] | 2017-12-04 | 0% | 0% | 0% | 11.65%
6 | Install Tie-in pieces and other shutdown works |  |  | 2 | 3.883% | 100% | 2018-03-09 | 2018-03-11
7 | Sleeving of Joints Imo 3 to Imo 1 f/s |  |  | 1 | 1.942% | 86% | 2017-12-13 | 2018-03-03 | [5 empty] | 2017-12-05 | 0% | 0% | 0% | 11.65%
8 | Road Crossing From Imo 3 F/s to Gatering Manifold |  |  | 2 | 3.883% | 100% | 2017-12-10 | 2017-12-31 | [5 empty] | 2017-12-06 | 0% | 0% | 0% | 11.65%
9 | Lowering of flowline From Imo 3 to Imo 1 F/S |  |  | 1 | 1.942% | 100% | 2017-12-13 | 2018-02-03 | [5 empty] | 2017-12-07 | 0% | 0% | 0% | 11.65%
10 | Backfilling of flowline ROW |  |  | 0.5 | 0.9709% | 0% | 2017-12-14 | 2018-02-04 | [5 empty] | 2017-12-08 | 0% | 0% | 1.942% | 13.59%
11 | Locate 4" flowline (W/5L) to Imo 1 manifold |  |  | 0.5 | 0.9709% | 100% | 2018-03-01 | 2018-03-04
12 | Tie-back 4" flowline to ex-59T ligaments |  |  | 1 | 1.942% | 25% | 2018-03-05 | 2018-03-10
C | Imo River 2 To Imo River 1 F/S |  |  |  | 27.18% | 0% | [7 empty] | 2017-12-09 | 0% | 0% | 0% | 13.59%
1 | Excavation of Imo 2 to Imo 1 Line 6" flowline |  |  | 1 | 1.942% | 50% | 2017-12-12 | 2018-03-10 | [5 empty] | 2017-12-10 | 0% | 0% | 0% | 13.59%
2 | Lay & Weld of 6" Bulk Line Imo 2 to Imo 1 f/s |  |  | 2 | 3.883% | 50% | 2017-11-30 | 2018-03-12 | [5 empty] | 2017-12-11 | 0% | 0% | 0% | 13.59%
3 | Radigraphy of 6" Bulk line Line Imo 2 to Imo 1 f/s |  |  | 1 | 1.942% | 46% | 2017-12-04 | 2018-03-13 | [5 empty] | 2017-12-12 | 0% | 0% | 0% | 13.59%
4 | Hydrotest of 6" Line Imo 2 to Imo 1 f/s |  |  | 1 | 1.942% | 0% | 2017-12-19 | 2018-03-14 | [5 empty] | 2017-12-13 | 0% | 0% | 0% | 13.59%
5 | Sleeving of Joints Imo 2 to Imo 1 f/s |  |  | 1 | 1.942% | 50% | 2017-12-04 | 2018-03-16 | [5 empty] | 2017-12-14 | 0% | 0% | 1.942% | 15.53%
6 | Road Crossing From Imo 2 F/s to Imo River 1 f/s |  |  | 1 | 1.942% | 50% | 2017-12-12 | 2018-02-14 | [5 empty] | 2017-12-15 | 0% | 0% | 1.942% | 17.48%
7 | Lowering of flowline from Imo 2 to Imo 1 F/S |  |  | 1 | 1.942% | 40% | 2017-12-16 | 2018-03-10 | [5 empty] | 2017-12-16 | 0% | 0% | 0% | 17.48%
8 | Backfilling of flowline ROW |  |  | 0.5 | 0.9709% | 0% | 2017-12-20 | 2018-03-18 | [5 empty] | 2017-12-17 | 0% | 0% | 0% | 17.48%
9 | Locate 4" flowlines (25L, 21S) |  |  | 0.5 | 0.9709% | 0% | 2018-02-12 | 2018-03-03
10 | Tie-back 4" flowlines to Imo 2 |  |  | 1 | 1.942% | 0% | 2018-03-13 | 2018-03-14
11 | Install Tie-in pieces and other shutdown works |  |  | 2 | 3.883% | 0% | 2018-03-14 | 2018-03-17
12 | Tie-back 4" bulk lines to Imo 1 |  |  | 1 | 1.942% | 0% | 2018-03-14 | 2018-03-17
13 | Gas generator fuel gas line modification |  |  | 1 | 1.942% | 0% | 2018-03-17 | 2018-03-20
D | Imo River 1 Gathering Manifold |  |  |  | 20.39% | 3.883% | [7 empty] | 2017-12-18 | 0% | 0% | 0% | 17.48%
1 | Installation of Bulk Header Manifold at Imo 1 FS |  |  | 2 | 3.883% | 0% | 2017-12-12 | 2018-03-07 | [5 empty] | 2017-12-19 | 0% | 0% | 0% | 17.48%
2 | Tie-In of 2Nos Flowline From Imo River 3 F/S |  |  | 2 | 3.883% | 95% | 2017-12-13 | 2018-03-06 | [5 empty] | 2017-12-20 | 0% | 0% | 0% | 17.48%
3 | Tie-In of 6" Bulk line from Imo River 2 F/S |  |  | 1 | 1.942% | 43% | 2017-12-13 | 2018-03-10 | [5 empty] | 2017-12-21 | 0% | 0% | 0% | 17.48%
4 | Road Crossing of of Inlet Flowline to LP1 & LP2 Header Imo1 F/s |  |  | 1 | 1.942% | 100% | 2017-12-08 | 2017-12-15 | 2017-12-15 |  |  |  |  | 2017-12-22 | 0% | 0% | 0% | 17.48%
5 | Lay & Weld of Inlet F/L to LP & HP Header Imo1 f/s |  |  | 1 | 1.942% | 100% | 2017-12-04 | 2018-02-14 | [5 empty] | 2017-12-23 | 0% | 0% | 0% | 17.48%
6 | Radigraphy of Inlet F/L to LP & HP Header Imo1 f/s |  |  | 1 | 1.942% | 51% | 2017-12-11 | 2018-03-13 | [5 empty] | 2017-12-24 | 0% | 0% | 0% | 17.48%
7 | Hydrotest of Inlet F/L to LP & HP Header Imo1 f/s |  |  | 1 | 1.942% | 0% | 2017-12-18 | 2018-03-15 | [5 empty] | 2017-12-25 | 0% | 0% | 0% | 17.48%
8 | Sleeving of Joints |  |  | 1 | 1.942% | 25% | 2017-12-16 | 2018-03-16 | [5 empty] | 2017-12-26 | 0% | 0% | 0% | 17.48%
9 | Backfilling of flowline Road Crossing |  |  | 0.5 | 0.9709% | 0% | 2017-12-20 | 2018-03-18 | [5 empty] | 2017-12-27 | 0% | 0% | 0% | 17.48%
E | Demobilization & Site Cleean Up |  |  |  | 7.767% | 0% | [7 empty] | 2017-12-28 | 0% | 0% | 0% | 17.48%
1 | SoF Sign off |  |  | 2 | 3.883% | 0% | 2017-12-25 | 2018-03-23 | [5 empty] | 2017-12-29 | 0% | 0% | 0% | 17.48%
2 | Commissioning & Handover |  |  | 2 | 3.883% | 0% | 2017-12-25 | 2018-03-23 | [5 empty] | 2017-12-30 | 0% | 0% | 0% | 17.48%
| Total |  |  | 51.5 | 100% | 36.89% | [7 empty] | 2017-12-31 | 0% | 0% | 0% | 17.48%

## S-Curve
View Report