## Sheet1
Order | Scheduled start | Scheduled finish | Latest Allowed Finish Date | User Status | Total planned costs | Estimated costs | Total actual costs | System status | Notification | Description | FunctLocDescrip. | Functional Location | Order Type | Main work center
22439153 | 2016-05-19 | 2016-05-21 | 2016-06-07 | XCNF MAXX XGI | 12917.61 | 12917.61 | 9124.74 | TECO CNF PRT GMPS PRC SETC | 11470916 | RECTIFY TRIP ON AIR COMPR K6801 | COMP, K-6801, INST AIR SYS, OKOG1 | NG.OKOG1.K-6801-K-6801LOD | 72FC | AFAMECH
22425336 | 2016-03-21 | 2016-03-22 | 2016-04-17 | XCNF XGI | 2112.8 | 2112.8 | 2029.2 | CLSD CNF PRT NMAT PRC SETC | 11460147 | REPAIR AIR COMPRESSOR K-6801 | COMP, K-6801, INST AIR SYS, OKOG1 | NG.OKOG1.K-6801-K-6801LOD | 72FC | AFAMECH
22456150 | 2016-08-04 | 2016-08-04 | 2016-08-16 | XCNF XGI | 699.2 | 699.2 | 532 | CLSD CNF PRT NMAT PRC SETC | 11496105 | 1M CHECKS ON AIR COMPRESSOR K-6801 | COMP, K-6801, INST AIR SYS, OKOG1 | NG.OKOG1.K-6801-K-6801LOD | 72FP | AFAMECH
22423647 | 2016-04-13 | 2016-04-13 | 2016-04-18 | XCNF XGI | 699.2 | 699.2 | 699.2 | CLSD CNF PRT NMAT PRC SETC | 11471039 | 1M CHECKS ON BOGE AIR COMPRESSOR K-6801 | COMP, K-6801, INST AIR SYS, OKOG1 | NG.OKOG1.K-6801-K-6801LOD | 72FP | AFAMECH
22406163 | 2016-02-13 | 2016-02-13 | 2016-02-18 | XCNF WPOK XGI | 1010.8 | 1010.8 | 1010.8 | CLSD CNF PRT NMAT PRC SETC | 11458305 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6801, INST AIR SYS, OKOG1 | NG.OKOG1.K-6801-K-6801LOD | 72FP | AFAMECH
22464314 | 2016-09-09 | 2016-09-09 | 2016-09-15 | XCNF WPOK XGI | 608 | 608 | 608 | TECO CNF PRT NMAT PRC SETC | 11503803 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6801, INST AIR SYS, OKOG1 | NG.OKOG1.K-6801-K-6801LOD | 72FP | AFAMECH
22481069 | 2016-11-08 | 2016-11-08 | 2016-11-14 | XCNF WPOK XGI | 691.6 | 691.6 | 691.6 | TECO CNF PRT NMAT PRC SETC | 11517046 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6801, INST AIR SYS, OKOG1 | NG.OKOG1.K-6801-K-6801LOD | 72FP | AFAMECH
22439815 | 2016-06-10 | 2016-06-10 | 2016-06-17 | XCNF XGI | 638.4 | 638.4 | 471.2 | CLSD CNF PRT NMAT PRC SETC | 11483597 | 1M PM CHECKS ON AIR COMPRESSOR K-6801 | COMP, K-6801, INST AIR SYS, OKOG1 | NG.OKOG1.K-6801-K-6801LOD | 72FP | AFAMECH
22398092 | 2016-01-13 | 2016-01-13 | 2016-01-19 | XCNF WPOK XGI | 623.2 | 623.2 | 592.8 | CLSD CNF PRT NMAT PRC SETC | 11451735 | 1M PM ON AIR COMPRESSOR K-6801 | COMP, K-6801, INST AIR SYS, OKOG1 | NG.OKOG1.K-6801-K-6801LOD | 72FP | AFAMECH
22431682 | 2016-05-09 | 2016-05-09 | 2016-05-18 | XCNF XGI | 585.2 | 585.2 | 585.2 | CLSD CNF PRT NMAT PRC SETC | 11476420 | 1M PM ON AIR COMPRESSOR K-6801 | COMP, K-6801, INST AIR SYS, OKOG1 | NG.OKOG1.K-6801-K-6801LOD | 72FP | AFAMECH
22448320 | 2016-07-12 | 2016-07-12 | 2016-07-17 | XCNF XGI | 577.6 | 577.6 | 448.4 | CLSD CNF PRT NMAT PRC SETC | 11491241 | 1M PM ON AIR COMPRESSOR K-6801 | COMP, K-6801, INST AIR SYS, OKOG1 | NG.OKOG1.K-6801-K-6801LOD | 72FP | AFAMECH
22473018 | 2016-10-08 | 2016-10-08 | 2016-10-15 | XCNF XGI | 684 | 684 | 684 | TECO CNF PRT NMAT PRC SETC | 11510436 | 1M PM ON AIR COMPRESSOR K-6801 | COMP, K-6801, INST AIR SYS, OKOG1 | NG.OKOG1.K-6801-K-6801LOD | 72FP | AFAMECH
22489362 | 2016-11-30 | 2016-11-30 | 2016-12-14 | XCNF XGI | 600.4 | 600.4 | 539.6 | TECO CNF PRT NMAT PRC SETC | 11521475 | 1M PM ON AIR COMPRESSOR K-6801 | COMP, K-6801, INST AIR SYS, OKOG1 | NG.OKOG1.K-6801-K-6801LOD | 72FP | AFAMECH
22414571 | 2016-05-30 | 2016-05-30 | 2016-06-09 | XCNF WPOK XGI | 851.2 | 851.2 | 851.2 | CLSD CNF PRT NMAT PRC SETC | 11480993 | 1Y PM ON AIR COMPRESSOR K-6801 | COMP, K-6801, INST AIR SYS, OKOG1 | NG.OKOG1.K-6801-K-6801LOD | 72FP | AFAMECH
22412059 | 2016-05-29 | 2016-05-29 | 2016-06-08 | XCNF WPOK XGI | 722 | 722 | 722 | CLSD CNF PRT ILAS NMAT PRC SETC | 11480721 | 1Y ELECTRIC MOTOR MAINTENANCE PM | MOTOR, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-EM-6802 | 72FP | AFAELEC
22386735 | 2016-03-01 | 2016-03-01 | 2016-03-10 | XCNF WPOK XGI | 456 | 456 | 456 | CLSD CNF PRT ILAS NMAT PRC SETC | 11462057 | 3M ELECTRIC MOTOR MAINTENANCE PM | MOTOR, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-EM-6802 | 72FP | AFAELEC
22437306 | 2016-08-21 | 2016-08-21 | 2016-09-06 | XCNF XGI | 456 | 456 | 0 | CLSD CNF ESTC ILAS NMAT PRC SETC | 11499404 | 3M ELECTRIC MOTOR MAINTENANCE PM | MOTOR, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-EM-6802 | 72FP | AFAELEC
22461965 | 2016-11-25 | 2016-11-25 | 2016-12-05 | XCNF XGI | 456 | 456 | 456 | TECO CNF PRT ILAS NMAT PRC SETC | 11520485 | 3M ELECTRIC MOTOR MAINTENANCE PM | MOTOR, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-EM-6802 | 72FP | AFAELEC
22455451 | 2016-11-30 | 2016-12-02 | 2016-12-06 | XCNF MANX XGI | 17894.13 | 18448.8 | 11758.74 | TECO CNF ESTC GMPS PRC SETC | 11483162 | OVERHAUL BOGE AIR COMP K-6802 | COMP, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-K-6802LOD | 72FC | AFAMECH
22455891 | 2016-08-04 | 2016-08-04 | 2016-08-15 | XCNF XGI | 699.2 | 699.2 | 0 | CLSD CNF PRT NMAT PRC SETC | 11496103 | 1M CHECKS ON AIR COMPRESSOR K-6802 | COMP, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-K-6802LOD | 72FP | AFAMECH
22423238 | 2016-04-10 | 2016-04-10 | 2016-04-17 | XCNF WPOK XGI | 623.2 | 623.2 | 0 | CLSD CNF PRT NMAT PRC SETC | 11470879 | 1M CHECKS ON BOGE AIR COMPRESSOR K-6802 | COMP, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-K-6802LOD | 72FP | AFAMECH
22405891 | 2016-02-12 | 2016-02-12 | 2016-02-17 | XCNF WPOK XGI | 630.8 | 630.8 | 630.8 | CLSD CNF PRT NMAT PRC SETC | 11458145 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-K-6802LOD | 72FP | AFAMECH
22431428 | 2016-05-07 | 2016-05-07 | 2016-05-17 | XCNF WPOK XGI | 585.2 | 585.2 | 0 | CLSD CNF PRT NMAT PRC SETC | 11475970 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-K-6802LOD | 72FP | AFAMECH
22464062 | 2016-09-09 | 2016-09-09 | 2016-09-14 | XCNF WPOK XGI | 661.2 | 661.2 | 661.2 | TECO CNF PRT NMAT PRC SETC | 11503804 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-K-6802LOD | 72FP | AFAMECH
22480680 | 2016-11-07 | 2016-11-07 | 2016-11-13 | XCNF WPOK XGI | 729.6 | 729.6 | 729.6 | TECO CNF PRT NMAT PRC SETC | 11516802 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-K-6802LOD | 72FP | AFAMECH
22397678 | 2016-01-12 | 2016-01-12 | 2016-01-18 | XCNF WPOK XGI | 623.2 | 623.2 | 516.8 | CLSD CNF PRT NMAT PRC SETC | 11451556 | 1M PM ON AIR COMPREESOR K-6802 | COMP, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-K-6802LOD | 72FP | AFAMECH
22447944 | 2016-07-12 | 2016-07-12 | 2016-07-16 | XCNF XGI | 577.6 | 577.6 | 0 | CLSD CNF PRT NMAT PRC SETC | 11491240 | 1M PM ON AIR COMPRESSOR K-6802 | COMP, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-K-6802LOD | 72FP | AFAMECH
22472698 | 2016-10-11 | 2016-10-11 | 2016-10-14 | XCNF XGI | 729.6 | 729.6 | 691.6 | TECO CNF ESTC NMAT PRC SETC | 11511062 | 1M PM ON AIR COMPRESSOR K-6802 | COMP, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-K-6802LOD | 72FP | AFAMECH
22489069 | 2016-11-30 | 2016-11-30 | 2016-12-13 | XCNF XGI | 600.4 | 600.4 | 509.2 | TECO CNF PRT NMAT PRC SETC | 11521474 | 1M PM ON AIR COMPRESSOR K-6802 | COMP, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-K-6802LOD | 72FP | AFAMECH
22439551 | 2016-06-10 | 2016-06-10 | 2016-06-16 | XCNF XGI | 638.4 | 638.4 | 0 | CLSD CNF PRT NMAT PRC SETC | 11483595 | 1M PM ON BOGE AIR COMPRESSOR K-6802 | COMP, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-K-6802LOD | 72FP | AFAMECH
22414246 | 2016-05-30 | 2016-05-30 | 2016-06-08 | XCNF WPOK XGI | 547.2 | 547.2 | 547.2 | CLSD CNF PRT NMAT PRC SETC | 11480992 | 1Y PM ON AIR COMPRESSOR K-6802 | COMP, K-6802, INST AIR SYS, OKOG1 | NG.OKOG1.K-6802-K-6802LOD | 72FP | AFAMECH
22479633 | 2016-12-11 | 2016-12-11 | 2016-12-15 | XCNF WPOK XGI | 456 | 608 | 456 | TECO CNF PRT ILAS NMAT PRC SETC | 11524078 | 1Y ELECTRIC MOTOR MAINTENANCE PM - OKOG1 | MOTOR, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-EM-6803 | 72FP | AFAELEC
22404541 | 2016-03-12 | 2016-03-12 | 2016-03-20 | XCNF WPOK XGI | 532 | 532 | 532 | CLSD CNF PRT ILAS NMAT PRC SETC | 11464469 | 3M ELECTRIC MOTOR MAINTENANCE PM - OKOG1 | MOTOR, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-EM-6803 | 72FP | AFAELEC
22430200 | 2016-06-11 | 2016-06-11 | 2016-06-18 | XCNF WPOK XGI | 608 | 608 | 608 | CLSD CNF PRT ILAS NMAT PRC SETC | 11483775 | 3M ELECTRIC MOTOR MAINTENANCE PM - OKOG1 | MOTOR, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-EM-6803 | 72FP | AFAELEC
22454623 | 2016-09-05 | 2016-09-05 | 2016-09-16 | XCNF WPOK XGI | 456 | 456 | 456 | TECO CNF PRT ILAS NMAT PRC SETC | 11502922 | 3M ELECTRIC MOTOR MAINTENANCE PM - OKOG1 | MOTOR, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-EM-6803 | 72FP | AFAELEC
22439154 | 2016-05-19 | 2016-05-20 | 2016-06-07 | XCNF MAXX XGI | 12917.61 | 12917.61 | 4606.76 | CLSD CNF ESTC GMPS PRC SETC | 11470917 | TRIPPING COMPR K6803 ON SYS. PRESSURE | COMP, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-K-6803LOD | 72FC | AFAMECH
22455611 | 2016-08-04 | 2016-08-04 | 2016-08-14 | XCNF XGI | 699.2 | 699.2 | 532 | CLSD CNF PRT NMAT PRC SETC | 11496100 | 1M CHECKS ON AIR COMPRESSOR K-6803 | COMP, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-K-6803LOD | 72FP | AFAMECH
22422765 | 2016-04-10 | 2016-04-10 | 2016-04-16 | XCNF WPOK XGI | 699.2 | 699.2 | 615.6 | CLSD CNF PRT NMAT PRC SETC | 11470877 | 1M CHECKS ON BOGE AIR COMPRESSOR K-6803 | COMP, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-K-6803LOD | 72FP | AFAMECH
22405604 | 2016-02-12 | 2016-02-12 | 2016-02-16 | XCNF WPOK XGI | 798 | 798 | 798 | CLSD CNF PRT NMAT PRC SETC | 11458147 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-K-6803LOD | 72FP | AFAMECH
22431174 | 2016-05-07 | 2016-05-07 | 2016-05-16 | XCNF WPOK XGI | 585.2 | 585.2 | 0 | CLSD CNF PRT NMAT PRC SETC | 11475965 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-K-6803LOD | 72FP | AFAMECH
22463792 | 2016-09-09 | 2016-09-09 | 2016-09-13 | XCNF WPOK XGI | 577.6 | 577.6 | 577.6 | TECO CNF PRT NMAT PRC SETC | 11503806 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-K-6803LOD | 72FP | AFAMECH
22480441 | 2016-11-08 | 2016-11-08 | 2016-11-12 | XCNF WPOK XGI | 577.6 | 577.6 | 577.6 | TECO CNF PRT NMAT PRC SETC | 11517048 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-K-6803LOD | 72FP | AFAMECH
22488801 | 2016-12-06 | 2016-12-06 | 2016-12-12 | XCNF WPOK XGI | 600.4 | 600.4 | 600.4 | TECO CNF PRT NMAT PRC SETC | 11522944 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-K-6803LOD | 72FP | AFAMECH
22397336 | 2016-01-12 | 2016-01-12 | 2016-01-17 | XCNF WPOK XGI | 699.2 | 699.2 | 615.6 | CLSD CNF PRT NMAT PRC SETC | 11451555 | 1M PM ON AIR COMPRESSOR K-6803 | COMP, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-K-6803LOD | 72FP | AFAMECH
22447617 | 2016-07-11 | 2016-07-11 | 2016-07-15 | XCNF XGI | 661.2 | 661.2 | 456 | CLSD CNF PRT NMAT PRC SETC | 11491010 | 1M PM ON AIR COMPRESSOR K-6803 | COMP, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-K-6803LOD | 72FP | AFAMECH
22472447 | 2016-10-11 | 2016-10-11 | 2016-10-13 | XCNF XGI | 691.6 | 691.6 | 691.6 | TECO CNF ESTC NMAT PRC SETC | 11511063 | 1M PM ON AIR COMPRESSOR K-6803 | COMP, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-K-6803LOD | 72FP | AFAMECH
22439306 | 2016-06-10 | 2016-06-10 | 2016-06-15 | XCNF XGI | 638.4 | 638.4 | 516.8 | CLSD CNF PRT NMAT PRC SETC | 11483596 | 1M PM ON BOGE AIR COMPRESSOR K-6803 | COMP, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-K-6803LOD | 72FP | AFAMECH
22414004 | 2016-05-30 | 2016-05-30 | 2016-06-07 | XCNF WPOK XGI | 623.2 | 623.2 | 623.2 | CLSD CNF PRT NMAT PRC SETC | 11480990 | 1Y PM ON AIR COMPRESSOR ON K-6803 | COMP, K-6803, INST AIR SYS, OKOG1 | NG.OKOG1.K-6803-K-6803LOD | 72FP | AFAMECH
22460836 | 2016-09-11 | 2016-09-11 | 2016-09-28 | XCNF WPOK XGI | 456 | 456 | 456 | TECO CNF PRT ILAS NMAT PRC SETC | 11504362 | 3M MTCE OF COMPRESSOR ELECTRIC MOTOR - O | MOT,INSTR AIR COMPR PKG A,OKOG1 | NG.OKOG1.K-6807-KM6807 | 72FP | AFAELEC
22467978 | 2016-12-18 | 2016-12-18 | 2016-12-27 | XCNF WPOK XGI | 456 | 456 | 471.2 | TECO CNF PRT ILAS NMAT PRC SETC | 11525621 | 3M MTCE OF COMPRESSOR ELECTRIC MOTOR - O | MOT,INSTR AIR COMPR PKG A,OKOG1 | NG.OKOG1.K-6807-KM6807 | 72FP | AFAELEC
22479057 | 2016-12-02 | 2016-12-02 | 2016-12-13 | XCNF WPOK XGI | 456 | 456 | 456 | TECO CNF PRT ILAS NMAT PRC SETC | 11521983 | 1Y ELECTRIC MOTOR MAINTENANCE PM - OKOG1 | MOTOR, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-EM-6891 | 72FP | AFAELEC
22404056 | 2016-03-09 | 2016-03-09 | 2016-03-18 | XCNF WPOK XGI | 456 | 608 | 456 | CLSD CNF PRT ILAS NMAT PRC SETC | 11463716 | 3M ELECTRIC MOTOR MAINTENANCE PM - OKOG1 | MOTOR, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-EM-6891 | 72FP | AFAELEC
22429712 | 2016-06-08 | 2016-06-08 | 2016-06-16 | XCNF WPOK XGI | 456 | 456 | 456 | CLSD CNF PRT ILAS NMAT PRC SETC | 11483125 | 3M ELECTRIC MOTOR MAINTENANCE PM - OKOG1 | MOTOR, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-EM-6891 | 72FP | AFAELEC
22454110 | 2016-09-09 | 2016-09-09 | 2016-09-14 | XCNF XGI | 608 | 608 | 456 | TECO CNF PRT ILAS NMAT PRC SETC | 11503916 | 3M ELECTRIC MOTOR MAINTENANCE PM - OKOG1 | MOTOR, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-EM-6891 | 72FP | AFAELEC
22455312 | 2016-08-05 | 2016-08-05 | 2016-08-13 | XCNF XGI | 699.2 | 699.2 | 539.6 | CLSD CNF PRT NMAT PRC SETC | 11496202 | 1M CHECKS ON AIR COMPRESSOR K-6891 | COMP, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-K-6891LOD | 72FP | AFAMECH
22422766 | 2016-04-13 | 2016-04-13 | 2016-04-15 | XCNF XGI | 699.2 | 699.2 | 699.2 | CLSD CNF PRT NMAT PRC SETC | 11471037 | 1M CHECKS ON BOGE AIR COMPRESSOR K-6891 | COMP, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-K-6891LOD | 72FP | AFAMECH
22438986 | 2016-06-08 | 2016-06-08 | 2016-06-14 | XCNF XGI | 638.4 | 638.4 | 547.2 | CLSD CNF PRT NMAT PRC SETC | 11483112 | 1M CHECKS ON BOGE AIR COMPRESSOR K-6891 | COMP, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-K-6891LOD | 72FP | AFAMECH
22405349 | 2016-02-10 | 2016-02-10 | 2016-02-15 | XCNF WPOK XGI | 646 | 646 | 494 | CLSD CNF PRT NMAT PRC SETC | 11457773 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-K-6891LOD | 72FP | AFAMECH
22430875 | 2016-05-06 | 2016-05-06 | 2016-05-15 | XCNF WPOK XGI | 585.2 | 585.2 | 494 | CLSD CNF PRT NMAT PRC SETC | 11475790 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-K-6891LOD | 72FP | AFAMECH
22463426 | 2016-09-02 | 2016-09-02 | 2016-09-12 | XCNF WPOK XGI | 630.8 | 630.8 | 623.2 | TECO CNF PRT NMAT PRC SETC | 11502284 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-K-6891LOD | 72FP | AFAMECH
22447379 | 2016-07-11 | 2016-07-11 | 2016-07-14 | XCNF XGI | 729.6 | 729.6 | 646 | CLSD CNF PRT NMAT PRC SETC | 11491008 | 1M PM CHECKS ON AIR COMPRESSOR K-6891 | COMP, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-K-6891LOD | 72FP | AFAMECH
22397057 | 2016-01-10 | 2016-01-10 | 2016-01-16 | XCNF WPOK XGI | 775.2 | 775.2 | 691.6 | CLSD CNF PRT NMAT PRC SETC | 11451245 | 1M PM ON AIR COMPRESSOR K-6891 | COMP, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-K-6891LOD | 72FP | AFAMECH
22472073 | 2016-10-07 | 2016-10-07 | 2016-10-12 | XCNF XGI | 684 | 684 | 684 | TECO CNF PRT NMAT PRC SETC | 11510437 | 1M PM ON AIR COMPRESSOR K-6891 | COMP, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-K-6891LOD | 72FP | AFAMECH
22480188 | 2016-11-04 | 2016-11-04 | 2016-11-11 | XCNF XGI | 577.6 | 577.6 | 501.6 | TECO CNF PRT NMAT PRC SETC | 11516135 | 1M PM ON AIR COMPRESSOR K-6891 | COMP, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-K-6891LOD | 72FP | AFAMECH
22488478 | 2016-12-02 | 2016-12-02 | 2016-12-11 | XCNF XGI | 600.4 | 600.4 | 600.4 | TECO CNF PRT NMAT PRC SETC | 11521942 | 1M PM ON AIR COMPRESSOR K-6891 | COMP, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-K-6891LOD | 72FP | AFAMECH
22413720 | 2016-05-27 | 2016-05-27 | 2016-06-06 | XCNF WPOK XGI | 623.2 | 623.2 | 623.2 | CLSD CNF PRT NMAT PRC SETC | 11480340 | 1Y PM ON AIR COMPRESSOR K-6891 | COMP, K-6891, INST AIR SYS, OKOG1 | NG.OKOG1.K-6891-K-6891LOD | 72FP | AFAMECH
22478814 | 2016-12-02 | 2016-12-02 | 2016-12-12 | XCNF WPOK XGI | 456 | 456 | 380 | TECO CNF ESTC ILAS NMAT PRC SETC | 11521988 | 1Y ELECTRIC MOTOR MAINTENANCE PM - OKOG1 | MOTOR, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-EM-6892 | 72FP | AFAELEC
22403792 | 2016-03-09 | 2016-03-09 | 2016-03-17 | XCNF WPOK XGI | 608 | 608 | 608 | CLSD CNF PRT ILAS NMAT PRC SETC | 11463717 | 3M ELECTRIC MOTOR MAINTENANCE PM - OKOG1 | MOTOR, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-EM-6892 | 72FP | AFAELEC
22429499 | 2016-06-08 | 2016-06-08 | 2016-06-15 | XCNF WPOK XGI | 456 | 456 | 456 | CLSD CNF PRT ILAS NMAT PRC SETC | 11483113 | 3M ELECTRIC MOTOR MAINTENANCE PM - OKOG1 | MOTOR, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-EM-6892 | 72FP | AFAELEC
22453816 | 2016-09-09 | 2016-09-09 | 2016-09-13 | XCNF WPOK XGI | 456 | 456 | 456 | TECO CNF ESTC ILAS NMAT PRC SETC | 11503917 | 3M ELECTRIC MOTOR MAINTENANCE PM - OKOG1 | MOTOR, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-EM-6892 | 72FP | AFAELEC
22447074 | 2016-07-11 | 2016-07-11 | 2016-07-13 | XCNF XGI | 775.2 | 775.2 | 539.6 | CLSD CNF PRT NMAT PRC SETC | 11491011 | 1M CHECKS ON AIR COMPRESSOR K-6892 | COMP, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-K-6892LOD | 72FP | AFAMECH
22422767 | 2016-04-13 | 2016-04-13 | 2016-04-14 | XCNF XGI | 866.4 | 866.4 | 866.4 | CLSD CNF PRT NMAT PRC SETC | 11471038 | 1M CHECKS ON BOGE AIR COMPRESSOR K-6892 | COMP, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-K-6892LOD | 72FP | AFAMECH
22438652 | 2016-06-08 | 2016-06-08 | 2016-06-13 | XCNF XGI | 638.4 | 638.4 | 592.8 | CLSD CNF PRT NMAT PRC SETC | 11483111 | 1M CHECKS ON BOGE AIR COMPRESSOR K-6892 | COMP, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-K-6892LOD | 72FP | AFAMECH
22405067 | 2016-02-10 | 2016-02-10 | 2016-02-14 | XCNF WPOK XGI | 722 | 722 | 646 | CLSD CNF PRT NMAT PRC SETC | 11457772 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-K-6892LOD | 72FP | AFAMECH
22430564 | 2016-05-06 | 2016-05-06 | 2016-05-14 | XCNF WPOK XGI | 585.2 | 585.2 | 501.6 | CLSD CNF PRT NMAT PRC SETC | 11475788 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-K-6892LOD | 72FP | AFAMECH
22463116 | 2016-09-02 | 2016-09-02 | 2016-09-11 | XCNF WPOK XGI | 623.2 | 623.2 | 608 | TECO CNF PRT NMAT PRC SETC | 11502271 | 1M CHECKS ON BOGE SR270 AIR COMPRESSOR | COMP, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-K-6892LOD | 72FP | AFAMECH
22396754 | 2016-01-10 | 2016-01-10 | 2016-01-15 | XCNF WPOK XGI | 547.2 | 547.2 | 501.6 | CLSD CNF PRT NMAT PRC SETC | 11451244 | 1M PM ON AIR COMPRESSOR K-6892 | COMP, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-K-6892LOD | 72FP | AFAMECH
22455010 | 2016-08-05 | 2016-08-05 | 2016-08-12 | XCNF XGI | 623.2 | 623.2 | 410.4 | CLSD CNF PRT NMAT PRC SETC | 11496339 | 1M PM ON AIR COMPRESSOR K-6892 | COMP, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-K-6892LOD | 72FP | AFAMECH
22471732 | 2016-10-07 | 2016-10-07 | 2016-10-11 | XCNF XGI | 684 | 684 | 684 | TECO CNF PRT NMAT PRC SETC | 11510438 | 1M PM ON AIR COMPRESSOR K-6892 | COMP, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-K-6892LOD | 72FP | AFAMECH
22479996 | 2016-11-04 | 2016-11-04 | 2016-11-10 | XCNF XGI | 577.6 | 577.6 | 570 | TECO CNF PRT NMAT PRC SETC | 11516134 | 1M PM ON AIR COMPRESSOR K-6892 | COMP, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-K-6892LOD | 72FP | AFAMECH
22488185 | 2016-12-02 | 2016-12-02 | 2016-12-10 | XCNF XGI | 600.4 | 600.4 | 600.4 | TECO CNF PRT NMAT PRC SETC | 11521943 | 1M PM ON AIR COMPRESSOR K-6892 | COMP, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-K-6892LOD | 72FP | AFAMECH
22413467 | 2016-05-27 | 2016-05-27 | 2016-06-05 | XCNF WPOK XGI | 775.2 | 775.2 | 874 | CLSD CNF PRT NMAT PRC SETC | 11480339 | 1Y PM ON AIR COMPRESSOR K-6892 | COMP, K-6892, INST AIR SYS, OKOG1 | NG.OKOG1.K-6892-K-6892LOD | 72FP | AFAMECH
22412077 | 2016-05-21 | 2016-05-21 | 2016-06-08 | XCNF XGI | 494 | 722 | 494 | CLSD CNF ESTC ILAS NMAT PRC SETC | 11478954 | 1Y ELECTRIC MOTOR MAINTENANCE ELEC PM | MOTOR, K-6893, INST AIR SYS, OKOG1 | NG.OKOG1.K-6893-EM-6893 | 72FP | AFAELEC
22386756 | 2016-03-02 | 2016-03-02 | 2016-03-10 | XCNF WPOK XGI | 380 | 380 | 380 | CLSD CNF PRT ILAS NMAT PRC SETC | 11462242 | 3M ELECTRIC MOTOR MAINTENANCE ELEC PM | MOTOR, K-6893, INST AIR SYS, OKOG1 | NG.OKOG1.K-6893-EM-6893 | 72FP | AFAELEC
22437324 | 2016-08-24 | 2016-08-24 | 2016-09-06 | XCNF XGI | 456 | 456 | 456 | CLSD CNF ESTC ILAS NMAT PRC SETC | 11500122 | 3M ELECTRIC MOTOR MAINTENANCE ELEC PM | MOTOR, K-6893, INST AIR SYS, OKOG1 | NG.OKOG1.K-6893-EM-6893 | 72FP | AFAELEC
22461980 | 2016-11-25 | 2016-11-25 | 2016-12-05 | XCNF XGI | 456 | 456 | 425.6 | TECO CNF ESTC ILAS NMAT PRC SETC | 11520472 | 3M ELECTRIC MOTOR MAINTENANCE ELEC PM | MOTOR, K-6893, INST AIR SYS, OKOG1 | NG.OKOG1.K-6893-EM-6893 | 72FP | AFAELEC