## Slide 1
SEPARATION OF POWER SUPPLY CABLES TO AGBADA/2 FLOWSTATION,FOC AND JTF CAMP FROM AGG INCOMER
Business Case/objectives:
Carrying out proper isolation of Agbada/2 flowstation and Joint Task Force (JTF) camp makes discrimination a big challenge as individual circuit can not be separately isolated. The incomer from Agbada AGG must be isolated from the MCC in order to isolate the 2 facilities because both the incomer and the outgoing power supply cables are connected in a junction box on the open field within the plant. This unapproved isolation procedure invariably leads to power outage in FOC as the supply to FOC is from the Agbada/2 flowstation LV switchboard. It poses a great hazard to personnel working on any of the circuit.
Project Scope/Actions (With start and end dates and action party) :
Raise & get approval EMoC for the permanent change
Procurement of Isolators and Cables for execution
Raise valid PTW for execution.
Cable laying and termination.
Installation of isolators
Testing and commissioning
Updating of Ex register to include the new isolators and including them in Ex inspections on SAP.
Updating of Asset register & Standard Operating Procedures.
  Project Sponsor: Wilcox Emmanuel/Alepaye Babatunde
  Implementation Lead: Isodje Oluseyi
  Project Team: Hart Alaidanengia; Aigiomawu Obehi; Sunny Nwoke, Eyo Etim, Chiuzor Onumadu
  Enwefah Lucky
  Asooto Afolabi
Input High-level Timeline:
L0-L1: Raise & get approval for EMoC (September 2017)
L2: Procurement of isolators and cables (15th October 2017)
L3: Civil works & Cable laying (31st October 2017)
L4:: Installation of isolators for the separation (2nd November)
L5:: Update of Ex-register & Single line drawings (December 2017)
Update of Asset register & Standard Operating Procedures (January 2018)
Critical Success Factors
Budget Constraint
Leadership support
Timely delivery of procured items
Potential Benefits & Measurement:
Assures personnel safety during isolation.
Better quantification of the power consumption by each facility.
Use of appropriate certified means of isolation.
Provision of separate isolation points for each individual circuit.
Conformance to the DEP 63.20.08.10 and ESOP installation standard.
Charter Template

## Slide 2: Improvement of Power Supply Hardware Between Agbada FOC & JTF Camp
BILL OF MATERIALS |  |  |  |  |  | 
 | MATERIALS | QUANTITY | UNITS | PRICES (NGN) |  | 
1 | ISOLATORS (150AMPS) | 1 | pc | 272000 | 1475.16USD | NGN531057.6
2 | ISOLATORS (125AMPS) | 1 | pc | 259057 |  | 
3 | ARMOURED CABLES (95mm) | 10 | Metre | 50000 |  | 
4 | CABLE LUGS | 30 | pcs | 3000 |  | 
5 | CABLE GLANDS | 6 | pcs | 10000 |  | 
6 | CABLE SHROUDS | 6 | pcs | 5000 |  | 
7 | CIVIL WORK/ISOLATOR COVER |  |  | 50000 |  | 
8 | CABLE LABELLING | 10 | pcs | 20000 |  | 
 | TOTAL ESTIMATE |  |  | 669057 |  | 

## Slide 3: Bi-Weekly Cadence Commitment Template Past 7 days
No. | Action | Action Party | Threat | Due Date | Status
10-4.1 | Include diverse team including Operations personnel in order to incorporate functional inputs | Isodje Oluseyi |  | 30.09.2017 | Closed
10-4.2 | Involve Technical Assurance personnel (e.g. from Maintenance Discipline Team) in the team | Isodje Oluseyi |  | 30.09.2017 | Closed
10-4.3 | Prepare Bill of Materials & Services required for execution of the Project | Isodje Oluseyi |  | 15.11.2017 | Open
10-4.4 | Coding of required Materials in SAP PM | Isodje Oluseyi |  | 15.11.2017 | Open
10-4.5 | Include Cost Breakdown of the Project in Project Pack | Isodje Oluseyi |  | 15.11.2017 | Open
10-4.6 |  |  |  |  | 
10-4.7 |  |  |  |  | 
10-4.8 |  |  |  |  | 
10-4.9 |  |  |  |  | 
10-4.12 |  |  |  |  | 
10-4.13 |  |  |  |  | 
10-4.14 |  |  |  |  | 
10-4.15 |  |  |  |  | 
10-4.16 |  |  |  |  | 
On track
At risk
Delayed
Completed
New

## Slide 4: Bi-Weekly Cadence Commitment Template Next 14days
No. | Action | Action Party | Threat | Due Date | Status
10-4.1 | Include Cost of the Project in Project Pack | Isodje Oluseyi |  | 30.09.2017 | Open
10-4.2 |  |  |  |  | 
10-4.3 |  |  |  |  | 
10-4.4 |  |  |  |  | 
10-4.5 |  |  |  |  | 
10-4.6 |  |  |  |  | 
10-4.7 |  |  |  |  | 
10-4.8 |  |  |  |  | 
10-4.9 |  |  |  |  | 
10-4.10 |  |  |  |  | 
10-4.11 |  |  |  |  | 
10-4.12 |  |  |  |  | 
10-4.13 |  |  |  |  | 
10-4.14 |  |  |  |  | 
10-4.15 |  |  |  |  | 
10-4.16 |  |  |  |  | 
On track
At risk
Delayed
Completed
New

## Slide 5: Overall Project Plan
 | 2013 { $2.881(Budget) / $2.815(Actuals and Total Expected Charges for the remainder of the year) } |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  | 
Work Streams | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  | J | F | M | A | M | J | J | A | S | O | N | D | Jan – Dec |  |  | 
Actual / LE | - |  | - |  | $53.6K |  | $229.9K |  | $171.8K |  | $245.5K |  | $481.3K |  | $708.2K |  | $488.8K |  | $436.1K |  | $40M |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Programme Management
Change Management
Information Architecture
&
Value
Migration
Key Milestone
Key Dependency
On Track
At Risk
Delayed
Completed