## Slide 1: SOKU AG3 RESTORATION
  Business Unit: Production
  Project Sponsor: Ireti Omotoso
  Champion: Chris Nnogo
  Project Manager: Victor Nketah
  Facilitator/Coach:
PROJECT OWNERSHIP
Increase production and minimize GHG emission by restoring Soku AG3 compressor back into production
OPPORTUNITY STATEMENT
SCOPE
BUSINESS CASE
  Team Members:
  Onephrojire Ojiyovwi,
  Okoro Bernard
  Adesina Lukmon
  Nwosu Peterclaver,
  Njoku Hyginus
  Festus Azibator
GOAL
POTENTIAL ROADBLOCKS/ ISSUES
Gross Hard Benefits:
BENEFITS
PROJECT STATUS
G
Y
R
On Track
Delayed
Stopped
NAPIMS approval of budget
Late arrival of ordered spares
100%
75%
01/06/18
15/02/18
01/06/18
05/02/18
85%
01/03/18
01/02/18
Health
% Compl
Completion Date
Start Date
Overall % Compl
100%
IDENTIFY
ENGAGE STK
STK APPROVAL
0%
31/12/18
01/06/18
IMPLEMENT
Increased production by circa F$20,000k/year
GHG emissions reduction
Soft Benefits:
Improved reputation with NAPIMS and third party injectors
Soku GP has three trains of AG compressors. Two trains (LP NAG and AG2) are available while AG3 requires a major revamp to return it to operation. The revamp of AG3 will recover additional 65MMScf/d of the available extra NAG volumes constrained by compression capacity. Also, a revamped AG3 will provide operational flexibility during increased AG supply from third party AG suppliers in Nembe, Santa Barbara and Ekulama as well as contribute to flare reduction in Soku GP as the increased flash gas from the condensate stabilization trains because of the introduction of K2S can now be fully utilized.
Increase production by 65MMscf/d.
Minimize GHG emission
Increased production by circa F$20,000k/year
GHG emissions reduction
Soft Benefits:
Improved reputation with NAPIMS and third party injectors