## Slide 1
Opportunity Framing Workshop incl. OAP, PCAP creation
(Adopt from Scaled OAP, PCAP for Infills)
Approved Project Mandate
Approved OAP, PCAP
Volume Assurance (from NNS, ERCR, history matching)
Stakeholder Management Plan
HSSE & SP Plan
Risk Register & Risk Management Plan
PPD
L0 Schedule & T0 Estimate
DG1
IDENTIFY
Competitive Concept Identification
Select Subsurface Design Archetype (incl. model framing event)
Assured Well Design Parameters
Assured Facilities Design Parameters (SSDS)
Static Peer Assist (TPA1 + TPA2)
Select Well Design Archetype
Select Facilities Design Archetype
Dynamic Peer Assist (TPA3)
Competitive Concept Selection
(incl. Carbon Competitiveness)
ASSESS / SELECT
Well Location & Trajectory Review
HSSE & SP Plan Update incl. NTR-Q
Subsurface DEP requirements
Wells CDE
dWFS
T2 Estimate, L2 Schedule, CSRA, Benchmarking, Economics
Coarse HAZID / HAZOP
BfD
(in Polarion)
CP Strategy Endorsement
EIA LOI, Screening Workshop
Issue PO for EIA
EIA ToR approval
Operations Readiness Review
PO for Survey RoW, Well Locations
FDP
(incl. feasible options)
PP
PES
ITR3 / SAR3
(Do we have feasible, competitive & economically viable concept at hand)
Competitiveness Review
DG3
DEFINE
Approved PCP Lite
Pre-FID release for LLI
Bid Evaluations for LLI
(Maximize EFA)
PO for LLI
Retrieve Analog FEED Design
30% Model Review
Preliminary ICCS
Approved Vendor Documents
60% Model Review
Construction HAZID / SIMOPS
90% Model Review
Key Drawing Approvals by TAs (KDA)
Approved AFC Design Packages
Approved Final ICCS
PP/FG Update
SS/WE Alignment
Retrieve Analog Well Design
Well Detailed Design
Well Technical Specification
Well Technical Review
Approved Well Proposal
EIA ToR Approval
EIA 1st season sampling & Report
EIA 2nd season sampling & Report
Final EIA Report & Endorsement
CP Tactics & Plan Endorsement
Prepare & Issue SOW Packages for Call Off Contracts
Call Off Contractor Selection
Contract Award Endorsement
AFC Report
PEP
T3 Estimate, L3 Schedule, CSRA, Benchmarking
PAR4/SAR4
(Is everything in place to ensure successful execution)
FID
Competitive Execution Framework
Permit Approvals
Risk Register Update
HSSE & SP Plan Update
WRFM & Technology Plan
Final Resource Volume & Production Profile
Survey Report RoW, Well Locations
ESFS Sign Off
SSFS
ESFS Sign Off
Prepare GIP
Prepare PCP Lite
Assured Economics Assessment
Preliminary Subsurface data gathering & analysis
CSR
(pdf of slide pack)
Approved FDP from Regulators
INTEGRATED & FOCUSED RISK AND STAKEHOLDER MANAGEMENT ACROSS ORS PHASES
Pause/Stop Checkping

## Slide 2
GIP Endorsement & Funds Release
Non LLI Procurement
Free Issue of LLI and Non LLI to Construction Contractor
Statement of Fitness
(Are we ready for a Flawless Start Up)
1st HC
Facilities Construction Contract Award
Final Alignment Engineering by Contractor
Bulk Procurement
Dredging Contract Award
Construction Readiness Review
Dredging & Site Preparation
Fabrication
Transportation to Site
Pre-Drill & Advance Tie Ins Installation
Rig Mobilization
Post Drill Installation
Hook Up & CSU
End of Well Report
Post Investment Review (PIR)
(Are we delivering on our promise)
Drilling & Completion
OPERATE
As Build Handover to Asset
EXECUTE
INTEGRATED & FOCUSED RISK AND STAKEHOLDER MANAGEMENT ACROSS ORS PHASES