## CUSTOMER SERVICE IMPROVEMENT
[7 empty] | 2017-03-01 |  |  |  | 2017-04-01 |  |  |  | 2017-05-01 |  |  |  |  | 2017-06-01 |  |  |  | 2017-07-01 |  |  |  | 2017-08-01 |  |  |  |  | 2017-09-01 |  |  |  | 2017-10-01 |  |  |  |  | 2017-11-01 |  |  |  | 2017-12-01
[7 empty] | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4
S/N | Activity | Duration | Start Date | End Date | Owner | % Completion | time axis 2017-03-06 to 2017-12-25
A.1 | DEVELOP PROJECT CHARTER AND PLAN
A.1.1 | - Prepare Project Charter and Plan | 5 | 2016-05-12 | 2016-12-12 | Tokoni | 100% | bar: 2017-03-20
A.1.2 | - Review Project Charter with Head Land Transport and Sign-off | bar: 2017-03-20
A.1.3 | - Review with cadence team | bar: 2017-03-20
A.1.4 | - Kick-off meeting with Land Transport Stakeholders | 5 | 2016-05-12 | 2016-12-12 | Hafizu | 100%
A.2 | GATHER DATA (DETERMINE THE CURRENT BASELINE)
A.2.1 | - Review 2016 Land Transport Customer Satisfaction Survey | bar: 2017-03-27
A.2.2 | - Interview key customers /stakeholders | 30 | 2016-12-12 | 2017-06-02 | Adedayo | 30% | bar: 2017-03-27 to 2017-04-17
A.2.3 | - Interview journey managers/supervisors | bar: 2017-03-27 to 2017-04-17
A.2.4 | - Review current Land Transport Request Management Process | 30 | 2016-12-12 | 2017-06-02 | Tokoni | 30% | bar: 2017-04-03 to 2017-04-17
A.2.5 | - Work closely with Journey Managers | bar: 2017-03-06 to 2017-06-05
A.2.6 | -Review current premob request management process | bar: 2017-04-17 to 2017-05-01
A.2.7 | - Review Driver DEP process | bar: 2017-04-17 to 2017-05-01
A.2.8 | -Failure Mode Annalysis for dedicated equipments | bar: 2017-04-17 to 2017-05-01
A.2.9 | - Review IVMS.Astrata Reporting Process | bar: 2017-04-17 to 2017-05-01
A.2.6 | - Engage logistics hub co-ordinators to ascertain customer perspective on dedicated equipment | bar: 2017-04-17 to 2017-05-01
A.3 | CONDUCT VALUE STREAM MAPPING
A.3.1 | -Conduct Value Stream Mapping Session for Land Transport RequestProcess | 15 | 2016-12-12 | 16/1/2017 | Tokoni | 70% | bar: 2017-05-08 to 2017-05-22
A.3.2 | -Conduct a workshop to enable the 'to be' discussion for creativity & innovation | bar: 2017-05-22
A.3.3 | - Conduct a workshop on Developing a Commercial Mindset for Supervisors and Journey Managers | bar: 2017-06-12 to 2017-06-19
A.4 | IMPLEMENTATION AND SOLUTION PROPOSAL
A.4.1 | - Customer Service Training for all journey maanagers | bar: 2017-07-10 to 2017-08-14
A.4.2 | - Development of cleaning schedule for all locations | bar: 2017-07-31 to 2017-08-14
A.4.3 | - Hearts and Mind session with drivers and Journey Managers | bar: 2017-08-21 to 2017-10-16
A.5 | - IMPLEMENTATION/SOLUTION TESTING
A.5.1 | -Development of feedback forms for passengers | bar: 2017-09-04 to 2017-09-18
A.5.2 | - Development of Key KPI's to measure success | bar: 2017-09-04 to 2017-10-16
Planned
Completed
On track
Overdue

## TASK
ACTIVITY | ACTION PARTY | INTERVIEWEE | DEADLINE
- Review 2016 Land Transport Customer Satisfaction Survey | ALL | N/A
- Interview key customers /stakeholders | OLAMIDE/HAFIZU
- Interview journey managers/supervisors | OLAMIDE/OLA | Taxi JM,Production/JM/ Team leads
- Review current Land Transport Request Management Process | ALL | N/A
- Work closely with Journey Managers | OLAMIDE | N/A
-Review current premob request management process | HAFIZU/Dr Ray | Richard Akinbile
- Review Driver DEP process | Hafizu/Dr Ray | Simi
-Failure Mode Annalysis for dedicated equipments | HAFIZU/Dr Ray
- Review IVMS.Astrata Reporting Process | Hafizu/Dr Ray | Lukam Omotoso/Ben- Chuks
- Engage logistics hub co-ordinators to ascertain customer perspective on dedicated equipment | Olamide | Eroms,Aminu, Saiki Timothy