## Asset Disposal Tracker
ASSET DISPOSAL TRACKER (SPDC & SNEPCO)
S/N | BRIEF DESCRIPTION |  | LOCATION(S) | SPACE (Sqm) | Support Receeved |  |  | ACTIONS COMPLETED |  |  |  | Outstanding Actions | REMARKS/ACTIONS | ACTION PARTY | ACTION DATE
|  | VENDOR(S) |  |  | BUSINESS SUPPORT | SNEPCO / SPDC APPROVAL | NAPIMS APPROVAL | ITT | AWARD | PAYMENT | EVACUATION
SNEPCo Materials
1 | Disposal of Bonga materials batch 5, Beams etc at Onne | SNEPCo/Community |  | 162.75 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Closed |  | Lazarus | 2019-03-28
2 | Disposal of Bonga materials, Alternator, Beams etc at Onne | NAPIMS/SNEPCo |  | same as item 1 | Yes | Yes | Yes | Yes | No | No | No | OLB outcome is out. To be reviewed for approval |  | Stewart | 2019-03-01
3 | Disposal of Surplus Offshore Production/Maintenenace Inventory at NG28 SNEPCo warhouse Onne Batch 1&2 | NAPIMS |  |  | Yes | Yes | Yes | No | No | No | No | Surplus. Tender via NIPEX tendering |  | Tunji | 2019-03-01
4 | Disposal of Surplus Offshore Production/Maintenenace Inventory at NG28 SNEPCo warhouse Onne Batch 1&2 | SNEPCO |  |  | Yes | Yes | Yes | No | No | No | No | Surplus. Tender via NIPEX tendering |  | Tunji | 2019-03-01
5 | Disposal of EPRS Line pipes at SNEPCo yard Onne | NAPIMS |  | 1828 | Yes | Yes | Yes | Yes | No | No | No | OLB outcome is out. Tender outcome is low. Need to engage NAPIMS |  | Tunji | 2019-03-01
6 | Disposal of EPRS Line pipes at SNEPCo yard Onne | SNEPCo/Community |  | as above | Yes | Yes | Yes | Yes | Yes | No | No | Make payment |  | Vendor | 2019-05-04
7 | Disposal of Bonga backload Batch 6 | Community |  | same as item 1 | Yes | Yes | NA | Yes | Yes | Yes | No | Closed |  | Lazarus | 28/3/2019
8 | Disposal of Subsea Platform at Onne | NAPIMS/SNEPCO/Community |  | 81.01 | Yes | No | No | No | No | No | No | Letter transmitted to NAPIMS and CoVs for approval |  | Lazarus | 2019-03-12
9 | Write-off and disposal of obsolete and damaged SNEPCo Wells materials NG28 | TBA |  |  | Yes | No | No. | No | No | No | No | MCB approval |  | MCB | 13/03/2019
10 | Wells OCTG Batch 1 2019 | TBA |  |  | No |  |  | No | No | No | No | Obtain wells team support |  | Obinna | 28/02/2019
10 | Disposal of Sea Eagle disused Lifeboats | SNEPCO |  | 286 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Closed |  | Lazarus | 28/02/2019
11 | Disposal of decommisioned Nodebus spares. | SNEPCO |  |  | Yes | Yes | No |  |  |  |  | Letter transmitted to NAPIMS and CoVs for approval |  | Lazarus | 27/2/2019
12 | Sales of 2 pieces, 5-1/2''20ppf 13CR-80 VAM TOP HC BOX x PIN Swell Packers to Total E & P Nigeria Limited. | Total E & P |  |  | Yes | No | No |  |  |  |  | Letter transmitted to NAPIMS and CoVs for approval- NAPIMS support expected |  | Lazarus | 18/3/2019
13 | Write-off and disposal of Leaked Degreaser and Foam Compound at NG28 Onne |  |  |  | Yes | Yes | NA | NA | NA | NA | Yes | Closed |  | Lazarus | 28/03/2019
14 | Write-off and disposal of Leaked Degreaser at NG16 Onne |  |  |  | Yes |  | NA | NA | NA | NA | NO | DocuSign in Progress |  |  | 2019-04-04
15
16
17
18
19
20
SPDC Materials
1 | Disposal of Tubings Recovered from ADIBAWA Wells Decom Campaign | Community |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Closed |  | Lazarus | 2019-08-03
2 | Disposal of Tubings Recovered from ADIBAWA Wells Decom Campaign | NAPIMS/SPDC |  |  | Yes | Yes | Yes | No |  |  |  | Awaiting Tendering |  | Lazarus | 15/03/2019
3 | Disposal of Tubings Recovered from ADIBAWA Wells Decom Campaign Community Lot |  |  |  | Yes | Yes | Yes | No |  |  |  | Awaiting Tendering
4 | Disposal of scrap metals generated fro genrating and instrument workshop overhaul activities in PHC-IA and Movable yard. | Community |  |  | Yes | Yes | N/A | Yes | Yes | Yes | Yes | Closed |  | Lazarus | 13/03/2019
5 | Disposal of 2 dilapidated containers at IA Power Plant | Community |  |  | Yes | Yes | NA | No |  |  |  | Awaiting Tendering |  | Lazarus | 15/03/2019
6 | Disposal of scrap materials at Soku Gas Plant SPDC Lot | NAPIMS | Soku Gas Plant |  | Yes | Yes | Yes | Yes | Yes | Yes | No | Awaiting evacuation |  | Vendor | 2019-12-04
7 | Disposal of scrap materials at Soku Gas Plant NAPIMS Lot | SPDC | Soku Gas Plant |  | Yes | Yes | Yes | Yes |  |  |  | ITT sent to vendors extended |  | Onomade | 2019-04-04
8 | Disposal of scrap materials at Soku Gas Plant Community Lot | Community | Soku Gas Plant |  | Yes | Yes | Yes | Yes | Yes |  |  | Make Payment |  | Vendor | 2019-01-04
9 | Disposal of scrap materials at Afam VI Power Plant | Community |  |  | Yes | NA | Yes | No |  |  |  | Awaiting Tendering |  | Lazarus | 15/03/2019
10 | Disposal of obsolete Electrical materials at NG11 PHC-IA Warehouse | NAPIMS |  |  | Yes | Yes | Yes | No |  |  |  | Awaiting Tendering |  | Lazarus | 15/03/2019
11 | Disposal of obsolete Electrical materials at NG11 PHC-IA Warehouse | SPDC |  |  | Yes | Yes | Yes | No |  |  |  | Awaiting Tendering |  | Lazarus | 15/03/2019
12 | Disposal of obsolete Electrical materials at NG11 PHC-IA Warehouse | Community |  |  | Yes | Yes | Yes | No |  |  |  | Awaiting Tendering |  | Lazarus | 15/03/2019
13 | Disposal of 5s Project obsolete materials at NG11 PHC-IA warehouse | NAPIMS | PHIA Warehouse |  | Yes | Yes | Yes | Yes |  |  |  | ITT sent to vendors |  | Onomade | 2019-05-04
14 | Disposal of 5s Project obsolete materials at NG11 PHC-IA warehouse | SPDC | PHIA Warehouse |  | Yes | Yes | Yes | Yes |  |  |  | ITT sent to vendors |  | Onomade | 2019-05-04
15 | Disposal of 5s Project obsolete materials at NG11 PHC-IA warehouse | Community | PHIA Warehouse |  | Yes | Yes | Yes | Yes |  |  |  | ITT sent to vendors |  | Onomade | 2019-05-04
16 | Write-off and disposal of disused items at Abuja Office | SPDC |  |  | Yes | Yes | N/A | No |  |  |  | Awaiting Tendering |  | Onomade | 15/03/2019
17 | Disposal of SPDC Surplus Matls - Batches 8, 9 & 10 | SPDC | PHIA< KI WR |  | Yes | Yes | No | No
18 | Write-off and Disposal of Fire-Retardant Chemicals in Warri Warehouse (NG12 SLoc. 1202) | Waste Mgt | Warri |  | Yes | [6 empty] | DocuSign in progress |  | Lazarus | 2019-04-04
19
20
21
22
23
24

## 2019 SPDC Disposal Records
DATABASE OF ALL DISPOSALS COMPLETED IN 2018 ($1=N305)
S/N | MATERIALS DESCRIPTION | VENDOR NAME | Acquisition Cost | ESTIMATED MARKET VALUE | NAPIMS APPROVAL THRESHOLD? | REVENUE REALISED NGN | REVENUE REALISED USD | REVENUE REALISED F$ | REQUEST DATE | DATE OF APPROVAL | RECEIPT DATE | DISPOSAL STRATEGY | SPDC RECEIPT NUMBER | LOCATION | DISPOSAL LOCATION | ALLOCTAED TO | QUARTER
1 | Disposal of Obsolate Bonny Warehouse Materials at Bonny | YUSSER Nigeria Limited | 3856425.59 | 192821.28 | Yes | 155000 |  | 508.1967 | July-21-2016 | Sept-14-2016 | Jan-8-2019 | Tender | 1517 | East | Bonny | NAPIMS | Q1
2 | NG01024026- Disposal of 2 Lots of 1 pc in each Lot MCB3A Safety Life Boats and Shipping Skid at Onne. | Strano Line Limited | 200000 | 10000 | Yes | 2500000 |  | 8196.7213 | July-16-2018 | July-25-2018 | Jan-30-2019 | Tender | 1523 | East | Onne | NAPIMS | Q1
3 | Disposal of scrap metals generated from generating and Instrument workshop at PHC-IA | J. C. Fabrication Company | 5437.5 | 271.88 | NO | 215000 |  | 704.918 | Nov-16-2018 | Nov-21-2018 | Feb-21-2019 | Tender | 1530 | East | Onne | COMMUNITY | Q
4 | Disposal of Scrap Tubing Recovered from ADIBAWA Wells Decom. Campaign | Zuan Services | 309160.6 | 6183.21 | Yes | 25000 |  | 81.9672 | Oct-16-2018 | Oct-24-2018 | Feb-13-2019 | Tender | 1528 | East | Adibawa | COMMUNITY | Q1
4 | Disposal scrap materials at Soku Gas Plant | Furda Ventures Limited | 15154.32 | 15154.32 | Yes | 800000 |  | 2622.9508 | Oct-20-2018 | Oct-19-2018 |  | Tender |  | East | Soku | SPDC | Q1
| Doc- 218939879- Disposal of scrap materials at Soku Gas Plant | Pre-Filda Nigeria Limited |  |  | Yes | 200000 |  | 655.7377 | Oct-20-2018 | Oct-19-2018 | Apr-3-2019 | Tender | 1538 | East | Soku | COMMUNITY | Q2
[6 empty] | 3895000 |  | 12770.4918

## 2019 SNEPCo Disposal Records
DATABASE OF ALL DISPOSALS COMPLETED IN 2018 ($1=N305)
S/N | MATERIALS DESCRIPTION | VENDOR NAME | Acquisition Cost | ESTIMATED MARKET VALUE | NAPIMS APPROVAL THRESHOLD? | REVENUE REALISED NGN | REVENUE REALISED USD | REVENUE REALISED F$ | REQUEST DATE | DATE OF APPROVAL | RECEIPT DATE | DISPOSAL STRATEGY | SNEPCo RECEIPT NUMBER | LOCATION | DISPOSAL LOCATION | ALLOCTAED TO | QUARTER
1 | Doc 218734982- Disposal of scrap materials Backloaded from Bonga FPSO currently stored at Onne Warehouse Yard (Batch 6) | G.B. Nchima | 253.75 | 253.75 | No | 63000 |  | 206.5574 | Jan-25-2019 | Feb-19-2019 | Mar-28-2019 | Tender | 1758 | Onne | Onne | Community | Q1
2 | Doc 217814559- Disposal of Bonga Batch 5 Backload, H beams at Onne | A. C. Uche & Sons | 2745 | 137.27 | Yes | 60000 |  | 196.7213 | Aug-28-2019 | Nov-2-2018 | Mar-28-2019 | Tender | 1759 | Onne | Onne | Community | Q1
[6 empty] | 123000 |  | 403.2787

## Asset Sales
Completed Sales
S/N | Decription of Asset | Asset Owner (SPDC / SNEPCo) | Buyer | Location(s) | Space (sqm) | Status of Transaction |  |  | Amount Received (US$) | Remarks | Support Receeved
|  |  | Vendor(s) |  |  | S/Agreement Signed | Payment Made | Materials Evacuated |  |  | Business Support | SNEPCO / SPDC Approval | NAPIMS Approval
1 | Sales of Wells Materials to Eni | SPDC | Eni / NAOC | KI & PH-IA |  |  |  |  | 2000000
2 | Sale of BNW Forgings to BHGE in Aberdeen | SNEPCo | BHGE UK | Aberdeen |  | Yes | No | Yes | 15600
3 | Direct Sales, 2 pieces, 5-1/2’’ 20ppf 13CR-80 VAM TOP HC Box x Pin Swell Packers to Total E & P Nig Ltd | SNEPCo | Total E & P Nig Ltd | Port Harcourt IA |  | Yes | No | Yes | 52553.84
4 | Disposal of Sea Eagle disused Lifeboats | SPDC |  |  | 286
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
| Total | [7 empty] | 2068153.84
SNEPCo
SPDC

## Asset Awaiting NAPIMS Approval
Applications for Scrap Disposal Awaiting NAPIMS approval - JV Requests
2019-04-08
S/N | Description | Our Ref | Acknowledgement date | Overdue by | Remarks | Value
1 | Application for Disposal of Scrapped and Dis-used Oil Spill Equipment and Materials at Ogunu Warri, Forcados Terminal(FOT) and Kidney Island Port Harcourt | SPDC-SCM-2017-0080L | 2017-10-31 | 524 | Awaiting NAPIMS approval
2 | Application for the Disposal of scrap Generators at 12 Inner Crescent Ikoyi Lagos | SPDC-SCM-2018-0021L | 2018-01-24 | 439 | Awaiting NAPIMS approval
3 | Application for Disposal of 1 Set VFLL-1 CAMERON SMART WELLHEAD By Direct Sales to CAMERON | SPDC-SCM-2018-0025L | 2018-01-26 | 437 | Awaiting NAPIMS approval
4 | Application for disposal of Tubings Recovered from Imo River well 16 and NKALI Well 08 Decom Campaign | SPDC-SCM-2018-0058L | 2018-03-05 | 399 | Awaiting NAPIMS approval
5 | Application for the Disposal of Well Engineering Pipes Direct to Rumuwoji Community | SPDC-SCM-2018-0135L | 2018-05-23 | 320 | Awaiting NAPIMS approval
6 | Application for the Disposal of Scrap Materials at RUMUAHIA Production Unit and Oguta FC | SPDC-SCM-2018-0227L | 2018-10-18 | 172 | Awaiting NAPIMS approval
7 | Application for the Disposal of Scrap Materials at Soku Gas Plant. | SPDC-SCM-2018-0229L | 2018-10-22 | 168 | APPROVED
8 | Write-off and disposal of Tubing recovered from ADIBAWA 003,006, 013 Well decommissioning. | SPDC-SCM-2018-0231L | 2018-10-26 | 164 | APPROVED
9 | Application for Disposal of 5s Project Obsolete Materials at NG11 PHC-IA Warehouse. | SPDC-SCM-2018-0272L | 2018-11-28 | 131 | APPROVED
10 | Application for Disposal of Obsolete Electrical and Shackle Materials at NG11 PHC-IA Warehouse | SPDC-SCM-2018-0291L | 2018-12-17 | 112 | APPROVED
11 | Application for Disposal of Tubulars and Well Head materials by Direct Sale to Nigeria Agip Oil Company (NAOC) Limited | SPDC-SCM-2019-0049L | 2019-03-05 | 34 | Awaiting NAPIMS approval