## Overall status Table
Toggle company:
Company | (All) | SCiN Disposal Status | Company | (All) | SCiN Disposal Status ($)
Row Labels | Count of S/N |  | Row Labels | Sum of Anticipated Sales Value
Awaiting sign off | 4 |  | Awaiting sign off | 5
Awaiting NAPIMS | 10 |  | Awaiting NAPIMS | 21
Tendering | 3 |  | Tendering | 13
Community issue | 2 |  | Community issue | 5
Payment outstanding | 1 |  | Payment outstanding | 7
Closed | 42 |  | Closed | 165
(blank) |  |  | (blank)
Evacuate | 1 |  | Evacuate
Re-tender | 1 |  | Re-tender | 2
Lotting | 2 |  | Lotting | 3
Grand Total | 66 |  | Grand Total | 221
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Asset Disposal Tracker 2019
ASSET DISPOSAL TRACKER (SPDC & SNEPCO)
[5 empty] | Support Recieved |  |  | ACTIONS COMPLETED
Company | S/N | BRIEF DESCRIPTION | LOCATION(S) | SPACE (Sqm) | BUSINESS SUPPORT | SNEPCO / SPDC APPROVAL | NAPIMS APPROVAL | ITT | AWARD | PAYMENT | EVACUATION | Anticipated Sales Value | VENDOR(S) | Outstanding Actions | Action | REMARKS / ACTIONS | ACTION PARTY | ACTION DUE DATE | Days
SNEPCO | 1 | Disposal of Bonga materials batch 5, Beams etc at Onne | Onne | 162.75 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 1 | SNEPCo/Community | Closed | Closed |  | Lazarus | 2019-03-28
SNEPCO | 2 | Disposal of Bonga materials, Alternator, Beams etc at Onne | Onne | same as item 1 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | NAPIMS/SNEPCo | Closed | Closed |  | Lazarus | 2019-05-10
SNEPCO | 3 | Disposal of Surplus Offshore Production/Maintenenace Inventory at NG28 SNEPCo warhouse Onne Batch 1&2 | Onne | 35 | Yes | Yes | Yes | Yes | No | No | No | 3 | NAPIMS | Closed | Closed |  | Lazarus | 15/10/2019
SNEPCO | 4 | Disposal of Surplus Offshore Production/Maintenenace Inventory at NG28 SNEPCo warhouse Onne Batch 3&4 | Onne | Covered area | Yes | Yes | Yes | YES | Yes | Yes | Yes | 4 | SNEPCO/NAPIMS | Closed | Tendering |  | Lazarus | 20/8/2019
SNEPCO | 5 | Disposal of EPRS Line pipes at SNEPCo yard Onne | Onne | 1828 | Yes | Yes | Yes | Yes | No | No | No | 5 | NAPIMS | Award to the bid winner | Awaiting NAPIMS |  | Tunji | 29/11/2019
SNEPCO | 6 | Disposal of EPRS Line pipes at SNEPCo yard Onne | Onne | as above | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 4 | SNEPCo/Community | Closed | Closed |  | Vendor | 43589
SNEPCO | 7 | Disposal of Bonga backload Batch 6 | Onne | same as item 1 | Yes | Yes | NA | Yes | Yes | Yes | Yes | 3 | Community | Closed | Closed |  | Lazarus | 28/3/2019
SNEPCO | 8 | Disposal of Subsea Platform at Onne | Onne | 81.01 | Yes | Yes | No | No | No | No | No | 2 | Re-tender NAPIMS Lot | Awarded | Re-tender |  | Lazarus | 2019-11-10
SNEPCO | 9 | Write-off and Disposal of Obsolete, Damaged and Surplus Wells Materials at NG28 SNEPCo Yard Onne Batch 2. | Onne | 1500 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 1 | TBA | Closed | Closed |  | Lazarus | 14/10/2019
SNEPCO | 10 | Write-off and Disposal of obsolete and damaged SNEPCO Wells materials (NG28) Batch 1 | Onne | 80 | Yes | Yes | No | No | No | No | No | 2 | Approved | Closed | Closed |  | Lazarus | 2019-08-04
SNEPCO | 11 | Disposal of decommisioned Nodebus spares. | Onne | 5 | Yes | Yes | No | No | No | No | No | 3 | SNEPCO | Closed | Closed |  | Lazarus | 27/2/2019
SNEPCO | 12 | Sales of 2 pieces, 5-1/2''20ppf 13CR-80 VAM TOP HC BOX x PIN Swell Packers to Total E & P Nigeria Limited. | Onne | 2.5 | Yes | Yes | Yes | NA | Yes | Outstanding Invoice | Yes | 4 | Total E & P | Closed | Closed |  | Lazarus | 18/3/2019
SNEPCO | 13 | Write-off and disposal of Leaked Degreaser and Foam Compound at NG28 Onne | Onne | 7.5 | Yes | Yes | NA | NA | NA | NA | Yes | 5 |  | Closed | Closed |  | Lazarus | 28/03/2019
SNEPCO | 14 | Write-off and disposal of Leaked Degreaser at NG16 Onne | onne | 5 | Yes | Yes | NA | NA | NA | NA | Yes | 6 |  | Closed | Closed |  | Lazarus | 23/4/2019
SNEPCO | 15 | Write-off and Disposal of expired and damaged materials at NG28 2801 | Onne | 5.5 | Yes | Yes | NA | NA | NA | NA | Yes | 7 | NA | Awaiting NAPIMS approval | Awaiting NAPIMS |  | BGR/Tunji | 29/11/2019
SNEPCO | 16 | Write-off and Disposal of Bonga Batch 2 expired and damaged materials at NG27-2701. | ONNE | 5 | Yes | Yes | Yes | NA | NA | NA | Yes | 6 | NA | Closed | Closed |  | BGR/Tunji | 30/8/2019
SNEPCO | 17 | Write-off and Disposal of Motorized Reel and Ancillaries at Onne SNEPCO warehouse Open yard Area Batch 1 | Onne | 208 | Yes | No | No | No | No | No | No |  | NA | Approved by NAPPIMS | Tendering |  | Austin | 29/11/2019
SNEPCO | 18 | Application for the Disposal of Surplus Bonga Inventory Batches 1, 2, and 3 and Offshore Project materials at SNEPCo NG28 and NG26 Onne warehouses. | Onne | 150 | Yes | Yes | Yes | No | No | NO | No |  |  | Awaiting Tendering | Lotting |  | Lazarus | 29/11/2019
SNEPCO | 19 | Write-off and disposal of Sub-Sea and Bonga Bulky Materials at Onne SNEPCo Warehouse Open Yard Area | Onne | 350 | Yes | Yes | No | No | No | NO | NO |  |  | Awaiting NAPIMS approval | Awaiting NAPIMS |  | BGR/Tunji | 29/11/2019
SNEPCO | 20 | Write-off and disposal of Bonga Bulky Materials at Onne SNEPCo Warehouse Open Yard Area | Onne | 390 | Yes | Yes | Yes | YES | No | No | Yes |  |  | Closed | Closed |  | Lazarus | 2019-09-10
SNEPCO | 21 | Write-off and disposal of SNEPCo light vehicles | Lagos |  | Yes | Yes | No | NA | NA | No | No |  |  | Review in progress | Awaiting sign off |  | SNEPCo | 30/10/2019
SNEPCO | 22 | Write-off and Disposal of Rapid Rock (RL) Riser Joints and Associated Equipment in Onne Yard | Onne | 323 | Yes | No | No | No | No | No | No |  | NAPIMS | Awaiting NAPIMS approval | Awaiting NAPIMS |  | bgr/tUNJI | 15/12/2019
SPDC | 1 | Disposal of Sea Eagle disused Lifeboats | Onne | 286 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 5 | NAPIMS | Closed | Closed |  | Lazarus | 28/02/2019
SPDC | 2 | Sale of Tubulars and Well head materials to Nigeria Agip Oil Company (NAOC) Limited | PHC-IA |  | Yes | Yes | NO | YES | YES | NO | YES | 7 | NAOC | Closed | Payment outstanding |  | Tunji | 31/5/2019
SPDC | 3 | Disposal of Tubings Recovered from ADIBAWA Wells Decom Campaign Community Lot | ADIBAWA |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 8 | Community | Closed | Closed |  | Lazarus | 2019-08-03
SPDC | 4 | Disposal of Scrap Materials at RUMUAHIA Production Unit and Oguta FC | rumuahia |  | Yes | Yes | Yes | No | No | No | NO | 2 | Community | Closed | Closed |  | Lazarus | 30/8/2019
SPDC | 5 | Disposal of Tubings Recovered from ADIBAWA Wells Decom Campaign NAPIMS | ADIBAWA |  | Yes | Yes | Yes | No | No | No | No | 9 | NAPIMS | Tendering in progress | Tendering |  | Austin | 2019-08-05
SPDC | 6 | Disposal of Tubings Recovered from ADIBAWA Wells Decom Campaign SPDC Lot | ADIBAWA |  | Yes | Yes | Yes | No | Yes | Yes | Yes | 10 | SPDC | Closed | Closed |  | Lazarus | 31/5/2019
SPDC | 7 | Disposal of scrap metals generated fro genrating and instrument workshop overhaul activities in PHC-IA and Movable yard. | PHC-IA |  | Yes | Yes | N/A | Yes | Yes | Yes | Yes | 6 | SPDC | Closed | Closed |  | Lazarus | 13/03/2019
SPDC | 8 | Disposal of 2 dilapidated containers at IA Power Plant | PHC-IA |  | Yes | Yes | NA | No | No | No | Yes | 5 | Community | Closed | Closed |  | Lazarus | 2019-10-07
SPDC | 9 | Disposal of scrap materials at Soku Gas Plant SPDC Lot | Soku Gas Plant |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 4 | SPDC | Closed | Closed |  | Vendor | 2019-12-04
SPDC | 10 | Disposal of scrap materials at Soku Gas Plant NAPIMS Lot | Soku Gas Plant |  | Yes | Yes | Yes | Yes | YES | Yes | Yes | 3 | NAPIMS | Closed | Closed |  | Lazarus | 2019-07-08
SPDC | 11 | Disposal of scrap materials at Soku Gas Plant Community Lot | Soku Gas Plant |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | Community | Closed | Closed |  | Vendor | 24/5/2019
SPDC | 12 | Disposal of scrap materials at Afam VI Power Plant | Afam |  | Yes | NA | Yes | No | No | No | No | 2 | Community | Awaiting Tendering/No community bidders list | Community issue |  | Lazarus | 15/03/2019
SPDC | 13 | Disposal of obsolete Electrical materials at NG11 PHC-IA Warehouse SPDC Lot | PHIA Warehouse |  | Yes | Yes | Yes | YES | Yes | Yes | Yes | 3 | SPDC | Closed | Closed |  | Lazarus | 2019-06-06
SPDC | 14 | Disposal of obsolete Electrical materials at NG11 PHC-IA Warehouse Coomuity Lot | PHIA Warehouse |  | Yes | Yes | Yes | YES | Yes | Yes | Yes | 4 | Community | Closed | Closed |  | Lazarus | 13/06/2019
SPDC | 15 | Disposal of obsolete Electrical materials at NG11 PHC-IA Warehouse NAPIMS Lot | PHIA Warehouse |  | Yes | Yes | Yes | YES | YES |  | Yes | 5 | NAPIMS | Closed | Closed |  | Vendor | 15/08/2019
SPDC | 16 | Disposal of 5s Project obsolete materials at NG11 PHC-IA warehouse SPDC Lot | PHIA Warehouse |  | Yes | Yes | Yes | Yes | YES | Yes | Yes | 6 | SPDC | Closed | Closed |  | Vendor | 2019-05-04
SPDC | 17 | Disposal of 5s Project obsolete materials at NG11 PHC-IA warehouse | PHIA Warehouse |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 7 | NAPIMS | Closed | Closed |  | Vendor | 2019-08-05
SPDC | 18 | Disposal of 5s Project obsolete materials at NG11 PHC-IA warehouse | PHIA Warehouse |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 8 | Community | Closed | Closed |  | Lazarus | 19/6/2019
SPDC | 19 | Write-off and disposal of disused items at Abuja Office | Abuja |  | Yes | Yes | N/A | Yes | Yes | Yes | Yes | 9 | SPDC | Closed | Closed |  | Vendor | 2019-01-06
SPDC | 20 | Disposal of SPDC Surplus Matls - Batches 8, 9 & 10 | PHIA< KI WR |  | Yes | Yes | Yes | No | No | NO | NO | 3 | SPDC | Awaiting Tendering | Lotting |  | Austin | 18/4/2019
SPDC | 21 | Write-off and Disposal of Fire-Retardant Chemicals in Warri Warehouse (NG12 SLoc. 1202) | Warri |  | Yes | Yes | NA | No | NA | NA | Yes | 2 | Waste Mgt | Closed | Closed |  | Waste mgt team | 24/4/2019
SPDC | 22 | Write-off and Disposal of Leaked Degreaser at NG16 stoc. 1601 Onne | Onne |  | Yes | Yes | NA | NA | NA | NA | Yes | 1 | NA | Closed | Closed |  | Waste mgt team | 29/4/2019
SPDC | 23 | Write-off and Disposal of leaked lubricants, expired and scrapped materials at PHC-IA Warehouse Yard | PHC-IA |  | Yes | Yes | NA | Yes | Yes | Yes | Yes | 2 | NA | closed | Closed |  | Lazarus | 2019-06-06
SPDC | 24 | Disposal of write-off materials from Okoloma Surplus Material Inventorization Project | Okoloma |  | Yes | Yes | No | No | NO | No | No | 3 | Community | Awaiting Tendering/No community bidders list | Community issue |  | Austin | 30/10/2019
SPDC | 25 | Write-off and disposal of decommissioned scrap metals at RA water facility (Sub 1, 2 and 3) | Shell RA |  | Yes | No | NA | Yes | Yes | Yes | Yes | 4 | Community | Closed | Closed |  | Vendor | 20/6/2019
SPDC | 26 | Disposal of Production Workshop West Scrap metals at Shell I.A Ogunu Warri | Warri |  | Yes | Yes | NA | YES | YES | Yes | YES | 5 | Community | Closed | Closed |  | Lazarus | 2019-07-06
SPDC | 27 | Write-off and Disposal of Expired Lubricants and Chemicals in Tunu Flow Station. | Tunu F/S |  | Yes | No | NO | NO | NO | NO | NO | 5 | NA | DocuSign is in progress | Awaiting sign off |  | Asset | 2019-03-05
SPDC | 28 | Write-off and disposal of ProBook 645 model Laptops | PHC/LAG |  | Yes | Yes | Yes | NO | NO | NO | NO | 4 | NA | Donation to schools | Closed |  | Tunji | 30/8/2019
SPDC | 29 | Write-off and Disposal of SPDC Operational Vehicles at Port Harcourt, Ogunu Warri, North Bank, Forcados Terminal and Abuja. | Ogunu |  | Yes | Yes | NO | NO | No | No | No | 2 | SPDC/NAPIMS | Closed | Closed |  | Lazarus | 17/6/2019
SPDC | 30 | Sales of 350 jts of 3.1/2'' 9.3# N80 HCS R2 Tubing to EROTON Exploration and Production Limited | Kidney Island |  | Yes | Yes | NO | NA | Yes | Yes | No | 3 | EROTON E & P | Closed | Closed |  | BGR | 13/6/2019
SPDC | 31 | Write-off and disposal of scrap materials at the decommissioned Imo River Gas old Compressor plant | Imo River |  | Yes | Yes | NO | No | No | No | No | 4 |  | Awaiting NAPIMS approval | Awaiting NAPIMS |  | BGR | 2019-09-08
SPDC | 32 | Write-off and disposal of scrap materials at Old Compressor building at Obigbo Node | Obigbo |  | Yes | Yes | NO | No | No | No | No | 5 |  | Awaiting NAPIMS approval | Awaiting NAPIMS |  | BGR | 2019-09-08
SPDC | 33 | Write-off and disposal of Intermediate Bulk Container (IBC) at Kidney Island | Kidney Island |  | Yes | Yes | NA | Yes | Yes | Yes | Yes | 6 | Community | Closed | Closed |  | Lazarus | 2019-10-07
SPDC | 34 | Sales of 800 jts of 3.1/2'' 9.3# N80 HCS R2 Tubing to EROTON Exploration and Production Limited | Kidney Island |  | Yes | Yes | NO | NA | Yes | No | No | 9 | EROTON E & P | Closed | closed |  | BGR | 2019-02-07
SPDC | 35 | Write-off and Disposal of Surplus Sea Eagle Materials at Onne Warehouse NG16 (Batch 2). | Onne | 25 | Yes | Yes | NA | No | No | No | No |  | Shell/NAPIMS/Comm | Awaiting NAPIMS approval | Awaiting NAPIMS |  | BGR | 21/6/2019
SPDC | 36 | Sale of Surplus and Used Wells Materials to NAOC Ltd | Kidney Island |  | Yes | Yes | NO | NA | Yes | NO | YES |  | NAOC Ltd | Closed | Closed |  | Line | 25/6/2019
SPDC | 37 | Write-off and Disposal of Obsolete Sea Eagle Materials (NG16) at Onne | Onne |  | Yes | Yes | NO | No | No | No | No |  |  | Awaiting NAPIMS approval | Awaiting NAPIMS |  | BGR | 31/7/2019
SPDC | 38 | DISPOSAL BY DIRECT SALES SURPLUS WELLS MATERIALS TO WEATHERFORD AND TENARIS. | PHC-IA/KI |  | Yes | Yes | No | NA | YES | YES-Weatherford | YES |  | Weatherford & Tenaris | Closed | Closed |  | BGR | 30/8/2019
SPDC | 39 | Write-off and disposal of faulty 40'' Ball Valves at PHC-IA warehouse yard | PHC-IA |  | Yes | No | NO | No | No | No | No |  |  | Closed | Closed |  | Alex/Lazarus | 28/11/2019
SPDC | 40 | Write-off and disposal of Bulky EA Materials at Onne Warehouse Open Yard Area | Onne | 24 | Yes | Yes | NA | Yes | Yes | Yes | Yes |  | JC Fabrication | Evacuation | Evacuate |  | Vendor | 30/9/2019
SPDC | 41 | Write-off and disposal of Forcados Terminal scrap materials | Forcados |  | Yes | No | NO | NO |  |  | NO |  |  | Review in progress | Awaiting sign off |  | Asset | 16/8/2019
SPDC | 42 | Write off and disposal of leaking and expired chemicals at NG01-0106 Soku Warehouse. | Soku Gas Plant |  | Yes | NO | NO | NO |  |  | No |  |  | Awaiting NAPIMS approval | Awaiting sign off |  | BGR/Tunji | 31/10/2019
SPDC | 43 | Write-off and Disposal of Expired and dis-used Batteries in SPDC Warehouses (NG11, NG12, NG15, NG16 and NG01-130, 170, 1060, and 108. | All warehouses |  | Yes | YES | NO | NO |  |  | No |  |  | Awaiting NAPIMS approval | Awaiting NAPIMS |  | BGR/Tunji | 31/10/2019
SPDC | 44 | Write-off and disposal of recovered completion tubing from Kolo Creek 016 and Adibawa 017 wells abandonment. | AdIBAWA/Kolo Creek |  | Yes | YES | NO | NO |  |  | No |  |  | Awaiting NAPIMS approval | Awaiting NAPIMS |  | BGR/Tunji | 31/10/2019

## 2019 SPDC Disposal Records
DATABASE OF ALL DISPOSALS COMPLETED IN 2019 ($1=N305)
S/N | MATERIALS DESCRIPTION | VENDOR NAME | Acquisition Cost | ESTIMATED MARKET VALUE | NAPIMS APPROVAL THRESHOLD? | REVENUE REALISED NGN | REVENUE REALISED USD | REVENUE REALISED F$ | REQUEST DATE | DATE OF APPROVAL | RECEIPT DATE | DISPOSAL STRATEGY | SPDC RECEIPT NUMBER | DISPOSAL LOCATION | ALLOCTAED TO | QUARTER
1 | Disposal of Obsolate Bonny Warehouse Materials at Bonny | YUSSER Nigeria Limited | 3856425.59 | 192821.28 | Yes | 155000 |  | 508.1967 | July-21-2016 | Sept-14-2016 | Jan-8-2019 | Tender | 1517 | Bonny | NAPIMS | Q1
2 | NG01024026- Disposal of 2 Lots of 1 pc in each Lot MCB3A Safety Life Boats and Shipping Skid at Onne. | Strano Line Limited | 200000 | 10000 | Yes | 2500000 |  | 8196.7213 | July-16-2018 | July-25-2018 | Jan-30-2019 | Tender | 1523 | Onne | NAPIMS | Q1
3 | Disposal of scrap metals generated from generating and Instrument workshop at PHC-IA | J. C. Fabrication Company | 5437.5 | 271.88 | NO | 215000 |  | 704.918 | Nov-16-2018 | Nov-21-2018 | Feb-21-2019 | Tender | 1530 | Onne | COMMUNITY | Q
4 | Disposal of Scrap Tubing Recovered from ADIBAWA Wells Decom. Campaign | Zuan Services | 309160.6 | 6183.21 | Yes | 25000 |  | 81.9672 | Oct-16-2018 | Oct-24-2018 | Feb-13-2019 | Tender | 1528 | Adibawa | COMMUNITY | Q1
5 | Disposal scrap materials at Soku Gas Plant | Furda Ventures Limited | 15154.32 | 15154.32 | Yes | 800000 |  | 2622.9508 | Oct-20-2018 | Oct-19-2018 |  | Tender |  | Soku | SPDC | Q1
| Doc- 218939879- Disposal of scrap materials at Soku Gas Plant | Pre-Filda Nigeria Limited |  |  | Yes | 200000 |  | 655.7377 | Oct-20-2018 | Oct-19-2018 | Apr-3-2019 | Tender | 1538 | Soku | COMMUNITY | Q2
6 | Doc -223247488-Disposal of 5s project surplus project materials at PHC-IA warehouse yard | A. C. Uche and Sons Ltd | 4647712.95 | 232388.65 | Yes | 104000 |  | 340.9836 | Oct-20-2013 | Dec-18-2018 | Apr-18-2019 | Tender | 1546 | PHC-IA | COMMUNITY | Q2
| Doc -223247488-Disposal of 5s project surplus project materials at PHC-IA warehouse yard | K-Maceleno Ventures | Do | DO | Yes | 220000 |  | 721.3115 | Oct-20-2013 | Dec-18-2018 | Apr-30-2019 | Tender | 2263 | PHC-IA | SPDC | Q2
7 | Sales of 350 jts of 3.1/2'' 9.3# N80 HCS R2 Tubing to EROTON Exploration and Production Limited | EROTON Exploration and Production Limited | 277837 |  | Yes |  | 277837 | 277837 | May-14-2019 | June-11-2019 |  | Negotiation |  | PHC-KI | SPDC | Q2
8 | Doc- 235727604-Disposal of Production Workshop West Scrap metals at Shell I.A Ogunu Warri | Hen-Xer Ventures | 6510.5 | 325.53 | No | 400000 |  | 1311.4754 | Mar-19-2019 | May-9-2019 | May-22-2019 | Tender | 2272 | Ogunu | SPDC | Q2
9 | Doc-235037175-Disposal of decommissioned scrap metals at RA water facility (Sub 1, 2 and 3) | Styno Global Resources | 6162.5 | 308.13 | No | 61000 |  | 200 | Apr-24-2019 | May-7-2019 | May-22-2019 | Tender | 2275 | RA | SPDC | Q2
10 | Write-off and disposal of disused items at Abuja office | Duzof Chemical & Engineering Services | 9857.38 | 197.15 | No | 410000 |  | 1344.2623 | Jan-8-2019 | feb-19-2019 | May-23-2019 | Tender | 2276 | Abuja | SPDC | Q2
11 | Doc-235257569-Disposal of Tubing Recovered from ADIBAWA 003,006,013 Well decommissioning | Omonye Ventures | 309160 | 6183.21 | Yes | 575000 |  | 1885.2459 | Oct-16-2018 | Oct-24-2018 | May-28-2019 | Tender | 2285 | ADIBAWA | SPDC | Q2
12 | Doc- 239667233- Disposal of 1 Lot Obsolete Electrical Materials at PHC-IA Warehouse Yard SPDC Lot | Silvafield Enterprises | 267754.57 | 5355.09 | Yes | 400000 |  | 1311.4754 | Sept-11-2018 | Dec-13-2018 | June-6-2019 | Tender | 2286 | PHC-IA | SPDC | Q2
13 | Doc- Disposal of 1 Lot Obsolete Electrical Materials at PHC-IA Warehouse Yard | A. C. Uche and Sons Ltd |  |  | Yes | 132000 |  | 432.7869 | Sept-11-2018 | Dec-13-2018 | June-10-2019 | Tender | 2288 | PHC-IA | SPDC | Q2
14 | Doc 218960542- Disposal of scrap materials at Soku Gas Plant NAPIMS Lot | Darsha Consults Nig Ltd |  |  | Yes | 400000 |  | 1311.4754 | Oct-20-2018 | Oct-19-2018 | June-6-2019 | Tender | 2287 | Soku | SPDC | Q2
15 | Doc 252400423- Disposal of Intermediate Bulk Containers (IBC) at Kidney Island | A. C. Uche and Sons Ltd | 5000 | 250 | No | 8000 |  | 26.2295 | May-24-2019 | June-14-2019 | July-8-2019 | Tender | 2291 | PHC-KI | COMMUNITY | Q3
16 | Doc- 252389889 Disposal of 2 pcs empty Coantainers at IA Power Plant | Chi-Tech Steel Company Nig Ltd | 295.08 | 147.54 | No | 20000 |  | 65.5738 | Sept-18-2018 | Oct-2-2018 | July-8-2019 | Tender | 2290 | PHC-IA | COMMUNITY | Q3
17 | Doc -223247470-Disposal of 5s project surplus project materials at PHC-IA warehouse yard | Vitex Interbiz Agency LTD |  |  | Yes | 550000 |  | 1803.2787 | Oct-20-2013 | Dec-18-2018 | July-16-2019 | Tender | 2292 | PHC-IA | NAPIMS | Q3
18 | Doc-239643253 Disposal of 1 Lot Obsolete Electrical Materials at PHC-IA Warehouse Yard | Aigog Nigeria Ventures |  |  | Yes | 100000 |  | 327.8689 | Sept-11-2018 | Dec-13-2018 | Aug-5-2019 | Tender | 554 | PHC-IA | NAPIMS | Q3
19 | Sales of Surplus and Used Wells materials to Weatherford Nigeria Limited | Weatherford Nigeria Limited | 121936.5 |  | Yes |  | 109162.2 | 109162.2 | June-24-2019 |  |  | Negotiation |  | PHC-IA |  | Q3
20 | DOC 280583402_DISPOSAL OF EA BULKY MATERIALS AT ONNE (COMMUNITY LOT) | JC Fabrication Company | 6390.88 | 319,54 | NO | 55000 |  | 180.3279 | July-25-2019 | Aug-21-2019 | Sept-24-2019 | Tender | 560 | Onne | COMMUNITY | Q3
SALES OF LIGHT VEHICLES-NAPIMS SHARE
21 | FKJ 241 CA | NWABUFO ELDRED |  |  | Yes | 250000 |  | 819.6721 |  |  | Oct-21-2019 | Allocation |  | East | NAPIMS | Q4
22 | FKJ 767 CA | DR FEMI PEARS |  |  | Yes | 175000 |  | 573.7705 |  |  | Oct-18-2019 | Allocation |  | East | NAPIMS | Q4
23 | AH 420 RGM/GBB 592 AA | BABA ISAH |  |  | Yes | 175000 |  | 573.7705 |  |  | Oct-23-2019 | Allocation |  | East | NAPIMS | Q4
24 | NCH 339 ST | KINGSLEY EBI |  |  | Yes | 175000 |  | 573.7705 |  |  | Oct-18-2019 | Allocation |  | East | NAPIMS | Q4
25 | SKN 446 PZ | FLORA ADENUGA |  |  | Yes | 175000 |  | 573.7705 |  |  | Oct-15-2019 | Allocation |  | East | NAPIMS | Q4
26 | SKN 469 PZ | OGBODABA PHILEMO OUMO |  |  | Yes | 175000 |  | 573.7705 |  |  | Oct-15-2019 | Allocation |  | East | NAPIMS | Q4
27 | SKN 422 PZ | JULIE UTANG |  |  | Yes | 175000 |  | 573.7705 |  |  | Oct-16-2019 | Allocation |  | East | NAPIMS | Q4
28 | AM 54 BNY | BASSEY E.R |  |  | Yes | 125000 |  | 409.8361 |  |  | Oct-16-2019 | Allocation |  | East | NAPIMS | Q4
29 | SKN 452 PZ | ALEX CHUKWU |  |  | Yes | 175000 |  | 573.7705 |  |  | Oct-16-2019 | Allocation |  | East | NAPIMS | Q4
30 | GBB 577 AA | IBRAHIM MARTINS |  |  | Yes | 100000 |  | 327.8689 |  |  | Oct-16-2019 | Allocation |  | East | NAPIMS | Q4
31 | YEN 512 SY | NKEM AGUMAGU |  |  | Yes | 175000 |  | 573.7705 |  |  | Oct-15-2019 | Allocation |  | East | NAPIMS | Q4
32 | KRK 685 BX | TIMOTHY ODEYEMI |  |  | Yes | 250000 |  | 819.6721 |  |  | Oct-15-2019 | Allocation |  | East | NAPIMS | Q4
33 | GBB 623 AA | TAFA FATAI KEHINDE |  |  | Yes | 150000 |  | 491.8033 |  |  | Oct-21-2019 | Allocation |  | East | NAPIMS | Q4
34 | DOC300527581 - DISPOSAL OF SCRAP MATERIALS AT RUMUAHIA . | Christo General Contracting And Enterprises | 1137.71 |  | Yes | 420000 |  | 1377.0492 | Sept-18-2018 | Oct-16-2019 | Nov-4-2019 | Tender | 570 | RUMUAHIA | COMMUNITY | Q4
35 | NCH 413 ST | USMAN BALA |  |  | Yes | 100000 |  | 327.8689 |  |  | Nov-5-2019 | Allocation |  | East | NAPIMS | Q4
36 | DEG 508 EQ | SAIDU USMAN |  |  | Yes | 100000 |  | 327.8689 |  |  | Nov-5-2019 | Allocation |  | East | NAPIMS | Q4
37 | NCH 399 ST | ETHAN SUNDAY |  |  | Yes | 150000 |  | 491.8033 |  |  | Nov-5-2019 | Allocation |  | East | NAPIMS | Q4
38 | BDG 17 BX | CHRISTOPHER DANIEL |  |  | Yes | 250000 |  | 819.6721 |  |  | Nov-5-2019 | Allocation |  | East | NAPIMS | Q4
39 | SKN 439 PZ | BUHARI SANNI |  |  | Yes | 175000 |  | 573.7705 |  |  | Oct-25-2019 | Allocation |  | East | NAPIMS | Q4
40 | SKN 421 PZ | IBRAHIM GONI |  |  | Yes | 175000 |  | 573.7705 |  |  | Nov-5-2019 | Allocation |  | East | NAPIMS | Q4
41 | AHD 458 QW | JUMOKE MOBI |  |  | Yes | 175000 |  | 573.7705 |  |  | Nov-5-2019 | Allocation |  | East | NAPIMS | Q4
42 | KJA-109EH | ABIOLA KOJO |  |  | Yes | 200000 |  | 655.7377 |  |  | Nov-5-2019 | Allocation |  | East | NAPIMS | Q4
43 | SMK 164 BZ | HAMZA ABACHA |  |  | Yes | 250000 |  | 819.6721 |  |  | Nov-5-2019 | Allocation |  | East | NAPIMS | Q4
44 | EKE 730 AA | DARAMOLA FRANCIS |  |  | Yes | 175000 |  | 573.7705 |  |  | Oct-25-2019 | Allocation |  | East | NAPIMS | Q4
45 | LND 235 CN | OKONKWO DENIS |  |  | Yes | 175000 |  | 573.7705 |  |  | Nov-5-2019 | Allocation |  | East | NAPIMS | Q4
46 | AH408-ABM | ODUKOYA JIDE |  |  | Yes | 200000 |  | 655.7377 |  |  | Nov-8-2019 | Allocation |  | East | NAPIMS
47 | KRK 651 BX | MARTHIAS DAMO |  |  | Yes | 175000 |  | 573.7705 |  |  | Nov-22-2019 | Allocation |  | East | NAPIMS
48 | Sales of written off Surplus OCTG and Equipment by Direct Sales to EROTON | EROTON Exploration and Production Limited | 120000 |  | Yes |  | 119975 | 119975 | [5 empty] | East |  | Q4
49 | APP 94 BD | ADENIRAN MOJISOLA |  |  | Yes | 800000 |  | 2622.9508 |  |  | Nov-12-2019 | Ballot | 581 | East | SPDC | Q4
50 | JJJ 585 CK | AFOLABI OLUBUNMI |  |  | Yes | 500000 |  | 1639.3443 |  |  | Nov-15-2019 | Ballot | 592 | East | SPDC | Q4
51 | SKN 443 PZ | OKONKWO OLUCHI |  |  | Yes | 250000 |  | 819.6721 |  |  | Nov-4-2019 | Ballot | 569 | East | SPDC | Q4
52 | DEG 531 EQ | OSHONUGA OLUFEMI |  |  | Yes | 350000 |  | 1147.541 |  |  | Nov-8-2019 | Ballot | 574 | East | SPDC | Q4
53 | JJJ 594 CK | UDOGU JOHN |  |  | Yes | 900000 |  | 2950.8197 |  |  | Nov-8-2019 | Ballot | 573 | East | SPDC | Q4
54 | RLU 93 MB | ABHURIMEN THANKGOD |  |  | Yes | 250000 |  | 819.6721 |  |  | Nov-8-2019 | Ballot | 575 | East | SPDC | Q4
55 | JJJ 592 CK | OKAFOR FRANKLIN |  |  | Yes | 900000 |  | 2950.8197 |  |  | Nov-8-2019 | Ballot | 576 | East | SPDC | Q4
56 | JJJ 589 CK | BADEMOSI ADEBAYO |  |  | Yes | 900000 |  | 2950.8197 |  |  | Nov-7-2019 | Ballot | 571 | East | SPDC | Q4
57 | GBB 599 AA | OSAYE SOLOMON |  |  | Yes | 500000 |  | 1639.3443 |  |  | Nov-12-2019 | Ballot | 577 | East | SPDC | Q4
58 | JJJ 586 CK | AJAYI JOY |  |  | Yes | 900000 |  | 2950.8197 |  |  | Nov-12-2019 | Ballot | 578 | East | SPDC | Q4
59 | NCH 338 ST | ALIKAH YEWANDE |  |  | Yes | 300000 |  | 983.6066 |  |  | Nov-13-2019 | Ballot | 587 | East | SPDC | Q4
60 | JJJ 588 CK | INYANG ERIC |  |  | Yes | 900000 |  | 2950.8197 |  |  | Nov-12-2019 | Ballot | 585 | East | SPDC | Q4
61 | JJJ 591 CK | OKAHIA VICTOR |  |  | Yes | 900000 |  | 2950.8197 |  |  | Nov-14-2019 | Ballot | 590 | East | SPDC | Q4
62 | JJJ 584 CK | BABATUNDE SALAWU |  |  | Yes | 900000 |  | 2950.8197 |  |  | Nov-13-2019 | Ballot | 589 | East | SPDC | Q4
63 | JJJ 590 CK | EZE GEORGE |  |  | Yes | 900000 |  | 2950.8197 |  |  | Nov-13-2019 | Ballot | 586 | East | SPDC | Q4
64 | XB 612 WWR | ANDREW BOCK-ORUMA |  |  | Yes | 350000 |  | 1147.541 |  |  | Nov-7-2019 | Ballot | 572 | East | SPDC | Q4
65 | NCH 430 ST | OLUWAFEMI AGBAVBE |  |  | Yes | 200000 |  | 655.7377 |  |  | Nov-12-2019 | Ballot | 579 | East | SPDC | Q4
66 | RGM 561 RD | MARYAM ABDULLAHI |  |  | Yes | 150000 |  | 491.8033 |  |  | Nov-12-2019 | Ballot | 584 | East | SPDC | Q4
67 | RGM 582 RD | UCHE ANYAOGU |  |  | Yes | 150000 |  | 491.8033 |  |  | Nov-12-2019 | Ballot | 582 | East | SPDC | Q4
68 | JJJ 581 CK | KingSLEY AMADI (AKPALA UDE) |  |  | Yes | 900000 |  | 2950.8197 |  |  | Nov-8-2019 | Ballot |  | East | SPDC
69 | NO DOC 314523858_DISPOSAL OF DECOMMISSIONED TUBING FROM IMO RIVER WELL 16_SPDC LOT | MEEK INTEGRATED SYSTEMS LTD | 77894.28 | 3894.71 | Yes | 1000000 |  | 3278.6885 | Feb-22-2018 | Mar-1-2019 | Dec-2-2019 | Tender | 3046 | East | SPDC | Q4
70 | DOC_315081350_DISPOSAL OF TUBINGS RECOVERED FROM NKALI WELL 08 _ SPDC LOT | KADIBIA MULTI PROJECTS NIG LTD | 100980 | 5049 | Yes | 1200000 |  | 3934.4262 | Feb-26-2018 | Mar-1-2019 | Dec-2-2019 | Tender | 1150 | East | SPDC | Q4
71 | Doc- 314980772, Disposal of Tubings Recovered from Nkali Wells 08 NAPIMS Lot | Ruma Investment Nigeria Limited |  |  | Yes | 114000 |  | 373.7705 | Feb-26-2018 | Mar-1-2019 | Dec-6-2019 | Tender | 171 | East | SPDC | Q4
72 | Doc- 314980772, Disposal of Tubings Recovered from Nkali Wells 08 NAPIMS Lot | Solid Gas and Oil Services Ltd |  |  | Yes | 114000 |  | 373.7705 | Feb-26-2018 | Mar-1-2019 | Dec-6-2019 | Tender | 174 | East | SPDC | Q4
73 | Doc-31505660, Disposal of Decommissioned Tubings from Imo River Well 16 NAPIMS LOT | Ruma Investment Nigeria Limited |  |  | Yes | 324000 |  | 1062.2951 | Feb-22-2018 | Mar-1-2019 | Dec-6-2019 | Tender | 173 | East | SPDC | Q4
74 | DOC 314394643_DISPOSAL OF 40 INCES BALL VALVES AT PHC-IA WAREHOUSE YARD_COMMUNITY LOT | A C UCHE AND SONS | 2744035.72 | 54880.72 | Yes | 370000 |  | 1213.1148 | Aug-5-2019 | Aug-29-2019 | Dec-10-2019 | Tender | 175 | East | SPDC | Q4
75 | DOC 318168285_DISPOSAL OF 40 INCES BALL VALVES AT PHC-IA WAREHOUSE YARD_NAPIMS LOT | Solid Gas and Oil Services Ltd |  |  | Yes | 325000 |  | 1065.5738 | Aug-5-2019 | Aug-29-2019 | Dec-18-2019 | Tender | 194 | East | NAPIMS | Q4
76 | DOC 318168285_DISPOSAL OF 40 INCES BALL VALVES AT PHC-IA WAREHOUSE YARD_NAPIMS LOT | Petro-Jam Nig Ltd |  |  | Yes | 325000 |  | 1065.5738 | Aug-5-2019 | Aug-29-2019 | Dec-18-2019 | Tender | 196 | East | NAPIMS | Q4
77 | DOC 318168285_DISPOSAL OF 40 INCES BALL VALVES AT PHC-IA WAREHOUSE YARD_NAPIMS LOT | Ruma Investment Nig. Ltd |  |  | Yes | 325000 |  | 1065.5738 | Aug-5-2019 | Aug-29-2019 | Dec-18-2019 | Tender | 193 | East | NAPIMS | Q4
78 | DOC NO DOC 317243524_DISPOSAL OF 40 INCES BALL VALVES AT PHC-IA WAREHOUSE YARD_SPDC LOT | MEEK INTEGRATED SYSTEMS LTD |  |  | Yes | 9000000 |  | 29508.1967 | Aug-5-2019 | Aug-29-2019 | Dec-24-2019 | Tender | 764 | East | SPDC | Q4
79 | DOC_321860295_DISPOSAL OF SURPLUS MATERIALS LOTS 1-4 AT PHC-IA WAREHOUSE YARD BATCH 8/9/10 SPDC LOT | Dinichuks and Company Limited | 93191523.04 | 4659576.15 | Yes | 4200000 |  | 13770.4918 | Nov-12-2019 | Dec-12-2018 | Dec-16-2019 | Tender | 180 | East | SPDC | Q4
80 | Sales of Wellhead Materials and accessories to NAOC | NAOC |  |  | Yes |  | 2420991.11 | 2420991.11 | Jan-23-2019 | May-3-2019 | Dec-19-2019 | Negotiation |  | East | SPDC | Q4
81 | DOC 332586768_DISPOSAL OF SCRAP METALS AT SHELL RA SUB 3. | STYNO GLOBAL RESOURCES | NA | 262.3 | No | 20000 |  | 65.5738 | Oct-22-2019 | De-c-9-2019 | Dec-19-2019 | Tender | 200 | East | SPDC | Q4
| TOTAL |  |  |  |  | 41542000 | 2927965.31 | 3064168.5887

## 2019 SNEPCo Disposal Records
DATABASE OF ALL DISPOSALS COMPLETED IN 2019 ($1=N305)
S/N | MATERIALS DESCRIPTION | VENDOR NAME | Acquisition Cost | ESTIMATED MARKET VALUE | NAPIMS APPROVAL THRESHOLD? | REVENUE REALISED NGN | REVENUE REALISED USD | REVENUE REALISED F$ | REQUEST DATE | DATE OF APPROVAL | RECEIPT DATE | DISPOSAL STRATEGY | SNEPCo RECEIPT NUMBER | DISPOSAL LOCATION | ALLOCTAED TO | QUARTER
1 | Doc 218734982- Disposal of scrap materials Backloaded from Bonga FPSO currently stored at Onne Warehouse Yard (Batch 6) | G.B. Nchima | 253.75 | 253.75 | No | 63000 |  | 206.5574 | Jan-25-2019 | Feb-19-2019 | Mar-28-2019 | Tender | 1758 | Onne | Community | Q1
2 | Doc 217814559- Disposal of Bonga Batch 5 Backload, H beams at Onne | A. C. Uche & Sons | 2745 | 137.27 | Yes | 60000 |  | 196.7213 | Aug-28-2019 | Nov-2-2018 | Mar-28-2019 | Tender | 1759 | Onne | Community | Q1
3 | Doc- 213390035 Sales of EPRS Pipes at Onne | Friday Nwibenale and Sons Enterprises Limited | 6620692.1 | 331034.61 | Yes | 28700000 |  | 94098.3607 | Nov-29-2018 | Dec-12-2018 | Apr-15-2019 | Tender | 1760 | Onne | SNEPCo | Q2
4 | Doc-216743177-Disposal of Bonga materials (1 Lot H Beam) at Onne SNEPCo | Dupre International Limited | 33000 | 6600 | Yes | 300000 |  | 983.6066 | Aug-28-2019 | Nov-2-2018 | May-14-2019 | Tender | 1764 | Onne | NAPIMS | Q2
5 | Doc 216413605_ Disposal of Bonga materials (9MW GT Alternator and H Beams at Onne SNEPCo | Ideki Services Limited | 1100000 | 167000 | Yes | 2000000 |  | 6557.377 | Aug-28-2019 | Nov-2-2018 | May-22-2019 | Tender | 1766 | Onne | SNEPCo | Q2
7 | DOC 275547096_DISPOSAL OF BULKY MATERIALS AT ONNE | Silvafield Enterprises | 493362.5 | 24668.13 | Yes | 800000 |  | 2622.9508 | July-17-2019 | July-17-2019 | Sept-11-2019 | Tender | 1778 | Onne | SNEPCo | Q3
8 | Doc 274653997_Disposal of NG28 surplus materials at Onne batches 3 and 4 NAPIMS Lot | Source Rock Ltd | 9087632.62 | 1817524.62 | Yes | 450000 |  | 1475.4098 | Dec-20-2018 | Dec-27-2018 | Sept-13-2019 | Tender | 1780 | Onne | NAPIMS | Q3
9 | DOC 275956054_DISPOSAL OF NG28 SURPLUS MATERIALS AT ONNE BATCHES 1 AND 2 SNEPCo LOT | Meje and Sons Ltd | 4946100.89 | 247305.04 | Yes | 550000 |  | 1803.2787 | Sept-24-2019 | Nov-23-2018 | Sept-13-2019 | Tender | 1779 | Onne | SNEPCo | Q3
| Doc 274438758_Disposal of NG28 surplus materials at Onne batches 3 and 4 SNEPCO Lot | Friday Nwibenale and Sons Enterprises Limited | 493362.5 | 24668.13 | Yes | 550000 |  | 1803.2787 | Dec-20-2018 | Dec-27-2018 | Sept-20-2019 | Tender | 1781 | Onne | SNEPCo | Q3
10 | DOC 280659719_DISPOSAL OF SNEPCo BATCH 2 WELLS MATERIALS AT ONNE (SNEPCo LOT) | J. Ifeanyi Ltd | 7885870.6 | 1088951.2 | Yes | 3800000 |  | 12459.0164 | Apr-23-2019 | June-21-2019 | Sept-20-2019 | Tender | 1783 | Onne | SNEPCo | Q3
| DOC 280728124_DISPOSAL OF SNEPCo BATCH 2 WELLS MATERIALS AT ONNE (COMMUNITY LOT | Mec Engineering Ltd |  |  | Yes | 405000 |  | 1327.8689 | Apr-23-2019 | June-21-2019 | Sept-20-2019 | Tender | 1786 | Onne | Community | Q3
| DOC 280728192_DISPOSAL OF SNEPCo BATCH 2 WELLS MATERIALS AT ONNE (NAPIMS LOT) | Asuru Integrated Services Nig Ltd |  |  | Yes | 900000 |  | 2950.8197 | Apr-23-2019 | June-21-2019 | Sept-20-2019 | Tender | 1782 | Onne | NAPIMS | Q3
| DOC 280728192_DISPOSAL OF SNEPCo BATCH 2 WELLS MATERIALS AT ONNE (NAPIMS LOT) | EKG Ltd |  |  | Yes | 900000 |  | 2950.8197 | Apr-23-2019 | June-21-2019 | Sept-20-2019 | Tender | 1784 | Onne | NAPIMS | Q3
| DOC 280728192_DISPOSAL OF SNEPCo BATCH 2 WELLS MATERIALS AT ONNE (NAPIMS LOT) | New Horozon Business System |  |  | Yes | 900000 |  | 2950.8197 | Apr-23-2019 | June-21-2019 | Sept-20-2019 | Tender | 1785 | Onne | NAPIMS | Q3
| DOC 280728192_DISPOSAL OF SNEPCo BATCH 2 WELLS MATERIALS AT ONNE (NAPIMS LOT) | Impex Agro Allied Ltd |  |  | Yes | 900000 |  | 2950.8197 | Apr-23-2019 | June-21-2019 | Oct-2-2019 | Tender | 1791 | Onne | NAPIMS | Q4
11 | DOC 280633329_DISPOSAL OF BULKY WELLS MATERIALS AT ONNE (COMMUNITY LOT) | J. C Fabrications Ltd | 6090 | 304.5 | No | 100000 |  | 327.8689 | Aug-22-2019 | Aug-29-2019 | Oct-2-2019 | Tender | 1793 | Onne | Community | Q4
| DOC 286520102_DISPOSAL OF NG28 NON-STOCK MATERIALS AT ONNE BATCHES 1 AND 2 SNEPCo LOT | Meje and Sons Ltd |  |  | Yes | 705000 |  | 2311.4754 | Apr-23-2019 | June-21-2019 | Oct-2-2019 | Tender |  | Onne | SNEPCo | Q4
12 | DOC287879323_DISPOSAL OF SUBSEA PLATFORM AND ITS ACCESSORIES AT SNEPCO ONNE GENERAL YARD SNEPCO LOT | G. B. Nchima Enterprises |  |  | Yes | 690000 |  | 2262.2951 | Jan-29-2019 | Mar-11-2019 | Oct-14-2019 | Tender |  | Onne | SNEPCo | Q4
| DOC 275547096_DISPOSAL OF BULKY MATERIALS AT ONNE NAPIMS LOT | Rowlas Investment Company Limited |  |  | Yes | 250000 |  | 819.6721 | July-17-2019 | July-17-2019 | Oct-15-2019 | Tender |  | Onne | NAPIMS | Q4
| NO DOC 299060575_DISPOSAL OF WELLS BATCH 2- 7.5/8’’ 42.8’’ VAM ACE BOX X PIN, R3 AT ONNE (NAPIMS LOT | New Horozon Business System |  |  | Yes | 330000 |  | 1081.9672 | Apr-23-2019 | June-21-2019 | Oct-25-2019 | Tender |  | Onne | NAPIMS | Q4
| NO DOC 299060575_DISPOSAL OF WELLS BATCH 2- 7.5/8’’ 42.8’’ VAM ACE BOX X PIN, R3 AT ONNE (NAPIMS LOT | Asuru Integrated Services Nig Ltd |  |  | Yes | 275000 |  | 901.6393 | Apr-23-2019 | June-21-2019 | Oct-25-2019 | Tender |  | Onne | NAPIMS | Q4
| NO DOC 299060575_DISPOSAL OF WELLS BATCH 2- 7.5/8’’ 42.8’’ VAM ACE BOX X PIN, R3 AT ONNE (NAPIMS LOT | Impex Agro Allied Ltd | 247500 |  | Yes | 247500 |  | 811.4754 | Apr-23-2019 | June-21-2019 | Oct-28-2019 | Tender |  | Onne | NAPIMS | Q4
| NO DOC 299060575_DISPOSAL OF WELLS BATCH 2- 7.5/8’’ 42.8’’ VAM ACE BOX X PIN, R3 AT ONNE (NAPIMS LOT | EKG Ltd |  |  | Yes | 247500 |  | 811.4754 | Apr-23-2019 | June-21-2019 | Nov-1-2019 | Tender |  | Onne | NAPIMS | Q4
13 | DOC 314382158_DISPOSAL OF BATCH 1 SNEPCO WELLS MATERIALS AT KIDNEY ISLAND COMMUNITY LOT | Nyenest Services Nig Ltd | 443690.67 | 250198.08 | Yes | 360000 |  | 1180.3279 | Feb-14-2019 | Apr-9-2019 | Nov-22-2019 | Tender |  | Onne | Community | Q4
14 | DOC 314096228_DISPOSAL OF BATCH 1 SNEPCo WELLS MATERIALS AT ONNE SNEPCo LOT | SEGBE ENGINEERING NIG. LTD | 5003961.61 | 250198.08 | Yes | 3000000 |  | 9836.0656 | Feb-14-2019 | Apr-9-2019 | Dec-6-2019 | Tender |  | Onne | SNEPCo | Q4
| DOC 314085900_DISPOSAL OF BATCH 1 SNEPCO WELLS MATERIALS AT ONNE (NAPIMS LOT) | Generation Merchants Nigeria Limited |  |  | Yes | 310000 |  | 1016.3934 | Feb-14-2019 | Apr-9-2019 | Dec-11-2019 | Tender |  | Onne | NAPIMS | Q4
| DOC 314960864_Disposal of Batch 1 SNEPCo Wells Materials at Onne (Community Lot) | JC Fabrication Co. Ltd |  |  | Yes | 330000 |  | 1081.9672 | Feb-14-2019 | Apr-9-2019 | Dec-11-2019 | Tender |  | Onne | Community | Q4
| DOC 317184595_DISPOSAL OF OBSOLETE PRODUCTION AND MAINTENANCE MATERIALS AT ONNE BATCHES 1 AND 2 COMMUNITY LOT | Dinichuks and Company Limited |  |  | Yes | 86000 |  | 281.9672 |  |  | Dec-11-2019 | Tender |  | Onne | Community | Q4
| DOC NO Doc332760284_DISPOSAL OF SUBSEA PLATFORM AT SNEPCO YARD ONNE | INTALY SERVICES LIMITED |  |  | Yes | 1530000 |  | 5016.3934 | Jan-29-2019 | Mar-11-2019 | Dec-20-2019 | Tender |  | Onne | SNEPCo | Q4
| TOTAL |  |  |  |  | 49739000 |  | 163078.6885

## Asset Sales
Completed Sales
S/N | Decription of Asset | Asset Owner (SPDC / SNEPCo) | Buyer | Location(s) | Space (sqm) | Status of Transaction |  |  | Value of Sale (US$) | Amount Received (US$) | Support Receeved
|  |  | Vendor(s) |  |  | S/Agreement Signed | Payment Made | Materials Evacuated |  |  | Business Support | SNEPCO / SPDC Approval | NAPIMS Approval
1 | Sales of Wells Materials to Eni | SPDC | Eni / NAOC | KI & PH-IA |  |  |  |  | 7500000 | 7500000
2 | Sale of BNW Forgings to BHGE in Aberdeen | SNEPCo | BHGE UK | Aberdeen |  | Yes | No | Yes | 15600 | 15600
3 | Direct Sales, 2 pieces, 5-1/2’’ 20ppf 13CR-80 VAM TOP HC Box x Pin Swell Packers to Total E & P Nig Ltd | SNEPCo | Total E & P Nig Ltd | Port Harcourt IA |  | Yes | No | Yes | 52553.84 | 52553.84
4 | Disposal of Sea Eagle disused Lifeboats | SPDC |  |  | 286
5 | Sales of OCTG to Eroton | SPDC | Eroton | KI |  |  |  |  | 277000 | 277000
6 | Sale of BNW Forgings to BHGE in Aberdeen (2) | SNEPCo | BHGE UK | Aberdeen |  | Yes | No | Yes | 5980
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
| Total | [7 empty] | 7851133.84 | 7845153.84
SNEPCo
SPDC

## Awaiting NAPIMS Approval JV
Applications for Scrap Disposal Awaiting NAPIMS approval - JV Requests
2020-01-13
S/N | Description | Our Ref | Acknowledgement date | Overdue by | Remarks | Value
1 | Application for Disposal of Scrapped and Dis-used Oil Spill Equipment and Materials at Ogunu Warri, Forcados Terminal(FOT) and Kidney Island Port Harcourt | SPDC-SCM-2017-0080L | 2017-10-31 | 804 | Awaiting NAPIMS approval
2 | Application for the Disposal of scrap Generators at 12 Inner Crescent Ikoyi Lagos | SPDC-SCM-2018-0021L | 2018-01-24 | 719 | Awaiting NAPIMS approval
3 | Application for Disposal of 1 Set VFLL-1 CAMERON SMART WELLHEAD By Direct Sales to CAMERON | SPDC-SCM-2018-0025L | 2018-01-26 | 717 | Awaiting NAPIMS approval
4 | Application for disposal of Tubings Recovered from Imo River well 16 and NKALI Well 08 Decom Campaign | SPDC-SCM-2018-0058L | 2018-03-05 | 679 | APPROVED
5 | Application for the Disposal of Well Engineering Pipes Direct to Rumuwoji Community | SPDC-SCM-2018-0135L | 2018-05-23 | 600 | Awaiting NAPIMS approval
6 | Application for the Disposal of Scrap Materials at RUMUAHIA Production Unit and Oguta FC | SPDC-SCM-2018-0227L | 2018-10-18 | 452 | APPROVED
7 | Application for the Disposal of Scrap Materials at Soku Gas Plant. | SPDC-SCM-2018-0229L | 2018-10-22 |  | APPROVED
8 | Write-off and disposal of Tubing recovered from ADIBAWA 003,006, 013 Well decommissioning. | SPDC-SCM-2018-0231L | 2018-10-26 | 444 | APPROVED
9 | Application for Disposal of 5s Project Obsolete Materials at NG11 PHC-IA Warehouse. | SPDC-SCM-2018-0272L | 2018-11-28 | 411 | APPROVED
10 | Application for Disposal of Obsolete Electrical and Shackle Materials at NG11 PHC-IA Warehouse | SPDC-SCM-2018-0291L | 2018-12-17 | 392 | APPROVED
11 | Application for Disposal of Written-off 10 Pieces, Abssorbent Pads by Direct Sales to Total E & P Nigeria Limited | SPDC-SCM-2019-0081L | 2019-04-24 | 264 | Awaiting NAPIMS approval
12 | Application for Disposal of Tubulars and Well Head materials by Direct Sale to Nigeria Agip Oil Company (NAOC) Limited | SPDC-SCM-2019-0049L | 2019-03-05 |  | APPROVED
13 | Application for Disposal of Scrap Materials at Okoloma Gas Plant | SPDC-SCM-2019-0101L | 2019-05-30 | 228 | APPROVED
14 | Application for Disposal of Laptop, HP, Probook640, Core 15-4210M, 500GB. | SPDC-SCM-2019-0111L | 2019-06-11 | 216 | APPROVED
15 | Application for Disposal by Direct Sales 350 joints of 3.1/2'' Tubing to EROTON Exploration and Production Company Limited | SPDC-SCM-2019-0119L | 2019-06-18 | 209 | Awaiting NAPIMS approval
16 | Application for Disposal of SPDC Light Vehicles in Port Harcourt, Warri and Abuja. | SPDC-SCM-2019-0127L | 2019-06-27 |  | APPROVED
17 | Application for Disposal of Surplus Sea Eagle Materials at Onne Warehouse NG16 (Batch 2). | SPDC-SCM-2019-0122L | 2019-06-21 | 206 | Awaiting NAPIMS approval
18 | Application for Disposal of written off Surplus OCTG of written-off Equipment by Direct Sales to EROTON | SPDC-SCM-2019-0128L | 2019-07-02 | 195 | Awaiting NAPIMS approval
19 | APPLICATION FOR DISPOSAL BY DIRECT SALES SURPLUS WELLS MATERIALS TO WEATHERFORD AND TENARIS. | SPDC-SCM-2019-0159L | 2019-08-07 | 159 | Awaiting NAPIMS approval
20 | Application for Disposal of Decommissioned scrap materials at Imo Rivers Old Gas Compression Plant and Old Compressor Building at Obigbo Node. | SPDC-SCM-2019-0160L | 2019-08-07 | 159 | Awaiting NAPIMS approval
21 | APPLICATION FOR DISPOSAL FAULTY 40 INCHES BALL VALVES. | SPDC-SCM-2019-0160L | 2019-09-11 | 124 | APPROVED
22 | Application for the Disposal of Expired and Dis-used Batteries in SPDC Warehouses | SPDC-SCM-2019-0208L | 2019-09-09 | 126 | Awaiting NAPIMS approval
23 | APPLICATION FOR THE DISPOSAL OF 2.3/8’’ TUBING FROM KOLO CREEK 016 AND ADIBAWA 017 WELLS | SPDC-SCM-2019-0207L | 2019-09-30 | 105 | Awaiting NAPIMS approval
24 | Abandoned Materials by NAPIMS Nominated Buyers | SPDC-SCM-2019-0226L | 2019-10-15 | 90 | Awaiting NAPIMS approval
25 | Application for Disposal of Wellhead and Xmas Tree Maintenance Accessories at NG11 PHC-IA Warehouse | SPDC-SCM-2019-0246L | 2019-10-31 | 74 | Awaiting NAPIMS approval

## Awaiting NAPIMS Approval PSC
Applications for Scrap Disposal Awaiting NAPIMS approval - PSC Requests
2020-01-13
S/N | Description | Our Ref | Acknowledgement date | Overdue by | Remarks | Value
1 | Application for Disposal of Bonga Materials at SNEPCo Warehouse Yard Onne. | SNEPCo-prod-2018-0162L | 2018-11-06 |  | APPROVED
2 | Application for Disposal of Obsolete Offshore Production/Maintenance Inventory at NG28 SNEPCoWarehouse Onne. Batches 1 & 2 | SNEPCo-PROD-2018-0169L | 2018-11-21 |  | APPROVED
3 | Application for the Disposal of EPRS Line Pipes at SNEPCo Yard Onne | SNEPCo-PROD-2018-0175L | 2018-12-12 |  | APPROVED
4 | Application for the Disposal of Subsea Platform and its Accessories at SNEPCo Onne general Yard. | SNEPCo-PROD-2019-0033L | 2018-03-12 |  | APPROVED
5 | Application fo Disposal of decommisioned Nodebus spares. |  | 2019-02-27 | 320 | Awaiting NAPIMS approval
6 | Application for Disposal by Direct Sales, 2 pieces, 5-1/2’’ 20ppf 13CR-80 VAM TOP HC Box x Pin Swell Packers to Total E & P Nigeria Limited. | SNEPCo-PROD-2019-0043L | 2019-03-09 |  | APPROVED
7 | Application for the Disposal of Wells Materials at Kidney Island and SNEPCo Yard Onne. | SNEPCo-PROD-2019-0055L | 2019-04-11 | 277 | APPROVED
8 | Application for the disposal of expired and damaged materials at NG28-2801 Bonga Onne | SNEPCo-PROD-2019-0069L | 2019-05-09 | 249 | Awaiting NAPIMS approval
9 | Application for the disposal of Bonga Batch 2 expired and damaged materials at NG27-2701 SNEPCo Onne | SNEPCo-PROD-2019-0079L | 2019-05-28 |  | APPROVED
10 | Application for the Disposal of Surplus Bonga Inventory Batches 1, 2, and 3 and Offshore Project materials at SNEPCo NG28 and NG26 Onne warehouses. | SNEPCo-PROD-2019-0091L | 2019-06-26 |  | APPROVED
11 | Application for the Disposal of Obsolete, Damaged and Surplus Wells Materials at NG28 SNEPCo Yard Onne Batch 2. | SNEPCo-PROD-2019-0104L | 2019-06-15 |  | APPROVED
12 | Application for the Disposal of Bulky Materials at Onne SNEPCo Warehouse Open Yard Area. | SNEPCo-PROD-2019-0110L | 2019-07-24 |  | APPROVED
13 | Application for the Disposal of Sub Sea and Bonga Bulky Materials at SNEPCo Yard Onne | SNEPCo-PROD-2019-0119L | 2019-08-19 | 147 | Awaiting NAPIMS approval
14 | Application for Disposal of Motorized Reel and other Bulky materials at Onne SNEPCO warehouse Open yard area | SNEPCo-PROD-2019-0132L | 2019-09-06 | 129 | APPROVED
15 | Application for the Disposal of EPRS Line Pipes at SNEPCo Yard Onne | SNEPCo-PROD-2019-0144L | 2019-09-30 | 105 | APPROVED
16 | Application for the disposal of Rapid Lock (RL) Riser Joints, baskets and Accessories at SNEPCo yard Onne. | SNEPCo-PROD-2019-0183L | 2019-12-02 | 42 | Awaiting NAPIMS approval

## Total Sales YTD
DISPOSAL SUMMARY YTD 2019 | TOTAL IN USD
PROCEEDS FROM DISPOSAL- SPDC | 418491
PROCEEDS FROM DISPOSAL- SNEPCo | 143198.36
TOTAL | 561689.36