## SNEPCO
SNEPCO Material Re-use 2018
7 Actions
Add action
Drag here to set row groups
Drag here to set column labels
#
Name
Responsible
Status
Start date
End date
6540
ONNE Material Inventorisation Revamp : Develop material revalidation plan for Onne materials
In Progress
2018-02-27
2018-03-30
ONNE Material Inventorisation Revamp : Identification / update of Bonga Inside materials requiring inventory update
In Progress
2018-02-28
2018-04-16
ONNE Material Inventorisation Revamp : Verification of Bonga outside material relocation space
In Progress
2018-03-01
2018-03-08
ONNE Material Inventorisation Revamp : Verification of Bonga outside material relocation status
In Progress
2018-03-01
2018-03-08
ONNE Material Inventorisation Revamp : Upload of Bonga Inside revalidated Materials into HDMMS
Not Started
2018-04-09
2018-04-20
ONNE Material Inventorisation Revamp : Revalidation of Onne outside Materials
Not Started
2018-05-01
2018-06-30
ONNE Material Inventorisation Revamp : Upload Onne outside revalidated materials into HDMMS
Not Started
2018-07-01
2018-07-13