## Slide 1: Digitise the Core - Invisible Assurance
D-FEAT – Digital Forensics, Error and Anomalies Tool
May 2021
Group CP Assurance/Nigeria CP Controls and Assurance
Robert Dabrowski – CP Assurance Advisor
Uchenna Okoroafor - Controls and Assurance Specialist
Ikemefula Ikwuagwu - Controls and Assurance Analyst

## Slide 2: D-FEAT – Agenda
D-FEAT – introduction
  Selection of the analytical tool for LOD2 CP Assurance enabling targeted deep-dives designed to limit fraud and CP process anomalies – See Project story line
  Implementation plans – for 16 high risk countries in scope – roll-out 2021/2022 – See implementation proposal
2021 – Pilot phase for wave1 countries
  Implementation for 3 countries – Go to Project Plan
    Brazil, Bolivia – go live planned end of Sep,
    Nigeria – go live planned end of Oct/beg Nov
  Data
    Historical transactional spend – initial data load from Jan 2019 to month before go live date
    Scope of documents being analyzed - Invoices, Purchase Orders, Payments
      Source of data – newly developed CP Data HUB in MS Azure or ERP tables directly
      Details of field extract from ERP tables as per the file ------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------>>
    New data incremental updates on a monthly basis
  Tool – state of art analytical being regularly updated with new scenarios based on industry and PwC forensic expertise – See about the Tool
    Analysis – scope
      150+ different Features grouped into 3 areas of analysis i.e., Legitimacy analysis, Compliance analysis, Anomaly analysis
      30+ Rules being checked based on the Features firing - with nomination of the cases for deep dive manual analysis - ------------------(POC examples) -->>
      Anomalies analysis using AI methodology (proprietary to PWC based on their forensic expertise) flagging each of the documents with certain number of anomaly level (0-100)
    Hosting
      Global instance – in the vendor managed cloud – for Brazil, Bolivia and wave2 countries in 2022
      Nigeria – due to Data embargo limitations - application to be hosted fully locally on premise without data being transferred outside the country
    Users
      Global Instance – Group CP Assurance Advisors (full access), local
      Nigeria – In country CP Assurance and controls team (full access), Group CP Assurance Advisors (limited access as per agreed control mechanism)
Nigeria specific plans
  Data – specifics
    Locally hosted – no SaaS solution involved application on premise
    Scenarios/Rules calibrated locally with CP Assurance and Control Team
  Implementation – part of the costing of central budget no impact on local level is planned from the tool costs (the possible local solution IT development/interface costs to be assessed after the Controller’s support for the project is granted)
  Potential benefits
    Strengthening of controls – validation of CP processes and finding anomalies/breaches
    Potential fraud limitation – based on conservative assumption that 1% (according to external sources worldwide it is even 4.5% - 10%) of procurement spend is at risk in Shell and the Tool could uncover 15% of it we do have for Nigeria potential cost avoidance of 3.7 MUSD (from yearly spend)
    Eliminating manual and fragmented checks with automation procedure using the Tool functionality - actionable for all the contracts before their end date
    Based on just one recent example of Reimbursable costs analysis for selected contracts the estimated potential benefits from elimination of overpay possibility is 0.5 MUSD
  Support required
    Local Shell IT Nigeria – cooperation with Global IT on specific hosting and implementation tasks
    Local CP Assurance and Control Team – cooperation with Group CP Assurance on details of the implementation

## Slide 3: D-FEAT PILOT PROJECT PoaP(Integrated with Nigeria)
 | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | July |  |  |  | Aug |  |  |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  | 
 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 1 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27
PROJECT MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CONTRACTING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GLOBAL WAVE 1 Data Sourcing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GLOBAL WAVE 1 Configuration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NIGERIA DATA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NIGERIA CONFIGURATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NIGERIA INFRASTUCTURE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Charter Agreed
PIRA Review & Signoff
SG2 Signoff
CIRA preparation and Sign-off
Project Execution and Solution Implementation
Contract negotiation Global and Nigeria
Engagement Kick-off
Data Sample
Go Live-Nigeria
BIA,LRA Preparation and Sign-Off
Go –Live Bolivia/Brazil
Contract Signed
Framework Agreement (MSA)
ARB review and sign-off
Build, Unit and UAT and Sign-off
Project kick -Off
Brazil & Bolivia Hypercare
ATO Brazil/Bolivia
PM/Azure dev
Onboarding
Test Strategy/planning with PwC and test cases sign-off
Agree hosting and management design
Prep test instance
Prep UAT instance
Prep staging & prod instance
SAHLD Doc prep
Budget & LE sign-off
ATD Brazil, Bolivia
Detailed Design
Development
Testing
Pre-deployment Plan/Review
SG 4 Sign-off
Data Agreement
Data Production for UAT
Agreed Data Spec
Configuration Scoping for Nigeria
Instance Configuration Prep
Prep with Live Data and UAT
Engagement with the CP data hub warehousing team
Data Sample
Data Production for UAT
Configuration Scoping for Brazil/Bolivia
Custom Feature
Prep Test Instance Configuration
D-FEAT specific SOW
Notes: Make Soc Gen red
Mashreq- 19 July

## Slide 4: WHAT: PROBLEM LEARNING NEXT STEPS
Recommendation
D-FEAT meeting CP Assurance requirements
Next Steps
D-FEAT implementation -2021-23
3
2021 Plan Milestones:
Mobilization of Shell IT team (PM, BA, IRM) – end Apr./beg May
Negotiated and signed contracts with Supplier - a) for the global instance and b) dedicated for Nigeria as local hosting is needed – Q3 2021
Development completed (Shell IT interfaces etc.) - Q3 2021 (including CP Data HUB in Azure for Blueprint countries of Wave1)
Go live of Wave1– Q3 (Bolivia, Brazil), Q4 (Nigeria)
Invisble Assurance: Digitize the Core, Time Liberation, Cash Preservation
D-FEAT - CP Assurance future Tool
Implement SaaS (Software as a Service) approach with Vendor hosting the D-FEAT application (with exception of Nigeria)
D-FEAT – Improvements before implementation
upgrade the Tool (defects/enhancements from PoC ); move to monthly cadence of data uploads; no data anonymization
D-FEAT - Phased Implementation
16 countries in 2 waves for 3 years contract
Costs: 1.02M$ vs. Benefits: 9.34M$
D-FEAT – Selected for Proof
of Concept (PoC)
D-FEAT – Scope and
Characteristics
D-FEAT - Learning
D-FEAT – Insights and benefits from PoC
2
PoC – Scope
2 sites - T&T (IG), MX (DS); 2 years spend (Jun18 - May20) - $1.7 bln; 2 ERPs - P42, GSAP
PoC - Dimensions
549 Vendors, 113 ERP Users, 92K Invoice lines, 55.5K PO lines,
Data partially anonymized
D-FEAT – characteristics
150+ Features inspected; 30+ Rules/Scenarios applied; Anomalies AI detection module used
Insights and benefits from PoC
After review of results with local teams 0.03% of Invoice spend and 2.3% of PO spend were indicated as suspicious anomalies
Anomalies screening functionality (using AI algorithm based on PWC experience) was able to localize and help in LOD2 control activities flagging numbers of certain Process Issues with examples
PoC has proven capabilities of D-FEAT of optimizing the time needed for a complete country review process. Based on experience from Nigeria it can be confirmed that with D-FEAT we could shorten the review time from 12-18 m to 4-5 m per country
Current State Problem
Business friction – based on CP Assurance
Control Desks activities for Nigeria
Strategic Movement Plans
CP Digitalization Vision – Theme 2: Digitize
the Core – Priority 5: Invisible Assurance
1
Manual efforts
Cumbersome ERP data extracts and laborious analysis (using Excel and simplified Spotfire reporting only)
Non effective
Statistically irrelevant results - based on small samples of targeted deep dives assurance checks – lack of scalability
Time consuming
12 to 18 months –(2 FTEs) – for a single country analysis, never-ending
Eliminate manual work
Enabled by state-of-the-art technology (integrated analytical solution) – Tool selected after extensive RFI follow by RFP process
Automate WOW
Ability to review big datasets and focus manual assurance analysis on automatically pre-selected valid targets
Scale the benefits without scaling the efforts
Do more and faster with the same resource level employed
A
B
A
B
A
B
Step No
A
B
D-FEAT – Digital Forensics, Error and Anomalies Tool

## Slide 5: D-FEAT: PROPOSAL FOR ACCELERATED IMPLEMENTATION (2021 - 2022)
Implement the project using SaaS (Software as a Service) approach with Vendor hosting the D-FEAT application
CP Data Hub – source of the data for D-FEAT without anonymisation
Release in 16 countries (including Nigeria in-country hosted) in 2 Waves (2021-2022)
Approx. annual spend: ~ $402k (Year1 – $230k — 3rd party and $172k -- Shell IT) + $375k (Year2) + $243k (Year3)
$1.02 million for 3 years contract against the conservative benefit of $9.34 million
Grouping of countries
Management
Difficult to manage all countries together
Tuning the tool in 1st Year
Less countries in first year will help in more deep-dive into analysis
Value and interest
Prioritization based on interest and potential value (*Malaysia could be over Brazil)
Wave 1
Bolivia, Brasil, Nigeria , (covered in 2020 POC: México, T&T)
Wave 2
Egypt, Malaysia, Oman, Pakistan, Philippines
Wave 3
CEE (Czech, Slovakia, Hungary, Bulgaria) Poland, Italy.
Reasons for Waves implementation
$1.02m Spend
$9.34m Benefits
Waves merged in 2022
* CEE - Czech Republic, Slovakia, Hungary, Bulgaria
Poland
Italy
Egypt
Malaysia
Oman
Pakistan
Philippines
Nigeria
Bolivia
Brazil
Mexico
Trinidad & Tobago
CEE*

## Slide 6: About D-FEAT Application
D-FEAT application is based on Data Ignition (from PWC), its mature compliance (30+ global major companies being clients), analytics and reporting platform. This platform supports end-to-end monitoring of financial transactions across several applications using Accounts Payable data. Application functionality breaks down into three areas:
ERP data ingestion
D-FEAT ingests data from common ERP systems (including SAP) via a pluggable connector architecture. It employs an extensible data model that allows the data fields to be customized for each instance.
Automated data/anomalies’ analysis for fraud detection purposes
A set of automated analysis jobs then identify ‘features’, representing interesting or unusual facets in the data. Further analysis jobs triangulate features to produce results, representing unusual and therefore potentially fraudulent/anomaly activity for further manual review.
Collaborative results review
The application provides functionality to help users review the results and explore the related data for context. This includes self-service interactive dashboards, the ability to annotate results, tag them and manage them through a review workflow.