## Slide 1: Provisional Schedule for KOMA Wells Rerouting
FEED/DED | LEC | Action Party
1st Contact Meeting (In-house DED) | Feb-22 | ALL
Piping modification/ISO/MTO List (D01) | 13th Mar | Nnamdi
Piping modification review | 17th Mar | Nnamdi
Piping modification/ISO/MTO List (D02) | 21st Mar | Nnamdi
PEFS Red-line mark-up | 31st Mar | Daniel Wya
Technical Risk Assessment | 1st Apr | Oluoma
Civil/Structural supports/MTO List (D01) | 7th Apr | Ayomide
CCMP (MoC) submission | 14th Apr | Nnamdi
Bow-Tie/HAZID Workshop | 15th Apr | Madu/Darlington
PDMS Model/Constructability review | 19th Apr | Nnamdi/Idio
Piping modification/ISO/MTO List (C01) | 25th Apr | Nnamdi
Civil/Structural supports/MTO list (C01) | 25th Apr | Ayomide

## Slide 2: Provisional Schedule for KOMA Wells Rerouting
C&P | LEC | Action Party
Issuance of existing SAP MM nos. | 1st May | Chinwe/Jimba
MMRF coding (New SAP MM nos.) | 6th May | Chinwe/Jimba
PR Creation (LLIs) | 10th May | Chinwe/Jimba
PO Creation (LLIs) | 31st May | Chinwe/Jimba
PMT | LEC | Action Party
Issue PO (Civil/Structural works) | 30th Jun | Chinwe/Jimba
Issue PO (Mech/Piping works) | 31st Jul | Chinwe/Jimba
Mobilize to site | 30th Aug | Chinwe/Jimba
Complete Civil/Structural supports | 30th Sept | Chinwe/Jimba
Delivery of LLIs to site | 10th Oct | Chinwe/Jimba
Koroama Mfd wells shut-in/de-pressurization/safe isolation | 20th Oct | Bayo
Complete Mech/Piping installation works | 30th Nov | Jimba
Pre-CSU/TIV/CSU/72hrs RTR | 10th Dec | Iheme
De-mobilize from site | 15th Dec | Jimba