## 2018
DSV OPTIMIZATION IN SEPCiN
SEA EAGLE
item | Project | Year | duration | Location | Working Schedule | IAP (Y/N) | Vessel Required | Past Vessel Used | Daily Rate (only Vessel) | Contract Type | Fuel (m3/d) | Mob/Demob Strategy | Security Vessel
2018 | OGGS Clamp Installation and Trawl Cage Remediation | 2018 | 42 | H-Block | 12 h | Y | DSV | TBA | 26500 | Call off | 10 | No Charges | dedicated
BONGA
1 | 30M Bonga IWS (Diver + ROV) | 2018 | 60 | Bonga Field | 12/24hr | Y | DSV with ROV | Larissa/UTAI | 47000 | Call off | 10 | Charge for mob/demob | Pool
2 | 3D Inspection of Flex Joints | 2018 | 21 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
3 | In-Water Inspection (ROV) - BOORS | 2018 | 5 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
4 | Insp of Bonga Water Inj F/lines (WFL1, WFL2, WFL3 & WFL4) | 2018 | 5 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
5 | BOOR Screening/Integrity and Fatigue Assessment | 2018 | 16 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
6 | Annual Riser ROV Inspection (Depth <100M) | 2018 | 15 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
7 | Diver Survey (Hang off/Flex Joint) | 2018 | 10 | Bonga Field | 12h | Y | DSV | Jascon 65 | 12000 | Call off | 5 | Charge for mob/demob | Pool
132
BONNY
1 | SPM buoys change-out at BOGT end 2018. | 2018 | 30 | Bonny Field | 12h/24hrs | Y | DSV | HD PIONEER | 70000 | L/Sum | Inclussive
2 | 3M Bonny SPMs/PLEMS Inspections & Recycling | 2018 | 84 | Bonny Field | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
3 | 6M Bonny SPMs/PLEMS Inspections & Recycling | 2018 |  | Bonny Field | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
4 | 12M Bonny SPMs/PLEMS Inspections & Recycling | 2018 |  | Bonny Field | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
5 | Bonny SPM 1 Floating and subsea hoses replacement | 2018 | 16 | Bonny Field | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
6 | Bonny SPM 3 Floating and subsea hoses replacement | 2018 | 16 | Bonny Field | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
7 | Bonny SPM 2 Subsea / T/R and FOB hoses replacement. | 2018 | 16 | Bonny Field | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
8 | Bonny grommet replacement - 3 SPMs | 2018 | 3 | Bonny Field | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
9 | Anode survey/Replacment - 3 SPMs | 2018 | 6 | Bonny Field | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
10 | PLEM and Underbuoy Marine growth/Barnacles removal - 3 SPMs | 2018 | 12 | Bonny Field | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
11 | Anchor Pile Inspections. - 3 SPMs | 2018 | 6 | Bonny Field | 12h | Y | DSV | TBC | 26500 | Call off | 9
12 | Bonny CLP structures underwater inspections, CP and wall thickness measurement. | 2018 | 25 | Bonny Field | 12h | Y | DSV/JUB | TBC | 26500 | Call off | 9
179
FORCADOS
1 | 3M Forcados SPMs/PLEMS Inspections & Recycling | 2018 | 56 | Forcados | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
2 | 6M Forcados SPMs/PLEMS Inspections & Recycling | 2018 |  | Forcados | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
3 | 12M Forcados SPMs/PLEMS Inspections & Recycling | 2018 |  | Forcados | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
4 | Forcados SPM 1 Subsea and floating hoses replacement. | 2018 | 16 | Forcados | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
5 | Forcados SPM 2 Subsea and floating hoses replacement. | 2018 | 16 | Forcados | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
6 | Forcados grommet replacement - 2 SPMs | 2018 | 2 | Forcados | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
7 | Forcados Helideck refurbishment work. | 2018 |  | Forcados | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
8 | Anode survey/Replacment - 2 SPMs | 2018 | 4 | Forcados | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
9 | PLEM and Underbuoy Marine growth/Barnacles removal - 2 SPMs | 2018 | 8 | Forcados | 12h | Y | DSV | MV Melody | 25719 | Call off | 9
10 | Anchor Pile Inspections. | 2018 | 4 | Forcados | 12h | Y | DSV | TBC | 26500 | Call off | 9
106
459

## 2019
DSV OPTIMIZATION IN SCIN
SEA EAGLE
item | Project | Year | duration | Location | Working Schedule | IAP (Y/N) | Vessel Required | Past Vessel Used | Daily Rate (only Vessel) | Contract Type | Fuel (m3/d) | Mob/Demob Strategy | Security Vessel
2 | Underwater Inspection(Riser | 2019 | 35 | EA Field | 12h | Y | DSV | Jascon 55 | 40000 | Call off | 5 | Charge for mob/demob | Pool
3 | Free Span Rectification | 2019 | 20 | EA Field | 12h | Y | DSV | Jascon 55 | 40000 | Call off | 5 | Charge for mob/demob | Pool
4 | 30M EA IWS (Diver + ROV) | 2019 | 75 | EA Field | 12hr | Y | DSV with ROV | LARISSA | 47000 | Call off | 8 | Charge for mob/demob | Pool
130
BONGA
2 | 30M Bonga IWS (Diver + ROV) | 2019 | 40 | Bonga Field | 12/24hr | Y | DSV with ROV | Larissa/UTAI | 47000 | Call off
11 | BOOR Screening/Integrity and Fatigue Assessment | 2019 | 16 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 10 | Charge for mob/demob | Pool
12 | In-Water Inspection (ROV) - BOORS Pressure Test | 2019 | 10 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 10 | Charge for mob/demob | Pool
13 | In-Water Inspection (ROV) - BOORS | 2019 | 5 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 10 | Charge for mob/demob | Pool
14 | Annual Riser ROV Inspection (Depth <100M) | 2019 | 15 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 10 | Charge for mob/demob | Pool
9 | 3D Inspection of Flex Joints | 2019 | 21 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 10 | Charge for mob/demob | Pool
107
BONNY
| 3M Bonny SPMs/PLEMS Inspections & Recycling | 2019 | 84 | Bonny Field | 12h | Y | DSV | TBC | 26500 | Call off | 9
| 6M Bonny SPMs/PLEMS Inspections & Recycling | 2019 |  | Bonny Field | 12h | Y | DSV | TBC | 26500 | Call off | 9
| 12M Bonny SPMs/PLEMS Inspections & Recycling | 2019 |  | Bonny Field | 12h | Y | DSV | TBC | 26500 | Call off | 9
| Bonny grommet replacement - 3 SPMs | 2019 | 3 | Bonny Field | 12h | Y | DSV | TBC | 26500 | Call off | 9
| Anode survey/Replacment - 3 SPMs | 2019 | 6 | Bonny Field | 12h | Y | DSV | TBC | 26500 | Call off | 9
| PLEM and Underbuoy Marine growth/Barnacles removal - 3 SPMs | 2019 | 12 | Bonny Field | 12h | Y | DSV | TBC | 26500 | Call off | 9
102
FORCADOS
| 3M Forcados SPMs/PLEMS Inspections & Recycling | 2019 | 56 | Forcados | 12h | Y | DSV | TBC | 26500 | Call off | 9
| 6M Forcados SPMs/PLEMS Inspections & Recycling | 2019 |  | Forcados | 12h | Y | DSV | TBC | 26500 | Call off | 9
| 12M Forcados SPMs/PLEMS Inspections & Recycling | 2019 |  | Forcados | 12h | Y | DSV | TBC | 26500 | Call off | 9
| Forcados grommet replacement - 2 SPMs | 2019 | 2 | Forcados | 12h | Y | DSV | TBC | 26500 | Call off | 9
| Anode survey/Replacment - 2 SPMs | 2019 | 4 | Forcados | 12h | Y | DSV | TBC | 26500 | Call off | 9
| PLEM and Underbuoy Marine growth/Barnacles removal - 2 SPMs | 2019 | 8 | Forcados | 12h | Y | DSV | TBC | 26500 | Call off | 9
| SPM buoys change-out at FOT end 2019. | 2019 | 30 | Forcados | 12h/24H | Y | DSV | HYDRODIVE | 70000 | L/Sum | 9
100
439

## 2020
DSV OPTIMIZATION IN SCIN
BONGA
item | Project | Year | duration | Location | Working Schedule | IAP (Y/N) | Vessel Required | Past Vessel Used | Daily Rate (only Vessel) | Contract Type | Fuel (m3/d) | Mob/Demob Strategy | Security Vessel
1 | 3D Inspection of Flex Joints | 2020 | 21 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
2 | In-Water Inspection (ROV) - BOORS | 2020 | 5 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
3 | BOOR Screening/Integrity and Fatigue Assessment | 2020 | 16 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
4 | Annual Riser ROV Inspection (Depth <100M) | 2020 | 15 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
57
BONNY
1 | 3M Bonny SPMs/PLEMS Inspections & Recycling | 2020 | 84 | Bonny Field | 12h | Y | DSV | TBC | 26500 | Call off | 9
2 | 6M Bonny SPMs/PLEMS Inspections & Recycling | 2020 |  | Bonny Field | 12h | Y | DSV | TBC | 26500 | Call off | 9
3 | 12M Bonny SPMs/PLEMS Inspections & Recycling | 2020 |  | Bonny Field | 12h | Y | DSV | TBC | 26500 | Call off | 9
4 | Bonny SPM 1/2&3 T/R and FOB hoses replacement. | 2020 | 9 | Bonny Field | 12h | Y | DSV | TBC | 26500 | Call off | 9
5 | Bonny grommet replacement - 3 SPMs | 2020 | 3 | Bonny Field | 12h | Y | DSV | TBC | 26500 | Call off | 9
6 | Anode survey/Replacment - 3 SPMs | 2020 | 6 | Bonny Field | 12h | Y | DSV | TBC | 26500 | Call off | 9
7 | PLEM and Underbuoy Marine growth/Barnacles removal - 3 SPMs | 2020 | 12 | Bonny Field | 12h | Y | DSV | TBC | 26500 | Call off | 9
111
FORCADOS
1 | 3M Forcados SPMs/PLEMS Inspections & Recycling | 2020 | 56 | Forcados | 12h | Y | DSV | TBC | 26500 | Call off | 9
2 | 6M Forcados SPMs/PLEMS Inspections & Recycling | 2020 |  | Forcados | 12h | Y | DSV | TBC | 26500 | Call off | 9
3 | 12M Forcados SPMs/PLEMS Inspections & Recycling | 2020 |  | Forcados | 12h | Y | DSV | TBC | 26500 | Call off | 9
4 | Forcados SPM 1 &2& T/R and FOB hoses replacement. | 2020 | 8 | Forcados | 12h | Y | DSV | TBC | 26500 | Call off | 9
5 | Forcados grommet replacement - 2 SPMs | 2020 | 2 | Forcados | 12h | Y | DSV | TBC | 26500 | Call off | 9
6 | Anode survey/Replacment - 2 SPMs | 2020 | 4 | Forcados | 12h | Y | DSV | TBC | 26500 | Call off | 9
7 | PLEM and Underbuoy Marine growth/Barnacles removal - 2 SPMs | 2020 | 8 | Forcados | 12h | Y | DSV | TBC | 26500 | Call off | 9
78
246

## SCHEDULE 2018
CRITICAL 2018 DSV ACTIVITIES.
item | Project | Year | duration | Location | Comments
1 | OGGS Clamp Installation and Trawl Cage Remediation | 2018-09-01 | 42 | H-Block
2 | Anchor Pile Inspections. - 3 SPMs | 2018-09-01 | 6 | Bonny Field
3 | Anchor Pile Inspections. 2 spms | 2018-09-01 | 4 | Forcados
4 | Bonny CLP structures underwater inspections, CP and wall thickness measurement. | 2018-10-01 | 25 | Bonny Field
5 | 30M Bonga IWS (Diver + ROV) | NOV 18 - DEC 2019 | 60 | Bonga Field
6 | 30M EA IWS (Diver + ROV) | Q1 - 19 | 75 | EA Field | Move to 2018
7 | Sea Eagle – Leg Repair | 2018-11-01 | TBA | EA FIELD