## Sheet1
ACTIONS FROM 08/06/2018 GMP CADENCE
S/N | ACTION | S/N | PLAN/RESPONSE | Comment /Date
A | Review the implication of the withdrawal of Pergasus by Miden and revert during the next session. | 1 | Impact on OGGS H-Block repair works with uncertainty of condition of trawl cage
|  | 2 | The Bonga IWS and Pit stop work scheduled from October/ November will require to source alternative vessel.
|  | 3 | Environmental Monitoring soil Sampling work in EA field may not be executed as planned without an alternative vessel.
|  | 4 | EA IWS may not hold this year as being planned.
|  | 5 | Long deviated anchor pile inspection in Bonny and Forcados SPMs will remain deviated.
|  | 6 | Bonny CLP Underwater inspection will remain unexecuted.
|  | 7 | There will be low confidence trusting Miden on his promises.
|  | 8 | Will require looking elsewhere for sourcing alternative vessel at existing market rates
|  | 9 | Will give credence to the call for contract rate review
B | Provide a back-up plan in lieu of vessel availability. | 1 | Prioritize pending activities according to criticality and schedule for the next 6 months to one year. | 21/06/2018
|  | 2 | Engage NAPIMS to secure support to action either of the following: | 26-28/06/2018
a. Latch on the reimbursable elements of either MIDEN or HYPROPS contract to source for a vessel directly from the market.
b. To do selective tendering targetting vessel owners that are ready to use.
|  | 3 | Engage other IOCs at Top Management level for any free time on their DSVs with adequate capability. | TBA
|  | 4 | Maintain a form of SLA with the owners of DSV Melody for intervention supports in Bonny and Forcados. | Immedate
C | Provide clear articulation of support required from Andy regarding engagement with Antony Ellis | i | Required Support from Anthony Elis is for a dedicated Category Manager to handle should-cost modelling for a std DSV. Chioma Okpechi is willing to support but lacks resource to give urgent attention.