## Sheet1
ACTION PLAN FOR ESTIMATING THE PRICE TO BE DELIVERED FROM THE DIVING VESSEL STANDARDIZATION.
S/N | ACTION PLAN | START | FINISH | ACTION PARTY | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2
1 | Engage IAP team for activities download. | 2018-04-06 | 2018-12-06 | Eustace/IAP Team
2 | Review for completeness and schedule the sequence | 13/06/201 | 15/06/2018 | IAP team/JB/Executors.
3 | Establish the total vesel demand | 15/06/2018 | 18/06/2018 | Eustace
4 | Engage Activity Executors to provide special DSV features/ equipment to satisfy need. | 2018-11-06 | 15/06/2018 | Eustace
5 | Conduct market pricing survey and determine "Should-cost" for a Standard DSV. | 2018-11-06 | 21/06/2018 | Aage/JB/Pius Okeadinma
6 | Benchmark the should-cost against the cost of the std DSV at current Contract rate. | 22/06/18 | 26/06/18 | Olatunbosun/ Aage
7 | Benchmark the Cost of the Std DSV against cost of DSVs currently in service. | 22/06/18 | 26/06/18 | Eustace/ Aage
8 | Estimate the fixed cost of upgrading the Contractor's DSV to the required standard above the contract specification. 29/06/2017. | 26/06/2018 | 29/06/2018 | Eustace/Contractor/Akinyemi.
9 | Calculate the price to be delivered. . | 2018-01-07 | 2018-02-07 | Bosun