## Schedule
ACTIVITY SCHEDULE | [5 empty] | Construction Schedule Template © 2017 by Vertex42.com | [47 empty] | [42]
DSV PICASSO
Project Start: |  |  | 2019-04-18
Show Week: |  |  | 1 | time axis 2019-04-18 to 2020-04-23
[6 empty] | 18 Ap 19 | 25 Ap 19 | 2 Ma 19 | 9 Ma 19 | 16 Ma 19 | 23 Ma 19 | 30 Ma 19 | 6 Ju 19 | 13 Ju 19 | 20 Ju 19 | 27 Ju 19 | 4 Ju 19 | 11 Ju 19 | 18 Ju 19 | 25 Ju 19 | 1 Au 19 | 8 Au 19 | 15 Au 19 | 22 Au 19 | 29 Au 19 | 5 Se 19 | 12 Se 19 | 19 Se 19 | 26 Se 19 | 3 Oc 19 | 10 Oc 19 | 17 Oc 19 | 24 Oc 19 | 31 Oc 19 | 7 No 19 | 14 No 19 | 21 No 19 | 28 No 19 | 5 De 19 | 12 De 19 | 19 De 19 | 26 De 19 | 2 Ja 20 | 9 Ja 20 | 16 Ja 20 | 23 Ja 20 | 30 Ja 20 | 6 Fe 20 | 13 Fe 20 | 20 Fe 20 | 27 Fe 20 | 5 Ma 20 | 12 Ma 20 | 19 Ma 20 | 26 Ma 20 | 2 Ap 20 | 9 Ap 20 | 16 Ap 20 | 23 Ap 20
LOCN | TASK DESCRIPTION | PLAN DAYS | PLAN START | PLAN END | READY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
CONFIRMED SCOPE |  |  | 2019-04-18 | 2019-12-25
BONNY SPM (1,2,3) | Anchor Chain Inspection + CM on SPM1 (replace broken "cactus - spike" ) | 7 | 2019-04-19 | 2019-04-26 | G
FORC SPM (1,2) | Anchor Chain Inspection | 5 | 2019-04-27 | 2019-05-02 | G
OGGS Leak --Ph1 | Pre-inspection , Preparatory works ( Trawl cage remediation,DMAs, Chaining the cage, cut members) | 2 | 2019-05-03 | 2019-05-05 | G
Sea Eagle | In-Water Survey (Class Cert) | 60 | 2019-05-06 | 2019-07-05 | O | 2019-06-20: ◄ Latest Permissible Start
OGGS Leak --Ph2 | Clamp Installation | 22 | 2019-07-06 | 2019-07-28 | O
EA RISER | Underwater Inspection(Riser at EA Field) | 40 | 2019-07-29 | 2019-09-07 | X
BONNY SPM (1,2,3) | 6M Structural Underwater Inspections | 63 | 2019-09-08 | 2019-11-10 | G
FORC SPM (1,2) | 6M Structural Underwater Inspections | 44 | 2019-11-11 | 2019-12-25 | G
ADDITIONAL SCOPE ( TBC)
Free Span Rectification (OGGS) |  | 20 |  |  | x
Divers Hang-off Inspection at Bonga |  | 10 |  |  | x
FSPM 1 Buoy Change-out |  | ? |  |  | x
Forcados CLP remedial works |  | ? |  |  | x
Sea Eagle SYMP repairs |  | ? |  |  | x
Boat Catcher Removal at DPA | Surface diving requirement to remove existing boat catcher at DPA to enable Drilling by SHENGLI in early Jul '19 | 8 | 2019-06-24 | 2019-07-01
Boat Catcher Removal at DPB | Surface diving requirement to remove existing boat catcher at DPB to enable Drilling by SHENGLI in Dec '19 | 8 | 2019-12-25 | 2020-01-02
Boat Catcher Re-installation at DPA | Surface diving requirement to reinstate boat catcher at DPA post Drilling by SHENGLI Rig. | 10 | 2020-01-04 | 2020-01-13
Boat Catcher Re-installation at DPB | Surface diving requirement to reinstate boat catcher at DPB post Drilling by SHENGLI Rig. | 10 | 2020-05-15 | 2020-05-24
Insert new rows ABOVE this one
Construction Schedule Template © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/construction-schedule.html
Note on F7: TYPE: This column is set up to allow you to change the colors of the bar charts. Default (blank) = Gray B = Blue G = Green R = Red Y = Yellow O = Orange P = Purple X = Black

## Readiness
READINESS FACTORS (Y/N)
LOCN | TASK DESCRIPTION | PLAN START | PLAN DAYS | READINESS | DIVE CONTRACT | DIVE PROCEDURE | WORK SCOPE FIRM | MATERIALS READY | IAP ( ANY REQD SHUTDOWNS FIRMED)
BONNY SPM (1,2,3) | Anchor Chain Inspection + CM on SPM1 (replace broken "cactus - spike" ) | 2019-04-19 | 7 |  | Y | Y | Y | Y | NA
FORC SPM (1,2) | Anchor Chain Inspection | 2019-04-27 | 5
OGGS Leak --Ph1 | Pre-inspection , Preparatory works ( Trawl cage remediation,DMAs, Chaining the cage, cut members) | 2019-05-03 | 2
Sea Eagle | In-Water Survey (Class Cert) | 2019-05-06 | 60
OGGS Leak --Ph2 | Clamp Installation | 2019-07-06 | 22
EA RISER | Underwater Inspection(Riser at EA Field) | 2019-07-29 | 40
BONNY SPM (1,2,3) | 6M Structural Underwater Inspections | 2019-09-08 | 63
FORC SPM (1,2) | 6M Structural Underwater Inspections | 2019-11-11 | 44
ADDITIONAL SCOPE ( TBC) | 0 | 0 | 0
Free Span Rectification (OGGS) | 0 | 0 | 20
Divers Hang-off Inspection at Bonga | 0 | 0 | 10
FSPM 1 Buoy Change-out | 0 | 0 | ?
Forcados CLP remedial works | 0 | 0 | ?
Sea Eagle SYMP repairs | 0 | 0 | ?

## Help
HELP
https://www.vertex42.com/ExcelTemplates/construction-schedule.html
© 2017 Vertex42 LLC
About
This construction schedule was designed to provide an extremely simple way to create a professional-looking construction schedule. The bars in the gantt chart are created automatically using conditional formatting. Other formatting is up to you.
Want more features?
Get Gantt Chart Template Pro for Excel
Adding More Rows
When you insert new rows, you should insert a blank row between rows that have the formatting you want. If you do that, the formatting will be copied automatically.
Enter Text Within the Gantt Chart
This template was designed to allow you to enter text within the gantt chart area, but that text does not move if you adjust the start/end dates.
The text characters ▲ ▼ ◄ ► can be useful if you are adding text within the gantt chart area. Hint: If you want to use these characters frequently, you could add Autocorrect options via File > Options > Proofing to automatically convert (<<-) into ◄ and (->>) into ►.
You can add shape objects and text boxes in Excel by going to Insert > Shapes, so what you can do to label your construction schedule is almost limitless. However, adding text boxes and shapes is a manual process and the objects won't move if you adjust the start/end dates.
Adding More Columns to the Gantt Chart
If you want to increase the time span shown in chart, you can copy the last column in the gantt chart and then paste the copied column to the right of the gantt chart.
Changing the Bar Colors
The TYPE column can be used to choose a color for the bars in the schedule. If you want to change how this columns works, you will need to edit the conditional formatting rules.
Conditional Formatting
If you want to edit the colors used in the gantt chart, you will need to edit the conditional formatting rules.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.

## ©
Construction Schedule Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/construction-schedule.html
© 2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet. If necessary, you may hide it by right-clicking on the tab and selecting Hide.

## Schedule UPDATED
ACTIVITY SCHEDULE | [5 empty] | Construction Schedule Template © 2017 by Vertex42.com | [47 empty] | [42]
DSV PICASSO
Project Start: |  |  | 2019-05-03
Show Week: |  |  | 1 | time axis 2019-05-03 to 2020-05-08
[6 empty] | 3 Ma 19 | 10 Ma 19 | 17 Ma 19 | 24 Ma 19 | 31 Ma 19 | 7 Ju 19 | 14 Ju 19 | 21 Ju 19 | 28 Ju 19 | 5 Ju 19 | 12 Ju 19 | 19 Ju 19 | 26 Ju 19 | 2 Au 19 | 9 Au 19 | 16 Au 19 | 23 Au 19 | 30 Au 19 | 6 Se 19 | 13 Se 19 | 20 Se 19 | 27 Se 19 | 4 Oc 19 | 11 Oc 19 | 18 Oc 19 | 25 Oc 19 | 1 No 19 | 8 No 19 | 15 No 19 | 22 No 19 | 29 No 19 | 6 De 19 | 13 De 19 | 20 De 19 | 27 De 19 | 3 Ja 20 | 10 Ja 20 | 17 Ja 20 | 24 Ja 20 | 31 Ja 20 | 7 Fe 20 | 14 Fe 20 | 21 Fe 20 | 28 Fe 20 | 6 Ma 20 | 13 Ma 20 | 20 Ma 20 | 27 Ma 20 | 3 Ap 20 | 10 Ap 20 | 17 Ap 20 | 24 Ap 20 | 1 Ma 20 | 8 Ma 20
LOCN | TASK DESCRIPTION | PLAN DAYS | PLAN START | PLAN END | READY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
CONFIRMED SCOPE |  |  | 2019-05-03 | 2020-03-07
BONNY SPM (1,2,3) | Anchor Chain Inspection + CM on SPM1 (replace broken "cactus - spike" ) | 7 | 2019-05-04 | 2019-05-11 | G
FORC SPM (1,2) | Anchor Chain Inspection | 5 | 2019-05-12 | 2019-05-17 | G
OGGS Leak --Ph1 | Pre-inspection , Preparatory works ( Trawl cage remediation,DMAs, Chaining the cage, cut members) | 2 | 2019-05-18 | 2019-05-20 | G
Sea Eagle | In-Water Survey (Class Cert) | 60 | 2019-05-21 | 2019-07-20 | O | 2019-07-05: ◄ Latest Permissible Start
OGGS Leak --Ph2 | Clamp Installation | 22 | 2019-07-21 | 2019-08-12 | O
EA RISER | Underwater Inspection(Riser at EA Field) | 40 | 2019-08-13 | 2019-09-22 | X
Boat Catcher Removal at DPA | Surface diving requirement to remove existing boat catcher at DPA to enable Drilling by SHENGLI in early Jul '19 | 8 | 2019-09-07 | 2019-09-15
Bonny CLP | Underwater structural inspection | 31 | 2019-09-17 | 2019-10-18 | G
BONNY SPM (1,2,3) | 6M Structural Underwater Inspections | 63 | 2019-10-19 | 2019-12-21 | G
FORC SPM (1,2) | 6M Structural Underwater Inspections | 44 | 2019-12-23 | 2020-02-05 | G
Boat Catcher Removal at DPB | Surface diving requirement to remove existing boat catcher at DPB to enable Drilling by SHENGLI in Dec '19 | 8 | 2020-02-06 | 2020-02-14
Boat Catcher Re-installation at DPA | Surface diving requirement to reinstate boat catcher at DPA post Drilling by SHENGLI Rig. | 10 | 2020-02-15 | 2020-02-25
Boat Catcher Re-installation at DPB | Surface diving requirement to reinstate boat catcher at DPB post Drilling by SHENGLI Rig. | 10 | 2020-02-26 | 2020-03-07
ADDITIONAL SCOPE ( TBC)
Free Span Rectification (OGGS) |  | 20 |  |  | x
Divers Hang-off Inspection at Bonga |  | 10 |  |  | x
FSPM 1 Buoy Change-out |  | ? |  |  | x
Forcados CLP remedial works |  | ? |  |  | x
Sea Eagle SYMP repairs |  | ? |  |  | x
Insert new rows ABOVE this one
Construction Schedule Template © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/construction-schedule.html
Note on F7: TYPE: This column is set up to allow you to change the colors of the bar charts. Default (blank) = Gray B = Blue G = Green R = Red Y = Yellow O = Orange P = Purple X = Black

## Help (2)
HELP
https://www.vertex42.com/ExcelTemplates/construction-schedule.html
© 2017 Vertex42 LLC
About
This construction schedule was designed to provide an extremely simple way to create a professional-looking construction schedule. The bars in the gantt chart are created automatically using conditional formatting. Other formatting is up to you.
Want more features?
Get Gantt Chart Template Pro for Excel
Adding More Rows
When you insert new rows, you should insert a blank row between rows that have the formatting you want. If you do that, the formatting will be copied automatically.
Enter Text Within the Gantt Chart
This template was designed to allow you to enter text within the gantt chart area, but that text does not move if you adjust the start/end dates.
The text characters ▲ ▼ ◄ ► can be useful if you are adding text within the gantt chart area. Hint: If you want to use these characters frequently, you could add Autocorrect options via File > Options > Proofing to automatically convert (<<-) into ◄ and (->>) into ►.
You can add shape objects and text boxes in Excel by going to Insert > Shapes, so what you can do to label your construction schedule is almost limitless. However, adding text boxes and shapes is a manual process and the objects won't move if you adjust the start/end dates.
Adding More Columns to the Gantt Chart
If you want to increase the time span shown in chart, you can copy the last column in the gantt chart and then paste the copied column to the right of the gantt chart.
Changing the Bar Colors
The TYPE column can be used to choose a color for the bars in the schedule. If you want to change how this columns works, you will need to edit the conditional formatting rules.
Conditional Formatting
If you want to edit the colors used in the gantt chart, you will need to edit the conditional formatting rules.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.

## © (2)
Construction Schedule Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/construction-schedule.html
© 2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet. If necessary, you may hide it by right-clicking on the tab and selecting Hide.