## Sheet1
DSV OPTIMIZATION IN SCIN
SEA EAGLE
item | Project | Year | duration | Estimated Start | Estimated Finish | Location | Working Schedule | IAP (Y/N) | Vessel Required | Past Vessel Used | Daily Rate (only Vessel) | Contract Type | Fuel (m3/d) | Mob/Demob Strategy | Security Vessel
1 | OGGS Clamp Installation and Trawl Cage Remediation | 2018 | 42 | 2018-02-20 | 2018-04-03 | H-Block | 12 h | Y | DSV | N/A | 26500 | Call off | 10 | No Charges | dedicated
2 | Underwater Inspection(Riser | 2019 | 35 | 2019-03-01 | 2019-04-05 | EA Field | 12h | Y | DSV | Jascon 55 | 40000 | Call off | 5 | Charge for mob/demob | Pool
3 | Free Span Rectification | 2019 | 20 | 2019-04-06 | 2019-04-26 | EA Field | 12h | Y | DSV | Jascon 55 | 40000 | Call off | 5 | Charge for mob/demob | Pool
4 | 30M EA IWS (Diver + ROV) | 2019 | 75 | 2019-12-02 | 30/04/2019 | EA Field | 12hr | Y | DSV with ROV | MV Melody/UTAI | 26000 | Call off | 8 | Charge for mob/demob | Pool
BONGA
1 | 30M Bonga IWS (Diver + ROV) | 2018 | 60 | 2018-01-11 | 31/12/2018 | Bonga Field | 12/24hr | Y | DSV with ROV | Larissa/UTAI | 47000 | Call off | 10 | Charge for mob/demob | Pool
2 | 30M Bonga IWS (Diver + ROV) | 2019 | 40 | 2019-01-01 | 2019-09-22 | Bonga Field | 12/24hr | Y | DSV with ROV | Larissa/UTAI | 47000 | Call off | 10 | Charge for mob/demob | Pool
3 | 3D Inspection of Flex Joints | 2018 | 21 | 2018-01-17 | 2018-02-07 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
4 | In-Water Inspection (ROV) - BOORS | 2018 | 5 | 2018-03-07 | 2018-03-11 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
5 | Diver Survey (Hang off/Flex Joint) | 2018 | 10 | 2018-02-02 | 2018-02-12 | Bonga Field | 12h | Y | DSV | Jascon 65 | 12000 | Call off | 5 | Charge for mob/demob | Pool
6 | Insp of Bonga Water Inj F/lines (WFL1, WFL2, WFL3 & WFL4) | 2018 | 5 | 2018-04-05 | 2018-04-09 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
7 | BOOR Screening/Integrity and Fatigue Assessment | 2018 | 16 | 2018-04-12 | 2018-04-27 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
8 | Annual Riser ROV Inspection (Depth <100M) | 2018 | 15 | 2018-05-07 | 2018-05-21 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
9 | 3D Inspection of Flex Joints | 2019 | 21 | 2019-01-17 | 2019-02-07 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
10 | Diver Survey (Hang off/Flex Joint) | 2019 | 10 | 2019-02-03 | 2019-02-13 | Bonga Field | 12h | Y | DSV | Jascon 65 | 12000 | Call off | 5 | Charge for mob/demob | Pool
11 | BOOR Screening/Integrity and Fatigue Assessment | 2019 | 16 | 2019-02-07 | 2019-02-22 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
12 | In-Water Inspection (ROV) - BOORS Pressure Test | 2019 | 10 | 2019-03-03 | 2019-03-12 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
13 | In-Water Inspection (ROV) - BOORS | 2019 | 5 | 2019-05-18 | 2019-05-22 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
14 | Annual Riser ROV Inspection (Depth <100M) | 2019 | 15 | 2019-06-07 | 2019-06-21 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
15 | 3D Inspection of Flex Joints | 2020 | 21 | 2020-01-17 | 2020-02-07 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
16 | In-Water Inspection (ROV) - BOORS | 2020 | 5 | 2020-05-07 | 2020-05-11 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
17 | BOOR Screening/Integrity and Fatigue Assessment | 2020 | 16 | 2020-05-07 | 2020-05-22 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
18 | Diver Survey (Hang off/Flex Joint) | 2020 | 10 | 2020-02-03 | 2020-02-13 | Bonga Field | 12h | Y | DSV | Jascon 65 | 12000 | Call off | 5 | Charge for mob/demob | Pool
19 | Annual Riser ROV Inspection (Depth <100M) | 2020 | 15 | 2020-11-07 | 2020-11-21 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
BONNY
FORCADOS
ENGINEERING MATRIX
1 | SPM Buoy Change-out | 2019 | 21 | 2019-05-10 | 2019-10-31 | SPM-1 | 24h | N | HD Pioneer + ROV | HD Pioneer | Lumpsum | Lumpsum | N/A | Lumpsum | Pool
DWP
Formulas:
Estimated Finish = [duration]+[Estimated Start]
Estimated Finish = [Estimated Start]+[duration]-1

## DATA
DSV OPTIMIZATION IN SCIN
SEA EAGLE
item | Project | Year | duration | Estimated Start | Estimated Finish | Location | Working Schedule | IAP (Y/N) | Vessel Required | Past Vessel Used | Daily Rate (only Vessel) | Contract Type | Fuel (m3/d) | Mob/Demob Strategy | Security Vessel
2018 | OGGS Clamp Installation and Trawl Cage Remediation | 2018 | 42 | 2018-02-20 | 2018-04-03 | H-Block | 12 h | Y | DSV | N/A | 26500 | Call off | 10 | No Charges | dedicated
2 | Underwater Inspection(Riser | 2019 | 35 | 2019-03-01 | 2019-04-05 | EA Field | 12h | Y | DSV | Jascon 55 | 40000 | Call off | 5 | Charge for mob/demob | Pool
3 | Free Span Rectification | 2019 | 20 | 2019-04-06 | 2019-04-26 | EA Field | 12h | Y | DSV | Jascon 55 | 40000 | Call off | 5 | Charge for mob/demob | Pool
4 | 30M EA IWS (Diver + ROV) | 2019 | 75 | 2019-12-02 | 30/04/2019 | EA Field | 12hr | Y | DSV with ROV | MV Melody/UTAI | 26000 | Call off | 8 | Charge for mob/demob | Pool
BONGA
1 | 30M Bonga IWS (Diver + ROV) | 2018 | 60 | 2018-01-11 | 31/12/2018 | Bonga Field | 12/24hr | Y | DSV with ROV | Larissa/UTAI | 47000 | Call off | 10 | Charge for mob/demob | Pool
2 | 30M Bonga IWS (Diver + ROV) | 2019 | 40 | 2019-01-01 | 2019-09-22 | Bonga Field | 12/24hr | Y | DSV with ROV | Larissa/UTAI | 47000 | Call off | 10 | Charge for mob/demob | Pool
3 | 3D Inspection of Flex Joints | 2018 | 21 | 2018-01-17 | 2018-02-07 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
4 | In-Water Inspection (ROV) - BOORS | 2018 | 5 | 2018-03-07 | 2018-03-11 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
5 | Diver Survey (Hang off/Flex Joint) | 2018 | 10 | 2018-02-02 | 2018-02-12 | Bonga Field | 12h | Y | DSV | Jascon 65 | 12000 | Call off | 5 | Charge for mob/demob | Pool
6 | Insp of Bonga Water Inj F/lines (WFL1, WFL2, WFL3 & WFL4) | 2018 | 5 | 2018-04-05 | 2018-04-09 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
7 | BOOR Screening/Integrity and Fatigue Assessment | 2018 | 16 | 2018-04-12 | 2018-04-27 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
8 | Annual Riser ROV Inspection (Depth <100M) | 2018 | 15 | 2018-05-07 | 2018-05-21 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
9 | 3D Inspection of Flex Joints | 2019 | 21 | 2019-01-17 | 2019-02-07 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
10 | Diver Survey (Hang off/Flex Joint) | 2019 | 10 | 2019-02-03 | 2019-02-13 | Bonga Field | 12h | Y | DSV | Jascon 65 | 12000 | Call off | 5 | Charge for mob/demob | Pool
11 | BOOR Screening/Integrity and Fatigue Assessment | 2019 | 16 | 2019-02-07 | 2019-02-22 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
12 | In-Water Inspection (ROV) - BOORS Pressure Test | 2019 | 10 | 2019-03-03 | 2019-03-12 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
13 | In-Water Inspection (ROV) - BOORS | 2019 | 5 | 2019-05-18 | 2019-05-22 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
14 | Annual Riser ROV Inspection (Depth <100M) | 2019 | 15 | 2019-06-07 | 2019-06-21 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
15 | 3D Inspection of Flex Joints | 2020 | 21 | 2020-01-17 | 2020-02-07 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
16 | In-Water Inspection (ROV) - BOORS | 2020 | 5 | 2020-05-07 | 2020-05-11 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
17 | BOOR Screening/Integrity and Fatigue Assessment | 2020 | 16 | 2020-05-07 | 2020-05-22 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
18 | Diver Survey (Hang off/Flex Joint) | 2020 | 10 | 2020-02-03 | 2020-02-13 | Bonga Field | 12h | Y | DSV | Jascon 65 | 12000 | Call off | 5 | Charge for mob/demob | Pool
19 | Annual Riser ROV Inspection (Depth <100M) | 2020 | 15 | 2020-11-07 | 2020-11-21 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
BONNY
FORCADOS
ENGINEERING MATRIX
1 | SPM Buoy Change-out | 2019 | 21 | 2019-05-10 | 2019-10-31 | SPM-1 | 24h | N | HD Pioneer + ROV | HD Pioneer | Lumpsum | Lumpsum | N/A | Lumpsum | Pool
DWP
Formulas:
Estimated Finish = [duration]+[Estimated Start]
Estimated Finish = [Estimated Start]+[duration]-1

## 2018
DSV OPTIMIZATION IN SCIN
SEA EAGLE
item | Project | Year | duration | Estimated Start | Estimated Finish | Location | Working Schedule | IAP (Y/N) | Vessel Required | Past Vessel Used | Daily Rate (only Vessel) | Contract Type | Fuel (m3/d) | Mob/Demob Strategy | Security Vessel
2018 | OGGS Clamp Installation and Trawl Cage Remediation | q1/q2 | 42 | 2018-02-20 | 2018-04-03 | H-Block | 12 h | Y | DSV | TBA | 26500 | Call off | 10 | No Charges | dedicated
BONGA
1 | 30M Bonga IWS (Diver + ROV) | 2018 | 60 | 2018-01-11 | 31/12/2018 | Bonga Field | 12/24hr | Y | DSV with ROV | Larissa/UTAI | 47000 | Call off | 10 | Charge for mob/demob | Pool
3 | 3D Inspection of Flex Joints | 2018 | 21 | 2018-01-17 | 2018-02-07 | Bonga Field | 24 h | Y | MPV with ROV | Mien Merline | 56000 | Call off | 12 | Charge for mob/demob | Pool
4 | In-Water Inspection (ROV) - BOORS | 2018 | 5 | 2018-03-07 | 2018-03-11 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
6 | Insp of Bonga Water Inj F/lines (WFL1, WFL2, WFL3 & WFL4) | 2018 | 5 | 2018-04-05 | 2018-04-09 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
7 | BOOR Screening/Integrity and Fatigue Assessment | 2018 | 16 | 2018-04-12 | 2018-04-27 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
8 | Annual Riser ROV Inspection (Depth <100M) | 2018 | 15 | 2018-05-07 | 2018-05-21 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
62
5 | Diver Survey (Hang off/Flex Joint) | 2018 | 10 | 2018-02-02 | 2018-02-12 | Bonga Field | 12h | Y | DSV | Florence | 12000 | Call off | 5 | Charge for mob/demob | Pool
BONNY
Ongoing
Completed
Still in plan
Asigned
FORCADOS
ENGINEERING MATRIX
DWP
Formulas:
Estimated Finish = [duration]+[Estimated Start]
Estimated Finish = [Estimated Start]+[duration]-1

## 2019
DSV OPTIMIZATION IN SCIN
SEA EAGLE
item | Project | Year | duration | Estimated Start | Estimated Finish | Location | Working Schedule | IAP (Y/N) | Vessel Required | Past Vessel Used | Daily Rate (only Vessel) | Contract Type | Fuel (m3/d) | Mob/Demob Strategy | Security Vessel
1 | OGGS Clamp Installation and Trawl Cage Remediation | Q1 | 42 | 2018-02-20 | 2018-04-03 | H-Block | 12 h | Y | DSV | TBA | 26500 | Call off | 10 | No Charges | dedicated
2 | Underwater Inspection(Riser | 2019 | 35 | 2019-03-01 | 2019-04-05 | EA Field | 12h | Y | DSV | Jascon 55 | 40000 | Call off | 5 | Charge for mob/demob | Pool
3 | Free Span Rectification (OGGS) | 2019 | 20 | 2019-04-06 | 2019-04-26 | EA Field | 12h | Y | DSV | Jascon 55 | 40000 | Call off | 5 | Charge for mob/demob | Pool
97
SEA EAGLE
1 | 30M EA IWS (Diver + ROV) | 2019 | 75 | 2019-12-02 | 30/04/2019 | EA Field | 12hr | Y | DSV with ROV | LARISSA | 47000 | Call off | 8 | Charge for mob/demob | Pool
75
BONGA
1 | BOOR Screening/Integrity and Fatigue Assessment | 2019 | 16 | 2019-02-07 | 2019-02-22 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
2 | In-Water Inspection (ROV) - BOORS Pressure Test | 2019 | 10 | 2019-03-03 | 2019-03-12 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
3 | In-Water Inspection (ROV) - BOORS | 2019 | 5 | 2019-05-18 | 2019-05-22 | Bonga Field | 24h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
4 | Annual Riser ROV Inspection (Depth <100M) | 2019 | 15 | 2019-06-07 | 2019-06-21 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
5 | 3D Inspection of Flex Joints | 2019 | 21 | 2019-01-17 | 2019-02-07 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
6 | 30M Bonga IWS (Diver + ROV) | 2019 | 40 | 2019-01-01 | 2019-09-22 | Bonga Field | 12/24hr | Y | DSV with ROV | Larissa/UTAI | 47000 | Call off
107
FORCADOS
1 | SPM Buoy Change-out | 2019 | 21 | 2019-05-10 | 2019-10-31 | SPM-1 | 24h | N | HD Pioneer + ROV | HD Pioneer | Lumpsum | Lumpsum | N/A | Lumpsum | Pool
2 | 6M SPM Structural Underwater Inspections SPM 1 and 2 | 2019 | 44 | 2019-01-01 | 2019-09-22 | Bonga Field | 12/24hr | Y | DSV with ROV | Larissa/UTAI | 47000 | Call off
3 | 7 Yearly SPM 1 Subsea hoses Changeout | 2019 | 24
4 | 1 Yearly Anchor Chains/ CP Surveys | 2019 | 15
104
BONNY
1 | 3Y FOB/TR and 7Y Subsea hoses changeout for BSPM2 | 2019 | 27
2 | 6M SPM Structural Underwater Inspections 3 SPMs | 2019 | 63
3 | 1 Yearly Anchor Chains/ CP Surveys | 2019 | 18
| TOTAL DEMAND BASED ON AVAILABLE DATA |  | 383
Formulas:
Estimated Finish = [duration]+[Estimated Start]
Estimated Finish = [Estimated Start]+[duration]-1

## 2020
DSV OPTIMIZATION IN SCIN
SEA EAGLE
item | Project | Year | duration | Estimated Start | Estimated Finish | Location | Working Schedule | IAP (Y/N) | Vessel Required | Past Vessel Used | Daily Rate (only Vessel) | Contract Type | Fuel (m3/d) | Mob/Demob Strategy | Security Vessel
15 | 3D Inspection of Flex Joints | 2020 | 21 | 2020-01-17 | 2020-02-07 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
16 | In-Water Inspection (ROV) - BOORS | 2020 | 5 | 2020-05-07 | 2020-05-11 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
17 | BOOR Screening/Integrity and Fatigue Assessment | 2020 | 16 | 2020-05-07 | 2020-05-22 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
19 | Annual Riser ROV Inspection (Depth <100M) | 2020 | 15 | 2020-11-07 | 2020-11-21 | Bonga Field | 24 h | Y | MPV with ROV | African Vision | 56000 | Call off | 12 | Charge for mob/demob | Pool
57
FORCADOS
| 6M SPM Structural Underwater Inspections 3 SPMs | 2020 | 40
| 1 Yearly Anchor Chains/ CP Surveys | 2020 | 15
55
BONNY
| 6M SPM Structural Underwater Inspections 3 SPMs | 2020 | 60
| 1 Yearly Anchor Chains/ CP Surveys | 2020 | 21
81
| TOTAL DEMAND BASED ON AVAILABLE DATA |  | 193
Formulas:
Estimated Finish = [duration]+[Estimated Start]
Estimated Finish = [Estimated Start]+[duration]-1

## BONNY 2018-2023
OPERATOR/COMPANY NAME: BNY UNDERWATER MAINTENANCE
FORECAST PERIOD (18-23):
DATE OF COMPLETION OF TEMPLATE:
S/N | PROJECT DESCRIPTION | PROJECT LOCATION | No of SPMS | PROJECTED TIMELINE (MM/YY) | DURATION (Days)//SPM | TOTAL TIME/LOCN | VESSEL TYPE REQUIRED | VESSEL SPECIFICATION | NUMBER REQUIRED
6 MONTHLY INSPECTIONS DEC 2018
| 6M SPM PLEM CAMERON BALL VLV INSP - BNC | Bonny SPM offshore | 3 | 2018-12-01 | 3 | 9 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - BNCLP | Bonny SPM offshore | 3 | 2018-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - BN | Bonny SPM offshore | 3 | 2018-12-01 | 6 | 18 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - BN | Bonny SPM offshore | 3 | 2018-12-01 | 0.5 | 1.5 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - BNCLP | Bonny SPM offshore | 3 | 2018-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - BNCLP | Bonny SPM offshore | 3 | 2018-12-01 | 0.5 | 1.5 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | 3 | 2018-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| TOTAL FOR 6 MONTHS IMR WORKS IN 2018 |  |  |  | 16 | 48
ANNUAL INSPECTIONS DEC 2018
| 1Y SPM ANCHOR PILES INSPECTION - BNCLP | Bonny SPM offshore | 3 | 2018-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | 3 | 2018-12-01 | 3 | 9 | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM CATHODIC PROTECTION INSP - BNCLP | Bonny SPM offshore | 3 | 2018-12-01 | 3 | 9 | Diving Support Vessel | DP2 capable vessel | 1
| 3Y SPM1 MOORING HAWSER CHANGEOUT | Bonny SPM offshore | 1 | 2018-12-01 | 1 | 1 | Diving Support Vessel | DP2 capable vessel | 1
| TOTAL FOR ANNUAL IMRs |  |  |  | 8 | 25
| TOTAL VESSEL DEMAND IN 2018 |  |  |  |  | 73
7 YEARLY SUBSEA HOSE CHANGEOUT JAN 2019
| 7Y SBM3 SUBSEA HOSESTRINGI CHANGEOUT - | Bonny SPM offshore | 1 | 2019-01-01 | 24 | 24 | Diving Support Vessel | DP2 capable vessel | SPM3 INSPECTION
| 3Y SBM3 FOB/ TANKER RAIL HOSE CHANGEOUT - | Bonny SPM offshore | 1 | 2019-01-01 | 2 | 2 | Diving Support Vessel | DP2 capable vessel | SPM3 INSPECTION
26
CLP UNDERWATER INSPECTION DEC JUN 2019
| BONNY CLP UNDERWATER STRUCTURE INSPECTION | Bonny SPM offshore | 1 | 2019-06-01 | 30 | 30 | Self Elevating Work Over Platform | DP2 capable vessel | JUB
SIX MONTHLY INSPECTIONS JUNE 2019
| 6M SPM PLEM CAMERON BALL VLV INSP - BNC | Bonny SPM offshore | 3 | 2019-06-01 | 1 | 3 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - BNCLP | Bonny SPM offshore | 3 | 2019-06-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - BN | Bonny SPM offshore | 3 | 2019-06-01 | 3 | 9 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - BN | Bonny SPM offshore | 3 | 2019-06-01 | 0.5 | 1.5 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - BNCLP | Bonny SPM offshore | 3 | 2019-06-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - BNCLP | Bonny SPM offshore | 3 | 2019-06-01 | 0.5 | 1.5 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | 3 | 2019-06-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
33
7 YEARLY FLOATING HOSES CHANGEOUT JAN 2019
| 7Y SBM2 SUBSEA HOSESTRINGI CHANGEOUT - | Bonny SPM offshore | 1 | 2019-06-01 | 24 | 24 | Diving Support Vessel | DP2 capable vessel | 1
| 3Y SBM2 FOB/ TR HOSE CHANGEOUT - | Bonny SPM offshore | 1 | 2019-01-01 | 3 | 3 | Diving Support Vessel | DP2 capable vessel | 1
27
6 MONTHLY INSPECTIONS DEC 2019
| 6M SPM PLEM CAMERON BALL VLV INSP - BNC | Bonny SPM offshore | 3 | 2019-12-01 | 1 | 3 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - BNCLP | Bonny SPM offshore | 3 | 2019-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - BN | Bonny SPM offshore | 3 | 2019-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - BN | Bonny SPM offshore | 3 | 2019-12-01 | 0.5 | 1.5 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - BNCLP | Bonny SPM offshore | 3 | 2019-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - BNCLP | Bonny SPM offshore | 3 | 2019-12-01 | 0.5 | 1.5 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | 3 | 2019-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
30
ANNUAL INSPECTIONS OF ANCHOR PILES DEC 19
| 1Y SPM ANCHOR PILES INSPECTION - BNCLP | Bonny SPM offshore | 3 | 2019-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | 3 | 2019-12-01 | 3 | 9 | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM CATHODIC PROTECTION INSP - BNCLP | Bonny SPM offshore | 3 | 2019-12-01 | 1 | 3 | Diving Support Vessel | DP2 capable vessel | 1
18
6 MONTHLY INSPECTIONS JUN 2020
| 6M SPM PLEM CAMERON BALL VLV INSP - BNC | Bonny SPM offshore | 3 | 2020-06-01 | 1 | 3 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - BNCLP | Bonny SPM offshore | 3 | 2020-06-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - BN | Bonny SPM offshore | 3 | 2020-06-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - BN | Bonny SPM offshore | 3 | 2020-06-01 | 0.5 | 1.5 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - BNCLP | Bonny SPM offshore | 3 | 2020-06-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - BNCLP | Bonny SPM offshore | 3 | 2020-06-01 | 0.5 | 1.5 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | 3 | 2020-06-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
30
SIX MONTHLY INSPECTIONS DEC 2020
| 6M SPM PLEM CAMERON BALL VLV INSP - BNC | Bonny SPM offshore | 3 | 2020-12-01 | 1 | 3 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - BNCLP | Bonny SPM offshore | 3 | 2020-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - BN | Bonny SPM offshore | 3 | 2020-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - BN | Bonny SPM offshore | 3 | 2020-12-01 | 0.5 | 1.5 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - BNCLP | Bonny SPM offshore | 3 | 2020-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - BNCLP | Bonny SPM offshore | 3 | 2020-12-01 | 0.5 | 1.5 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | 3 | 2020-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
30
ANNUAL INSPECTIONS DEC 2020
| 1Y SPM ANCHOR PILES INSPECTION - BNCLP | Bonny SPM offshore | 3 | 2020-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | 3 | 2020-12-01 | 3 | 9 | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM CATHODIC PROTECTION INSP - BNCLP | Bonny SPM offshore | 3 | 2020-12-01 | 2 | 6 | Diving Support Vessel | DP2 capable vessel | 1
21
81
MOORING HAWSER CHANGEOUT JAN 2021
| 3Y SPM1 MOORING HAWSER CHANGEOUT | Bonny SPM offshore | 1 | 2021-01-01 | 2 | 2 | Diving Support Vessel | DP2 capable vessel | 1
6 MONTHLY INSPECTIONS 2021
| 6M SPM PLEM CAMERON BALL VLV INSP - BNC | Bonny SPM offshore | Diving | 2021-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - BNCLP | Bonny SPM offshore | Diving | 2021-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - BN | Bonny SPM offshore | Diving | 2021-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - BN | Bonny SPM offshore | Diving | 2021-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - BNCLP | Bonny SPM offshore | Diving | 2021-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - BNCLP | Bonny SPM offshore | Diving | 2021-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | Diving | 2021-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
6 monthly inspections December 2021
| 6M SPM PLEM CAMERON BALL VLV INSP - BNC | Bonny SPM offshore | Diving | 2021-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - BNCLP | Bonny SPM offshore | Diving | 2021-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - BN | Bonny SPM offshore | Diving | 2021-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - BN | Bonny SPM offshore | Diving | 2021-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - BNCLP | Bonny SPM offshore | Diving | 2021-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - BNCLP | Bonny SPM offshore | Diving | 2021-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | Diving | 2021-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
Annual activities Dec 2021
| 1Y SPM ANCHOR PILES INSPECTION - BNCLP | Bonny SPM offshore | Diving | 2021-12-01 | 12 |  | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | Diving | 2021-12-01 | 6 |  | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM CATHODIC PROTECTION INSP - BNCLP | Bonny SPM offshore | Diving | 2021-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
3 YEARLY CHANGEOUT DEC 2021
| 3Y SPM2 MOORING HAWSER CHANGEOUT | Bonny SPM offshore | Diving | 2021-12-01 | 2 |  | Diving Support Vessel | DP2 capable vessel | 1
| 3Y SPM3 MOORING HAWSER CHANGEOUT | Bonny SPM offshore | Diving | 2021-12-01 | 2 |  | Diving Support Vessel | DP2 capable vessel | 1
| 3Y SBM1 SUPERSAMSON HOSE CHANGEOUT - | Bonny SPM offshore | Diving | 2021-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 3Y SBM1 TANKER RAIL HOSE CHANGEOUT - | Bonny SPM offshore | Diving | 2021-12-01 | 2 |  | Diving Support Vessel | DP2 capable vessel | 1
| 5Y SBM1 MARINE BREAKAWAY CPLG CHGEOUT- | Bonny SPM offshore | Diving | 2022-05-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 5Y SBM2 MARINE BREAKAWAY CPLG CHGEOUT- | Bonny SPM offshore | Diving | 2022-05-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
6 MONTHLY INSPECTION JUNE 2022
| 6M SPM PLEM CAMERON BALL VLV INSP - BNC | Bonny SPM offshore | Diving | 2022-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - BNCLP | Bonny SPM offshore | Diving | 2022-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - BN | Bonny SPM offshore | Diving | 2022-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - BN | Bonny SPM offshore | Diving | 2022-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - BNCLP | Bonny SPM offshore | Diving | 2022-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - BNCLP | Bonny SPM offshore | Diving | 2022-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | Diving | 2022-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
6 monthly inspections Dec 2022
| 6M SPM PLEM CAMERON BALL VLV INSP - BNC | Bonny SPM offshore | Diving | 2022-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - BNCLP | Bonny SPM offshore | Diving | 2022-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - BN | Bonny SPM offshore | Diving | 2022-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - BN | Bonny SPM offshore | Diving | 2022-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - BNCLP | Bonny SPM offshore | Diving | 2022-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - BNCLP | Bonny SPM offshore | Diving | 2022-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | Diving | 2022-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
Annual Inspections DEC 20122
| 1Y SPM ANCHOR PILES INSPECTION - BNCLP | Bonny SPM offshore | Diving | 2022-12-01 | 12 |  | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | Diving | 2022-12-01 | 6 |  | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM CATHODIC PROTECTION INSP - BNCLP | Bonny SPM offshore | Diving | 2022-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
3YEARLY INSPECTIONS DEC 2022
| 3Y SBM2 SUPERSAMSON HOSE CHANGEOUT - | Bonny SPM offshore | Diving | 2022-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 3Y SBM3 SUPERSAMSON HOSE CHANGEOUT - | Bonny SPM offshore | Diving | 2022-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 3Y SBM2 TANKER RAIL HOSE CHANGEOUT - | Bonny SPM offshore | Diving | 2022-12-01 | 2 |  | Diving Support Vessel | DP2 capable vessel | 1
| 3Y SBM3 TANKER RAIL HOSE CHANGEOUT - | Bonny SPM offshore | Diving | 2022-12-01 | 2 |  | Diving Support Vessel | DP2 capable vessel | 1
6 MONTHLY INSPECTIONS DEC 2022
| 6M SPM PLEM CAMERON BALL VLV INSP - BNC | Bonny SPM offshore | Diving | 2023-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - BNCLP | Bonny SPM offshore | Diving | 2023-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - BN | Bonny SPM offshore | Diving | 2023-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - BN | Bonny SPM offshore | Diving | 2023-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - BNCLP | Bonny SPM offshore | Diving | 2023-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - BNCLP | Bonny SPM offshore | Diving | 2023-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | Diving | 2023-06-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
7 YEARLY FLOATING HOSESTRING CHANGEOUT JUNE 2023
| 7Y SBM2 FLOATING HOSESTRINGI CHANGEOUT - | Bonny SPM offshore | Diving | 2023-06-01 | 2 |  | Diving Support Vessel | DP2 capable vessel | 1
6 MONTHLY INSPECTIONS DEC 2023
| 6M SPM PLEM CAMERON BALL VLV INSP - BNC | Bonny SPM offshore | Diving | 2023-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - BNCLP | Bonny SPM offshore | Diving | 2023-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - BN | Bonny SPM offshore | Diving | 2023-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - BN | Bonny SPM offshore | Diving | 2023-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - BNCLP | Bonny SPM offshore | Diving | 2023-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - BNCLP | Bonny SPM offshore | Diving | 2023-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | Diving | 2023-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
Annual inspections 2023
| 1Y SPM ANCHOR PILES INSPECTION - BNCLP | Bonny SPM offshore | Diving | 2023-12-01 | 12 |  | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM ANCHORING CHAIN INSP & MTCE- BNC | Bonny SPM offshore | Diving | 2023-12-01 | 6 |  | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM CATHODIC PROTECTION INSP - BNCLP | Bonny SPM offshore | Diving | 2023-12-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
Note on B82: Chime, Eustace A SPDC-UPO/G/USMI:

## FORCADOS 2018-2023
OPERATOR/COMPANY NAME: FOT UNDERWATER MAINTENANCE
FORECAST PERIOD (2019 - 2024)
DATE OF COMPLETION OF TEMPLATE:
S/N | PROJECT DESCRIPTION | PROJECT LOCATION | No of SPMS | PROJECTED TIMELINE (MM/YY) | DURATION (Days)//SPM | TOTAL TIME/LOCN | VESSEL TYPE REQUIRED | VESSEL SPECIFICATION | NUMBER REQUIRED | SAP DATE
SIX MONTHLY INSPECTIONS DUE APRIL 2019
| 6M SPM PLEM CAMERON BALL VLV INSP - FOC | Forcados SPM offshore | 2 | 2019-04-04 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - FOCLP | Forcados SPM offshore | 2 | 2019-04-04 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - FO | Forcados SPM offshore | 2 | 2019-04-04 | 3 | 6 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - FO | Forcados SPM offshore | 2 | 2019-04-04 | 0.5 | 1 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - FOCLP | Forcados SPM offshore | 2 | 2019-04-04 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - FOCLP | Forcados SPM offshore | 2 | 2019-04-04 | 0.5 | 1 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | 2 | 2019-04-04 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
[5 empty] | 12 | 24
| 7Y SBM3 SUBSEA HOSESTRINGI CHANGEOUT - | Bonny SPM offshore | 1 | 2019-04-04 | 24 | 24 | Diving Support Vessel | DP2 capable vessel | 44
ANNUAL INSPECTIONS DUE APRIL 2019
| 1Y SPM ANCHOR PILES INSPECTION - FOCLP | Forcados SPM offshore | 2 | 2019-04-04 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | 2 | 2019-04-04 | 3.5 | 7 | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM CATHODIC PROTECTION INSP - FOCLP | Forcados SPM offshore | 2 | 2019-04-04 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
15
63
SIX MONTHLY ISPECTIONS DUE OCTOBER 2019
| 6M SPM PLEM CAMERON BALL VLV INSP - FOC | Forcados SPM offshore | 2 | 2019-10-01 | 1 | 2 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - FOCLP | Forcados SPM offshore | 2 | 2019-10-01 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - FO | Forcados SPM offshore | 2 | 2019-10-01 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - FO | Forcados SPM offshore | 2 | 2019-10-01 | 0.5 | 1 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - FOCLP | Forcados SPM offshore | 2 | 2019-10-01 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - FOCLP | Forcados SPM offshore | 2 | 2019-10-01 | 0.5 | 1 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | 2 | 2019-10-01 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
20
83
SIX MONTHLY INSPECTIONS DUE APRIL 2020
| 6M SPM PLEM CAMERON BALL VLV INSP - FOC | Forcados SPM offshore | 2 | 2020-04-04 | 1 | 2 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - FOCLP | Forcados SPM offshore | 2 | 2020-04-04 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - FO | Forcados SPM offshore | 2 | 2020-04-04 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - FO | Forcados SPM offshore | 2 | 2020-04-04 | 0.5 | 1 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - FOCLP | Forcados SPM offshore | 2 | 2020-04-04 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - FOCLP | Forcados SPM offshore | 2 | 2020-04-04 | 0.5 | 1 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | 2 | 2020-04-04 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
20
ANNUAL INSPECTIONS DUE APRIL 2020
| 1Y SPM ANCHOR PILES INSPECTION - FOCLP | Forcados SPM offshore | 2 | 2020-04-04 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | 2 | 2020-04-04 | 3.5 | 7 | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM CATHODIC PROTECTION INSP - FOCLP | Forcados SPM offshore | 2 | 2020-04-04 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
15
SIX MONTHLY ACTIVITIES DUE OCT 2020
| 6M SPM PLEM CAMERON BALL VLV INSP - FOC | Forcados SPM offshore | 2 | 2020-10-01 | 1 | 2 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - FOCLP | Forcados SPM offshore | 2 | 2020-10-01 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - FO | Forcados SPM offshore | 2 | 2020-10-01 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - FO | Forcados SPM offshore | 2 | 2020-10-01 | 0.5 | 1 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - FOCLP | Forcados SPM offshore | 2 | 2020-10-01 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - FOCLP | Forcados SPM offshore | 2 | 2020-10-01 | 0.5 | 1 | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | 2 | 2020-10-01 | 2 | 4 | Diving Support Vessel | DP2 capable vessel | 1
[5 empty] | 10 | 20
55
138
SIX MONTHLY ACTIVITIES DUE APRIL 21
| 6M SPM PLEM CAMERON BALL VLV INSP - FOC | Forcados SPM offshore | Diving | 2021-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - FOCLP | Forcados SPM offshore | Diving | 2021-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - FO | Forcados SPM offshore | Diving | 2021-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - FO | Forcados SPM offshore | Diving | 2021-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - FOCLP | Forcados SPM offshore | Diving | 2021-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - FOCLP | Forcados SPM offshore | Diving | 2021-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | Diving | 2021-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
ANNUAL ACTIVITIES DUE APRIL 2021
| 1Y SPM ANCHOR PILES INSPECTION - FOCLP | Forcados SPM offshore | Diving | 2021-04-04 | 12 |  | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | Diving | 2021-04-04 | 6 |  | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM CATHODIC PROTECTION INSP - FOCLP | Forcados SPM offshore | Diving | 2021-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| MOORING HAWSER CHANGE-OUT | Forcados SPM offshore | Diving | 2021-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
CHANGEOUT ACTIVITIES DUE JUNE 2021
| TANKER RAIL CHANGE-OUT | Forcados SPM offshore | Diving | 2021-06-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| SUPERSAMPSON CHANGE-OUT | Forcados SPM offshore | Diving | 2021-06-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
SIX MONTHLY INSPECTIONS DUE OCTOBER 2021
| 6M SPM PLEM CAMERON BALL VLV INSP - FOC | Forcados SPM offshore | Diving | 2021-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - FOCLP | Forcados SPM offshore | Diving | 2021-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - FO | Forcados SPM offshore | Diving | 2021-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - FO | Forcados SPM offshore | Diving | 2021-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - FOCLP | Forcados SPM offshore | Diving | 2021-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - FOCLP | Forcados SPM offshore | Diving | 2021-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | Diving | 2021-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
6 monthly inspections due APRIL 2021
| 6M SPM PLEM CAMERON BALL VLV INSP - FOC | Forcados SPM offshore | Diving | 2022-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - FOCLP | Forcados SPM offshore | Diving | 2022-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - FO | Forcados SPM offshore | Diving | 2022-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - FO | Forcados SPM offshore | Diving | 2022-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - FOCLP | Forcados SPM offshore | Diving | 2022-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - FOCLP | Forcados SPM offshore | Diving | 2022-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | Diving | 2022-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
ANNUAL INSPECTIONS DUE APRIL 2022
| 1Y SPM ANCHOR PILES INSPECTION - FOCLP | Forcados SPM offshore | Diving | 2022-04-04 | 12 |  | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | Diving | 2022-04-04 | 6 |  | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM CATHODIC PROTECTION INSP - FOCLP | Forcados SPM offshore | Diving | 2022-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
SIX MONTHLY INSPECTIONS DUE 2022
| 6M SPM PLEM CAMERON BALL VLV INSP - FOC | Forcados SPM offshore | Diving | 2022-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - FOCLP | Forcados SPM offshore | Diving | 2022-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - FO | Forcados SPM offshore | Diving | 2022-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - FO | Forcados SPM offshore | Diving | 2022-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - FOCLP | Forcados SPM offshore | Diving | 2022-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - FOCLP | Forcados SPM offshore | Diving | 2022-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | Diving | 2022-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
ANNUAL INSPECTIONS DUE APRIL 2023
| 6M SPM PLEM CAMERON BALL VLV INSP - FOC | Forcados SPM offshore | Diving | 2023-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - FOCLP | Forcados SPM offshore | Diving | 2023-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - FO | Forcados SPM offshore | Diving | 2023-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - FO | Forcados SPM offshore | Diving | 2023-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - FOCLP | Forcados SPM offshore | Diving | 2023-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - FOCLP | Forcados SPM offshore | Diving | 2023-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | Diving | 2023-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
ANNUAL INSPECTIONS DUE 2023
| 1Y SPM ANCHOR PILES INSPECTION - FOCLP | Forcados SPM offshore | Diving | 2023-04-04 | 12 |  | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | Diving | 2023-04-04 | 6 |  | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM CATHODIC PROTECTION INSP - FOCLP | Forcados SPM offshore | Diving | 2023-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
SIX MONTHLY INSPECTIONS DUE 2023
| 6M SPM PLEM CAMERON BALL VLV INSP - FOC | Forcados SPM offshore | Diving | 2023-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - FOCLP | Forcados SPM offshore | Diving | 2023-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - FO | Forcados SPM offshore | Diving | 2023-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - FO | Forcados SPM offshore | Diving | 2023-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - FOCLP | Forcados SPM offshore | Diving | 2023-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - FOCLP | Forcados SPM offshore | Diving | 2023-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | Diving | 2023-10-01 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
SIX MONTHLY INSPECTION DUE APRIL 2024
| 6M SPM PLEM CAMERON BALL VLV INSP - FOC | Forcados SPM offshore | Diving | 2024-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SUBSEA HOSE STRING INSP - FOCLP | Forcados SPM offshore | Diving | 2024-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PIPE LINE END MANIFOLD INSP - FO | Forcados SPM offshore | Diving | 2024-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM PLEM VALVE REMOTE UMBILICAL - FO | Forcados SPM offshore | Diving | 2024-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM SPAR BUOY INSP & MTCE PM - FOCLP | Forcados SPM offshore | Diving | 2024-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM UNDERBUOY 24/20" REDUCER - FOCLP | Forcados SPM offshore | Diving | 2024-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
| 6M SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | Diving | 2024-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
ANNUAL INSPECTIONS DUE APRIL 2024
| 1Y SPM ANCHOR PILES INSPECTION - FOCLP | Forcados SPM offshore | Diving | 2024-04-04 | 12 |  | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM offshore | Diving | 2024-04-04 | 6 |  | Diving Support Vessel | DP2 capable vessel | 1
| 1Y SPM CATHODIC PROTECTION INSP - FOCLP | Forcados SPM offshore | Diving | 2024-04-04 | 3 |  | Diving Support Vessel | DP2 capable vessel | 1
Note on C104: Chime, Eustace A SPDC-UPO/G/USMI:

## CRITICAL ACTIVITIES
DSV OPTIMIZATION IN SCIN
CRITICAL ACTIVITIES
item | Project | Year | duration | Estimated Start | Estimated Finish | Location | Working Schedule | IAP (Y/N) | Vessel Required | Past Vessel Used | Daily Rate (only Vessel) | Contract Type | Fuel (m3/d) | Mob/Demob Strategy | Security Vessel
2019 | BONNY/FORCADOS ANCHORE PILE INSPECTIONS | 2019 | 16 | 2019-01-15 | 2019-01-31 | BNY/FORC
2019 | OGGS Clamp Installation and Trawl Cage Remediation | 2019 | 42 | 2019-02-20 | 2019-04-03 | H-Block | 12 h | Y | DSV | POSH | 26500 | Call off | 10 | No Charges | dedicated
2019 | 30M EA IWS (Diver + ROV) | 2019 | 75 | 2019-12-02 | 30/04/2019 | EA Field | 12hr | Y | DSV with ROV | LARISSA | 47000 | Call off | 8 | Charge for mob/demob | Pool
2019 | Free Span Rectification (OGGS) | 2019 | 20 | 2019-04-06 | 2019-04-26 | EA Field | 12h | Y | DSV | Jascon 55 | 40000 | Call off | 5 | Charge for mob/demob | Pool
153
| COMPARATIVE VESSEL COST /IMPACTS |  | TOTAL | % Difference | AVAILABILITY | LOCATION
HYPROPS | YEUXEN OCEAN at $36,860pd |  | 5639580 |  | JUNE | CHINA
PETROLOG | Vinnice at $57,000pd + DIVE SPREAD $10.000 |  | 10251000 | 4611420 | TBC | MOBIL
MIDEN | Liechtenstein at $45,000pd |  | 6885000 | 1245420 | JAN/FEB | SINGAPORE
HYDRODIVE | HD Pioneer at $70,000p.d |  | 10710000 | 5070420 | JANUARY | BNY SPM 3
BONGA IWS | Olympic triton AT $56,000pd + Spread $10,000 |  | 10098000 | 4458420 | MAR/APR | BONGA IWS
OTHER VESSEL RATES OPERATING FOR OTHER IOCs
MOBIL | Evolution 808 at $80k pd
Formulas:
Estimated Finish = [duration]+[Estimated Start]

## FORCADOS 2018-2023 (2)
OPERATOR/COMPANY NAME: FOT UNDERWATER MAINTENANCE
FORECAST PERIOD (2019 - 2024)
DATE OF COMPLETION OF TEMPLATE:
S/N | PROJECT DESCRIPTION | PROJECT LOCATION | MARINE SERVICE REQUIRED | PROJECTED TIMELINE (MM/YY) | DURATION (Days) | SCOPE OF INSPECTION | SAP DATE
| 6M SPM PLEM CAMERON BALL VLV INSP - FOC | Forcados SPM 1&2offshore | Diving | 2019-04-04 | 3 | Including valve recycling, check actuators, clean marine growth around valve. Check connectors
| 6M SPM SUBSEA HOSE STRING INSP - FOCLP | Forcados SPM 1&2offshore | Diving | 2019-04-04 | 2 | Check configuration, check beads, clean marine growth, CVI, Flanges, etc
| 6M SPM PIPE LINE END MANIFOLD INSP - FO | Forcados SPM 1&2offshore | Diving | 2019-04-04 | 6 | Marine growth cleaning, Anodes Inspection, CVI
| 6M SPM PLEM VALVE REMOTE UMBILICAL - FO | Forcados SPM 1&2offshore | Diving | 2019-04-04 | 0.5 | GVI/CVI, Check brackets, check avaiability
| 6M SPM SPAR BUOY INSP & MTCE PM - FOCLP | Forcados SPM 1&2offshore | Diving | 2019-04-04 | 5 | Check centrality, check entanglement, remove marine growth
| 6M SPM UNDERBUOY 24/20" REDUCER - FOCLP | Forcados SPM 1&2offshore | Diving | 2019-04-04 | 0.5 | Clean marine growth and barnacles, CVI, Check Anodes, Sound compartments.
| 6M SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM 1&2offshore | Diving | 2019-04-04 | 3 | Chain Angles and Chain wear measurments
| 1Y SPM ANCHOR PILES INSPECTION - FOCLP | Forcados SPM 1&2offshore | Diving | 2019-04-04 | 4 | Plan for five years
| 1Y SPM ANCHORING CHAIN INSP & MTCE- FOC | Forcados SPM 1&2offshore | Diving | 2019-04-04 | 7 | Marine growth and barnacles removal, CVI at selected links from stopper to touchdown.
| 1Y SPM CATHODIC PROTECTION INSP - FOCLP | Forcados SPM 1&2offshore | Diving | 2019-04-04 | 4 | Conduct CP survey and retrofit depleted anodes.
| 5 yearly CLP structural underwater Inspections | Forcados SPM 1&2offshore | Diving | 2019-10-01 | 30 | Detailed statutory inspections
| 3Y TANKER RAIL AND fob Floating hoses replacement | Forcados SPM 1&2offshore | Diving | 2019-10-01 | 4 | Backflush, diconnection and replacement
| 7 YEARLY SUBSEA HOSES REPLACMENT | Forcados SPM 1&2offshore | Diving | 2019-10-01 | 24 | Backflush, diconnection and replacement
| 7 YEARLY FLOATING HOSES REPLACMENT | Forcados SPM 1&2offshore | Diving | 2019-10-01 | 3 | Backflush, diconnection and replacement
| 2 YEARLY GROMMET ROPES REPLACMENT. | Forcados SPM 1&2offshore | Diving | 2019-10-01 | 2 | Removal and replacement