## Sheet1
PROGRAM FOR EXECUTING CRITICAL INTEGRITY ASSURANCE WORKS.
S/N | ACTIVITY DESCRIPTION | START | END | DURATION (Days) | ACTION PARTY | COMMENTS
A | ANCHOR PILES INSPECTIONS
A1 | Secure MTB approval to engage Hydrodive for SPM Pile inspections. | 2018-08-10 | 2018-08-10 | 1 | Eustace/Sunny/Bunmi | Completed.
A2 | Agree duration and scope of the inspection with Hydrodive.
A3 | Write a letter to NAPIMS to fix a meeting.
A4 | Engage NAPIMS to secure their support.
A5 | Raise and Secure approval for E-ldl
A6 | Update ACV of Contract.
A7 | Issue PO to Contractor
A8 | Hydrodive completes Installation of BSPM 3
A9 | Execute Inspections in Bonny Field starting with BSPM 3
A10 | Transit to Forcados
A11 | Execute Inspections in Forcados Field.
A12 | Transit to Onne
B | CLP UNDERWATER INSPECTION
B1 | Engage Logistics for a Jackup Badge | 2018-12-10 |  |  | Daniel Okoye
B2 | Request CTR from Hydrodive and benchmark with Forcados CLP U/W Inspection CTR
B3 | Issue PO to HYPROPS
B4 | Carryout Assurances and pre-mob of equipments
B5 | Prepare Project Execution and diving plans.
B6 | Complete Review of PEP and Diving plans
B7 | Engineering demobilizes from the CLP site.
B8 | HYPROPS mobilizes to Site.
B9 | Execute CLP Underwater Inspection.
B10 | Demobilize Contractor from Site.
C | OGGS H-BLOCK REMEDIATION WORKS.
C1 | Secure MTB approval to renegotiate rate with Miden and HYPROPS | 2018-05-10 | 22/10/18 |  | Eustace/ Tobechukwu/ Jonathan Boyle
C2 | Negotiate rates with Both Contractors
C3 | Engage NAPIMS for Support
C4 | Raise E-LDL
C5 | Vary Contract in SAP.