## Sheet1
OGGS MOBILIZATION PLAN
Activity ID | Activity Name | ACTION PARTY | TARGET DATE | COMMENT
1 | Provide Technical Spec of Vessel and details of other project items to Debo for scouting prices and market rates. | Daniel Okoye/Alvaro Quintero | 28/09/2018
2 | Conduct market survey and do a should cost modelling of DSV and compare rates of all vessels proposed by Miden, hydrodive and Petrolog | Debo Ogunjimi/Chiedozie Ukeje | 03/10/2018
3 | Set up a meeting for Internal Alignment on Oct 4th 2018 for all rates and reimbursable items of H-Block Scope. | Alvaro Quintero | 28/09/2018
4 | Prepare and submit MTB submission seeking support to negotiate new rates and reimbursables. Action: | Chiedozie Ukeje/Alvaro | 04/10/2018
5 | Attend MTB meeting to secure approval to negotiate rates with Contractor: | Chiedozie Ukeje/Alvaro/Tony | 15/10/2018
6 | Notify NAPIMS and set up/hold negotiation meeting with Miden/ Subcontractors. | Alvaro Quintero | 18/10/18
7 | Submit to NAPIMS the rates agreed in the negotiation. Action: Alvaro. Date: 19/10/2018. | Alvaro Quintero | 19/10/2018.
8 | Place PO to Miden with negotiated rates for H-Block. Action: Alvaro Quintero. Date: 22/10/2018. | Alvaro Quintero | 22/10/2018.