## Sheet1
SPM 3 CHANGE OUT
Activity ID | Activity Name | Duration | Start | Finish | % Complete
S-2.1.0 Preliminary Activities |  | 5.2d | 2018-09-23 | 2018-09-28
SPM1000 | Surfer UTAH 17 arrives site | 0.0d |  | 2018-09-23 | 100%
SPM1010 | AHT takes tow rope from HD Pioneer | 0.3d | 2018-09-23 | 2018-09-23 | 100%
SPM1005 | AHT Al Harty Tide arrives site | 0.0d |  | 2018-09-23 | 100%
SPM1030 | Prepare and Carry out essential Drills including ERP | 0.8d | 2018-09-23 | 2018-09-24 | 100%
SPM1040 | Respool Old SP Winch wire | 1.0d | 2018-09-24 | 2018-09-25 | 100%
SPM1050 | inspect and restart New SPM winch | 1.0d | 2018-09-24 | 2018-09-25 | 100%
SPM1060 | Respool New SPM winch wire | 1.0d | 2018-09-25 | 2018-09-26 | 100%
SPM1070 | Load test Old SPM winch with A-frame | 1.0d | 2018-09-26 | 2018-09-27 | 0%
SPM1080 | Load test New SPM winch wire with A-frame | 1.0d | 2018-09-27 | 2018-09-28 | 0%
SPM1090 | Commence Survey activities | 0.0d | 2018-09-28 |  | 0%
S-2.2 MAIN OPERATIONS |  | 65.0d | 2018-09-28 | 2018-12-02
S-2.2.1 STAGE 1 ( REMOVAL OF OLD BUOY ) |  | 12.9d | 2018-09-28 | 2018-10-11
A1000 | Mesotech Survey 500m Zone | 3.0d | 2018-09-28 | 2018-10-01 | 0%
A1010 | AHT set up 2-point anchor heading 220, connect to new SPM 2 x hawsers | 0.8d | 2018-10-01 | 2018-10-01 | 0%
A1020 | Lower Chain 7, 4 to seabed | 1.1d | 2018-10-01 | 2018-10-03 | 0%
A1030 | Relocate Hang off Rigging Old SPM (8,3,2) | 1.1d | 2018-10-03 | 2018-10-04 | 0%
A1040 | Lift Chain by Old Winch (8,3,2) remove plug, transfer to hang off | 1.5d | 2018-10-04 | 2018-10-05 | 0%
A1050 | Disconnect chains 8,3 and 2 from rigging and lay on the seabed. | 1.5d | 2018-10-05 | 2018-10-07 | 0%
A1060 | Install towing rigging Old SPM | 0.8d | 2018-10-07 | 2018-10-07 | 0%
A1070 | Lower chain 1 to seabed | 0.5d | 2018-10-07 | 2018-10-08 | 0%
A1080 | Recover 3 x sets hang off rigging old SPM from skirt | 0.9d | 2018-10-08 | 2018-10-09 | 0%
A1090 | Recover all tools & rigging from old SPM to HDP | 0.3d | 2018-10-09 | 2018-10-09 | 0%
A1100 | AHT pick up anchors, relocate to connect to Old SPM, release mooring lines, tow old SPM | 1.5d | 2018-10-09 | 2018-10-11 | 0%
S-2.2.2 STAGE 2 ( INSTALLATION OF NEW BUOY ) |  | 9.0d | 2018-10-11 | 2018-10-20
A1110 | AHT set up 2-point anchor heading 220 of new SPM | 0.8d | 2018-10-11 | 2018-10-11 | 0%
A1120 | Rotate new SPM turn table | 0.3d | 2018-10-11 | 2018-10-12 | 0%
A1130 | Install long hang off rigging chain 6 new SPM | 0.5d | 2018-10-12 | 2018-10-12 | 0%
A1140 | Lower Chain 6 onto hang off rigging | 0.3d | 2018-10-12 | 2018-10-12 | 0%
A1150 | Connect AHT mooring hawsers to new SPM | 0.4d | 2018-10-12 | 2018-10-13 | 0%
A1160 | Pick up chains 1 and 3 from seabed and connect to hang off rigging new SPM. | 1.3d | 2018-10-13 | 2018-10-14 | 0%
A1170 | Connect to Chains 1 & 3, disconnect hang off rigging & pull through the stoppers new SPM | 1.1d | 2018-10-14 | 2018-10-15 | 0%
A1180 | Connect to Chain 6, disconnect hang off rigging & pull through the stoppers new SPM | 0.6d | 2018-10-15 | 2018-10-16 | 0%
A1200 | Disconnect BL212 hawsers from new SPM | 0.6d | 2018-10-16 | 2018-10-16 | 0%
A1210 | HDP picks up and install chain 2 | 0.8d | 2018-10-16 | 2018-10-17 | 0%
A1220 | HDP Picks up & Installs Chain 4 | 0.8d | 2018-10-17 | 2018-10-18 | 0%
A1230 | HDP Picks up & Installs Chain 7 | 0.8d | 2018-10-18 | 2018-10-19 | 0%
A1240 | HDP Picks up & Installs Chain 8 | 0.8d | 2018-10-19 | 2018-10-19 | 0%
A1250 | Turntable rotation test | 0.3d | 2018-10-19 | 2018-10-20 | 0%
S-2.2.3 DEPLOYMENT AND TIE-IN OF HOSE STRINGS |  | 34.4d | 2018-10-20 | 2018-11-23
S-2.2.3.1 DEPLOYMENT AND TIE-IN OF HOSE STRING #1 |  | 17.2d | 2018-10-20 | 2018-11-06
A1260 | Hose string connection hose 1 – 4 tie in on HDP deck | 1.5d | 2018-10-20 | 2018-10-21 | 0%
A1270 | Lower hose string to seabed & disconnect | 1.2d | 2018-10-21 | 2018-10-22 | 0%
A1280 | Securing Hose 1 Flange to PLEM flange No.1 | 12.0d | 2018-10-22 | 2018-11-03 | 0%
A1290 | Hose 4 connection to SPM underside flange No.1 | 2.5d | 2018-11-03 | 2018-11-06 | 0%
S-2.2.3.2 DEPLOYMENT AND TIE-IN OF HOSE STRING #2 |  | 17.2d | 2018-11-06 | 2018-11-23
A1300 | Hose string connection hose 1 – 4 tie in on HDP deck | 1.5d | 2018-11-06 | 2018-11-07 | 0%
A1310 | Lower hose string 2 to seabed & disconnect | 1.2d | 2018-11-07 | 2018-11-09 | 0%
A1320 | Securing Hose 1 Flange to PLEM flange No.2 | 12.0d | 2018-11-09 | 2018-11-21 | 0%
A1330 | Hose 4 connection to SPM underside flange No.2 | 2.5d | 2018-11-21 | 2018-11-23 | 0%
S-2.2.4 COMPLETION ACTIVITIES |  | 8.7d | 2018-11-23 | 2018-12-02
A1340 | Install Floating Hoses | 1.5d | 2018-11-23 | 2018-11-25 | 0%
A1350 | Hydrostatic leak test | 2.0d | 2018-11-25 | 2018-11-27 | 0%
A1360 | Install mooring hawsers | 1.5d | 2018-11-27 | 2018-11-28 | 0%
A1370 | Assist on Pre-commissioning | 1.0d | 2018-11-28 | 2018-11-29 | 0%
A1380 | As-Built video survey | 0.4d | 2018-11-29 | 2018-11-30 | 0%
A1390 | Recover temporary mooring | 0.3d | 2018-11-30 | 2018-11-30 | 0%
A1400 | HD Pioneer demobilises and transits to Lagos | 2.0d | 2018-11-30 | 2018-12-02 | 0%