## SPDC
SEPCiN 2017 Demand-led Integrated Planning - IS Detailed Deployment Roadmap
| Deliverables | SPDC Action Lead | SPDC Action Lead | Team Members | Due Date | Status | Comments | S |  |  |  | O |  |  |  | N |  |  |  | D
[8 empty] | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4
A.3. Implement Integrated Schedule concept to ensure disciplined execution of plans | A1 Cross Asset Activity Plan (All Hubs & Bonga) | Elo/Akaka/Chinedu |  | Chinedu/Akpe/ID/Moji/Oba/ Kareem/Ebiere | bar: S WK1 to N WK4
| A1.1 Send note to PUMs about deployment and seek support | Elo |  | Chinedu/Akpe/ID/Moji/Oba/ Kareem/Ebiere | bar: S WK2
| A1.2 General Schedulers and Asset Planners Engagements | Elo |  | Chinedu/Akpe/ID/Moji/Oba/ Kareem/Ebiere | bar: S WK2 to S WK3
| A1.3 Engage PUMs during their Monthly Connect | Elo/Akaka |  | Chinedu/Akpe/ID/Moji/Oba/ Kareem/Ebiere | bar: S WK4
| A3.2.4 Train Planners and Schedulers on Primavera (P6) and Impress | Chinedu |  | Moji/Elo | bar: S WK4 to N WK4
| A3.2.7 Train Super Users | Chinedu |  | Moji/Elo | bar: S WK4 to N WK4
| A2 Swamp East Hub IS Deployment | Elo/Moji/ Chinedu/Oba |  | ID/ Kareem/Ebiere | bar: S WK3 to D WK4
| A2.1 Set up Impress/P6 IS Layout | Chinedu/Moji |  | Elo | bar: S WK3
| A2.2 Review and deploy Template (Cut Over) | Chinedu/Moji |  | Akpe/ID/Oba/ Kareem/Ebiere | bar: S WK3
| A3.1.4 Implement IS and track embedment. | Moji/Elo |  | ID/Oba/Kareem/Ebiere/Chinedu | bar: S WK3
| A3.2.8 Monitor implementation/usage of IS through IS KPIs | Elo/Moji/ Oba |  | ID/Kareem/Ebiere/Chinedu | bar: S WK4 to D WK4
| A3 EA Hub IS Deployment | Elo/Akpe/ Chinedu/Oba/Moji |  | Chinedu/ID/Oba/ Kareem/Ebiere | bar: S WK4 to D WK4
| A3.1 Set up Impress/P6 IS Layout | Chinedu/Moji/Akpe |  | Elo | bar: S WK4
| A3.2 Review and deploy Template (Cut Over) | Elo/Chinedu/Moji/Akpe |  | ID/Oba/ Kareem/Ebiere | bar: S WK4
| A3.3 Implement IS and track embedment. | Akpe/Elo |  | ID/Oba/Kareem/Ebiere/Chinedu/ Moji | bar: S WK4
| A3.4 Monitor implementation/usage of IS through IS KPIs | Elo/Akpe/ Oba |  | ID/Kareem/Ebiere/Chinedu/Moji | bar: O WK1 to D WK4
| A4 Central Hub IS Deployment | Elo/ID/ Chinedu/Oba |  | Chinedu/Akpe/Moji/Oba/ Kareem/Ebiere | bar: O WK1 to D WK4
| A4.1 Set up Impress/P6 IS Layout | Chinedu/Moji/ID |  | Elo | bar: O WK1
| A4.2 Review and deploy Template (Cut Over) | Elo/Chinedu/Moji/ID |  | Akpe/Oba/ Kareem/Ebiere | bar: O WK1
| A4.3 Implement IS and track embedment. | ID/Elo |  | Moji/Oba/Kareem/Ebiere/Chinedu/ Akpe | bar: O WK1
| A4.4 Monitor implementation/usage of IS through IS KPIs | Elo/ID/ Oba |  | Moji/Kareem/Ebiere/Chinedu | bar: O WK2 to D WK4
| A5 Swamp West Hub IS Deployment | Elo/Moji/ Chinedu/Oba |  | ID/ Kareem/Ebiere | bar: O WK2 to D WK4
| A5.1 Set up Impress/P6 IS Layout | Chinedu/Moji |  | Elo | bar: O WK2
| A5.2 Review and deploy Template (Cut Over) | Elo/Chinedu/Moji |  | Akpe/ID/Oba/ Kareem/Ebiere | bar: O WK2
| A5.3 Implement IS and track embedment. | Moji/Elo |  | ID/Oba/Kareem/Ebiere/Chinedu | bar: O WK2
| A5.4 Monitor implementation/usage of IS through IS KPIs | Elo/Moji/ Oba |  | ID/Kareem/Ebiere/Chinedu | bar: O WK3 to D WK4
| A6 Land East Hub IS Deployment | Elo/ID/ Chinedu/Oba |  | Chinedu/Akpe/Moji/Oba/ Kareem/Ebiere | bar: O WK4 to D WK4
| A6.1 Set up Impress/P6 IS Layout | Chinedu/Moji/ID |  | Elo | bar: O WK4
| A6.2 Review and deploy Template (Cut Over) | Elo/Chinedu/Moji/ID |  | Akpe/Oba/ Kareem/Ebiere | bar: O WK4
| A6.3 Implement IS and track embedment. | ID/Elo |  | Moji/Oba/Kareem/Ebiere/Chinedu/ Akpe | bar: O WK4
| A6.4 Monitor implementation/usage of IS through IS KPIs | Elo/ID/ Oba |  | Moji/Kareem/Ebiere/Chinedu | bar: N WK1 to D WK4
| A7 Bonga IS Deployment | Elo/Kareem/ Chinedu/Oba |  | Chinedu/Akpe/Moji/Oba/ ID/Ebiere | bar: N WK1 to D WK4
| A7.1 Set up Impress/P6 IS Layout | Chinedu/Moji/Kareem |  | Elo/Ebiere | bar: N WK1
| A7.2 Review and deploy Template (Cut Over) | Chinedu/Moji/Kareem/Elo |  | Akpe/Oba/Ebiere | bar: N WK1
| A7.3 Implement IS and track embedment. | Kareem/Elo |  | Moji/Oba/ID/Ebiere/Chinedu/ Akpe | bar: N WK1
| A7.4 Monitor implementation/usage of IS through IS KPIs | Elo/Kareem/ Oba |  | Moji/ID/Ebiere/Chinedu | bar: N WK2 to D WK4
| A8 Review performance of IS implementation and seek improvement | Elo |  | Akpe/ID/Moji/Oba/Kareem/Ebiere | bar: N WK2 to D WK4
| A8.1 Develop schedule for IS implementation performance review | Elo |  | Akpe/ID/Moji/Oba/Ademola/Ebiere | bar: N WK3
| A8.2 Conduct Performance Review | Elo/ID/Moji/Kareem/Akpe |  | Oba/Ebiere | bar: N WK4 to D WK2
| A8.3 Implement performance review improvement outcomes and monitor performance | Elo/ID/Moji/Kareem/Akpe |  | Oba/Ebiere/Chinedu | bar: D WK3 to D WK4
On Track, No Significant Concerns
Completed
Progress behind Schedule, Intervention Required
On Track, No Significant Concerns
Progress behind Schedule, Intervention Required