## Slide 1: Initiative Update
  Separated Backlog liquidation and Cycle time reduction into two different initiatives.
  Completed the identification and ranking of opportunities for cycle time reduction.
  Secure Sponsor and LT alignment and support for Implementation plan starting 1st Dec 2020
  Engagement / alignment with Regulators (DPR and NOSDRA)
  Progress Initiative to L2.
  Contracts
    6 months Time extension (31/12/2020 to 30/06/2021) and Ceiling Increase on Existing Execution Mega Contract pending award of new contract
    Ceiling increase on existing Consultancy/Lab services Mega Contract to cater for increased scope of work in 2021
  New Technology
    Support (CAPEX) to acquire new technology for site assessments (geo probes and test kits etc) at circa $500k in 2021
Promise for next week
Support required/Key decisions
Last Week
Expected impact (Additional Budget)
2020: Nil
2021: ~$0.5m (Capex)
#I-0095405: Reduce SPDC Spill Remediation Cycle Time from avg.386 to less than 200days by Q4 2021

## Slide 2: Implementation Plan
Action/Milestone | Expected Cycle Time Reduction (days) | Who | When
1. Establish SOP to implement PCI for small volume <= 5bbls | 10 - 30 | Ivan Okoye | 15/01/2021
2. Create a workflow process for phase-2-phase handover of sites | 3 - 7 | Usman Anibasa | 11/12/2020
3. Merge the review and assurance processes of Phase 1 reports and RAP together | 15 - 30 | Ivan Okoye | 1/12/2020
4. Explore and deploy technology to improve PCI/Assessment and QAQC activities e.g. use of Geo-Probe and Field Test Kits | 3 - 14 | Sam Campbell | 31/03/2021
5. Prepare CTS dashboard to show compliance and share at weekly OSRR LT and monthly ER LT meeting | 7 - 14 | Sunkanmi Bisiriyu | 4/12/2020
6. Improve competence level of remediation contractors in planning and control system. | 7 - 14 | Sunkanmi Bisiriyu | 31/01/2021
7. Provide dedicated resources to enable prompt commencement of site certification immediately on completion of remediation | 30 - 60 | Pankyes Hirse | 01/12/2020
8. Secure Regular support (DPR and NOSDRA) and Implement risk based screening levels (RBSL) | 15 - 40 | Sam Campbell | 31/01/2021
9. Establish SOP for improved QA/QC and verification process | 15 - 40 | Sam Campbell | 4/12/2020
10. Secure Regulator support and SOP for use of Nutrients to aid Remediation Process (RENA) | 15 - 30 | Bruce | 31/01/2021

## Slide 3: Initiative Update
  Created initiative in Fit-4 (I-0096259)
  Established site prioritisation process for liquidation backlog implementation
  Established the clear resourced implementation plan to be active at a maximum of 60 sites starting 1st December 2020
  Secure Sponsor and LT alignment and support for Implementation plan starting 1st Dec 2020
  Secure outstanding critical resources for 1st December 2020 Implementation Plan
  Progress Initiative to L2.
  Decisions Already Made
    Support to commence Remediation E2E Activities (Assessments, Remediation and Certifications) at maximum of 60 sites starting 1st Dec 2020 up-to 31st Dec 2020.
    Additional budget of F$0.5m on top of 2020 budget to enable mobilisation and commencement of Remediation E2E activities from 1st Dec 2020
  Logistics, Security & CTS Support
    16nos Security escort teams (Men + accommodation + Vehicles)
    15 nos Vehicle + Driver for SPDC CSR
    Expedited CTS for 12 sites by 30th Nov 20
    1 nos Dedicated Surveyor from Geomatics
Promise for next week
Support required/Key decisions
Last Week
Expected impact (Additional Budget)
2020: $0.5m
2021: ~$6m
#I-0096259: Liquidate Remediation backlogs from 258 to Zero by Q4 2021

## Slide 4: OVERVIEW OF DECEMBER 1 PLAN AND CRITICAL RESOURCES
#I-0096259: Liquidate Remediation backlogs from 258 to Zero by Q4 2021

## Slide 5: 1ST DECEMBER 2020 BACKLOG LIQUIDATION PLAN
Ogale MF
K-Dere MF
12”
24”
Egbema MF
Assa MF
Rumuekpe MF
Okordia MF
Gbaran GP
Kolo Creek MF
Nun River MF
Diebu Creek MF
Nkpoku MF
Imo River II MF
Imo River I MF
Ebubu MF
10”
16”
20”
20”
18”
14”
18”
16”
36”
20”
36”
28”
12”
24”
28”
28”
6”
Obigbo FS
8”
Old KCTL
New KCTL
40”
30”
San Barth MF
Nembe Ck
Sego MF
Awoba MF
Krakama MF
CawC Jn MF
Belema FS
Oguta
Soku
11ICs
Isimiri FS
Pipeline Manifolds
Pipelines
LEGEND
Inactive IC
Active IC
Active IR
Destroyed IR
3
4
5
6
8
9
10
11
1
7
2
PCI: 1
REM: 4
CERT: 3
FLC: 3
PCI: 3
REM: 5
CERT: 6
PCI: 1
CERT: 1
PCI: 3
REM: 11
FLC: 3
PCI: 7
FLC: 2
PCI: 3
PCI: 1
PCI: 1
FLC: First Line Clean up
PCI: Post Clean Up Assessment
REM: Remediation
CERT: Certification
Total 17
Total 14
Total 8
Total 10
Total 5
Total 2
Grand Total: 60

## Slide 6: OSRR DECEMBER 2020 PLAN
Forcados Terminal
Brass Creek MF
Benisede MF
Opukushi MF
Ogbotobo
FS
Tunu FS
Agge BV
Excel
(3rd Party)
KM 0
12” x 11.7 Km
16” x 8.5km
20” x 19 Km
FLC: 2