## Slide 1: Priority 1 & 2 Opportunities Plan
Area | Opportunity | Priority | Possible Solutions | Action Party | LEC
Pre-Incident Activities | Have a stagging room to plan and respond to emergencies. | 1 | Allocate at least 2 rooms Fix arrival time per job | Cle | April 24
Resourcing | Logistics to get regulators. Request for nominated regulators | 1 | Logistics team to assign driver to pick regulators by 7:30am Regulators to nominate and share list of personnel | Cle | Mar 20
Documentation | Standardize request and approval process (BFM, materials, POs) for emergencies | 1 | Create a separate approval workflow for emergencies. | Ewos | May 31st
Execution | Quickly request and printing the POs. | 1 | Quick cost estimate review and PR approval. Automate process using power platforms | Ewos | May 31st
Payment/Close out | Raise umbrella emergency POs | 1 | Get approval to get generate umbrella PO | Ewos | May 31st
Documentation | Time to develop and review documentation | 1 | Standardize documentation based on location and risk profile | Iyare | May 10
 | Time lost due to local draining | 1 | Identify low points across the network and provide contingency plans for local draining | Iyare | April 30
Resourcing (Personnel and materials) | OSR (JIV): ability to support more than 5 sites at any time. | 1 | Increase capacity to support 7 sites by May 1st | Sir P | May 1st
 | Geomatics Can currently support 3 sites in a day across East and West. | 1 | Increase capacity to support 6 sites by May 31st | Uche | May 31st
 | Fire Team Land location: 12 sites (5 Water tankers currently available for land activities ). Swamp location: 4 sites (8 pumps) | 1 | Require more Hilux for land location activities Purchase extra 2 pumps to increase number of sites to 5. | Cle | August 31st
Execution (JIV and Repair) | Early pickup and arrival of regulators | 2 | Logistics team to assign driver to pick regulators by 7:30am Regulators to nominate and share list of personnel | Cle | Mar 20
 | Planned vs Emergency jobs for warehouse weekend activities. | 2 | Early communication to enable security grant access. Add warehouse duty manager to emails | Cle | Mar 20
 | Time to organize logistics | 2 | Plans should be firmed up the day before Drivers should be at meeting point by 7:30am | Cle | 

## Slide 2: Workshop Details
Summary Opportunity Identification |  |  |  |  |  | 
Note: Do not include solutions here! Priority level 1 is most important and 3 least important (High - > 6hrs, Medium 3 - 6 hrs, low < 3 hrs) |  |  |  |  |  | 
Ref# | Area | Opportunity/Defect | Ease of Implementation (High, Medium, Low) | Value (High, Medium, Low) | Priority Level (1 Hi Hi,2 Hi Me,3 ) | Possible Solution
1 | Pre-Incident Actvities | Have a stagging room to plan and respond to emergencies. | high | high - circa 1 day delay removed |  | 
2 |  | Set up a special team for emergencies. Including office, field and support personnel | low | Medium |  | 
3 |  | Carry out low point mapping for depressurisation; Terrain delineation (difficult, normal, medium); resources mapping | Medium | high |  | 
4 |  | Standardise CTS with the list of locations - | Low | high |  | Breakdown CTS components (FTO & community personnel)
5 |  | Capacity to respond when we have more than 6 incident sites per day. | Low | High |  | 
6 |  | Quick availability of resources for depressurisation - storage and reinjection capacity during network outage (Gbaran, Ebubu, Oghale, PWS) | Low | High |  | 
7 |  | Logistics to get regulators. Assigned regulators | high | High |  | 
8 |  | Standardise request and approval process (BFM, materials, POs) for emergencies | high | high - E&C implication |  | 
9 |  | Quickly request and printing the POs. | high | high - E&C implication |  | 
10 |  | Raise umbrella emergency POs | high | high - E&C implication & cycle time reduction |  | 
11 | Notification / Reporting |  |  |  |  | 
12 |  |  |  |  |  | 
13 |  |  |  |  |  | 
14 | Resourcing. Personnel and materials | Fire team Land location: 12 sites (5 Water tankers currently available for land activities ). Require more hilux for land location activities Swamp location: 4 sites (8 pumps) | Medium | high |  | 
15 |  | Geomatics Can support 3 sites in a day across East and West | low | high |  | 
 |  | OSR (JIV): 5 sites can be supported at once, at any time | high | high |  | 
16 |  | Security: Can support 3 locations (1 black 1 red for east and 1 for west) | low | high |  | 
17 | Documentation |  |  |  |  | 
18 |  |  |  |  |  | 
19 |  |  |  |  |  | 
20 |  |  |  |  |  | 
21 |  |  |  |  |  | 
22 | Execution. JIV and Repair | 1. Time to organise logistics | High | high |  | 
 |  | 2. Site Access. How quickly we can mobilise equipment to site, especially through third party land | Low | high |  | 
 |  | 3. Understanding the terrian and early visit to site. | high | high |  | 
 |  | 4. Access with our ROW. Buggies take time to track to the work site. (Relocation of equipment to close camps of known areas with frequent incidents.) Location of equipment to hot spots, mudmat, swamp carrier, hovercraft, airboat, mobile bridges & access. | low (east) high (west) | high (east) high (west) |  | 
 |  | 5. Fixing the access way to and along our RoW. | low | high |  | 
23 |  | 6. Geomatics personnel being alone sometimes, making it difficult to capture the entire scope. |  |  |  | 
 |  | 7. Time of arrival at site. | Medium | high |  | 
24 |  | 8. Time for fire to release equipment | High | Low |  | 

## Slide 3: Workshop Outcome
Summary Opportunity Identification |  |  |  | 
Note: Do not include solutions here! Priority level 1 is most important and 3 least important (High - > 6hrs, Medium 3 - 6 hrs, low < 3 hrs) |  |  |  | 
Ref# | Opportunity/Defect | Ease of Implementation (High, Medium, Low) | Value (High, Medium, Low) | Priority Level (1 Hi Hi,2 Hi Me,3 every other )
1 | Have a stagging room to plan and respond to emergencies. | high | high - circa 1 day delay removed | 1
7 | Logistics to get regulators. Assigned regulators | high | High | 1
8 | Standardise request and approval process (BFM, materials, POs) for emergencies | high | high - E&C implication | 1
9 | Quickly request and printing the POs. | high | high - E&C implication | 1
10 | Raise umbrella emergency POs | high | high - E&C implication & cycle time reduction | 1
22 | 1. Time to organise logistics | High | high | 1
 | 12. Early pickup and arrival of regulators | High | Medium | 2
 | 13. Planned vs Emergency jobs for warehouse weekend activities. Share duty managers information. | High | Medium | 2

## Slide 4: Workshop Outcome 02
Summary Opportunity Identification |  |  |  | 
Note: Do not include solutions here! Priority level 1 is most important and 3 least important (High - > 6hrs, Medium 3 - 6 hrs, low < 3 hrs) |  |  |  | 
Ref# | Opportunity/Defect | Ease of Implementation (High, Medium, Low) | Value (High, Medium, Low) | Priority Level (1 Hi Hi,2 Hi Me,3 every other )
2 | Set up a special team for emergencies. Including office, field and support personnel | low | Medium | 3
3 | Carry out low point mapping for depressurisation; Terrain delineation (difficult, normal, medium); resources mapping | Medium | high | 3
4 | Standardise CTS with the list of locations - | Low | high | 3
5 | Capacity to respond when we have more than 6 incident sites per day. | Low | High | 3
6 | Quick availability of resources for depressurisation - storage and reinjection capacity during network outage (Gbaran, Ebubu, Oghale, PWS) | Low | High | 3
14 | Fire team Land location: 12 sites (5 Water tankers currently available for land activities ). Require more hilux for land location activities Swamp location: 4 sites (8 pumps) | Medium | high | 3
15 | Geomatics Can support 3 sites in a day across East and West | low | high | 3
16 | Security: Can support 3 locations (1 black 1 red for east and 1 for west) | low | high | 3
 | 2. Site Access. How quickly we can mobilise equipment to site, especially through third party land | Low | high | 3
 | 3. Understanding the terrian and early visit to site. | high | high | 3
 | 4. Access with our ROW. Buggies take time to track to the work site. (Relocation of equipment to close camps of known areas with frequent incidents.) Location of equipment to hot spots, mudmat, swamp carrier, hovercraft, airboat, mobile bridges & access. | low (east) high (west) | high (east) high (west) | 3
 | 5. Fixing the access way to and along our RoW. | low | high | 3
 | 7. Time of arrival at site. | Medium | high | 3
24 | 8. Time for fire to release equipment | High | Low | 3
 | 9. Security to mobilise. | Medium | High | 3
 | 10. Logistics to get vehicles available on time | Medium | High | 3
 | 11. Getting lunch packs on time. | High | Low | 3
 | 14. PEs to quickly get approval from line managers to get materials over the weekend | High | Low | 3
 | 15. Depressurisation of line around the leak points considering line profiles. Put a process in place to quickly manage local depressurisation(vacuum trucks and decanting ) | Low | High | 3
 | 17. No of SNs for emergencies. | Low | High | 3
 | 18. Leveraging technology for local depressurisation | Low | High | 3
 | 19. Standby emergency security team (Patrick to provide how many emergency sites they can support) | Medium | High | 3
 | 20. Ease to access IA during weekends. Effective communication to all stakeholders including access control during an emergency. | High | Low | 3
 | 21. Contractors to provide support for fire team. Provide a contract for this | Medium | Medium | 3
 | 22. Faulty equipment and tools during execution Focused premob/pre-site mobilisation inspections | Medium | High | 3
 | 23. Limiting COC based on depth and terrain | Medium | Low | 3
 | 24. Difficulty in mapping terrian. Weather condition (heavy rain and sunshine) can impact on the speed of mapping. (Raincoat, umbrella, water) | Low | Low | 3