## Project Plan
No | Activity | Start Date | End Date | Remarks
1 | Send initial communication to users (non-secondees) | 2017-08-30 | 2017-09-11 | Completed
2 | Engage IT leadership on initial user response | 2017-09-13 | 2017-09-15 | Completed
3 | Delete account of users who do not responsd within advised timeline | 2017-09-20 | 2017-09-22 | 9 deleted, 67 planned for deletion
4 | Send out communication to users to provide L3 manager's approval and account to charge | 2017-09-21 | 2017-10-13
5 | Send out communication to Secondees with DTAO and laptop | 2017-09-21 | 2017-09-21
6 | Retrieve Laptop or DTAO from secondees | 2017-10-02 | 2017-10-06
7 | Collate user responses and feedback to IT leadership for review | 2017-10-13 | 2017-10-16
8 | Delete accounts not supported by IT | 2017-10-17 | 2017-10-20
9 | Provide a close out report | 2017-10-23 | 2017-10-25
10 | Project close out | 2017-10-26 | 2017-10-26

## Progress Tracker
COUNT | TOTAL | REMARKS
Secondees (NLNG, etc) | 69 | 7 users have laptop
Support staff | 6
Non-Secondees | 367 | SPDC: 302, SNEPCO: 65
Total Accounts (July Data) | 442
WHERE ARE WE? | TOTAL | REMARKS
Deleted (as at 20/09/2017) | 75
Non Secondee Accounts Under Review | 292
ITEM | Qty | Unit monthly Cost ($) | Annual Cost ($)
ITSO H&S DTAO EXTERNAL ACCESS | 367 | 1 | 4404
ITSO H&S DTAO PRODUCTIVITY TOOLHEAVYUSER | 367 | 25.56 | 112566.24
ITSO H&S DTAO TWO-FACTOR AUTHENT SUPPORT | 367 | 1 | 4404
Total Potential Savings |  |  | 121374.24