## Downside_Risk
S/N | Notes | ID | Bow-tie | Title | Description | Cause | Event | Consequence | Status | Owner | (Sub) Project | Reporting Level | Next Review Date | Risk Exposure Start Date | Risk Exposure End Date | Manageability | Current Assessment Probability, Project RAM | Cost/Benefit, Consequence | Schedule Type, Consequence | Production/Availability Type, Consequence | Ultimate Recovery Type, Consequence | Quality, Consequence | Legal, Consequence | Financing, Consequence | Resources, Consequence | Relationships, Consequence | Probability, HSSE_SP RAM | People-HSE, Consequence | Assets-HSE, Consequence | Community-HSE, Consequence | Environment-HSE, Consequence | Target Assessment Probability, Project RAM | Cost/Benefit, Consequence | Schedule Type, Consequence | Production/Availability Type, Consequence | Ultimate Recovery Type, Consequence | Quality, Consequence | Legal, Consequence | Financing, Consequence | Resources, Consequence | Relationships, Consequence | Probability, HSSE_SP RAM | People-HSE, Consequence | Assets-HSE, Consequence | Community-HSE, Consequence | Environment-HSE, Consequence | Top Downside Risk on (Sub) Project | Functional Areas | Physical Component Type | Impact Phase (ORP) | Contractor | Co-Owner/Partner Company | Early Indicators | Controls
1 | Level of Effort (LoE) | D-7781 | Bow-tie visual | Delays on some activities may lead to cumulative impact on others | Cause: Integrated project delivery entails provision of equipment, materials and resources by different parties (SEDO, Efx, I&C, FLB, Site prep, Sub vendors) Event: there is a risk that delays on some activities may lead to cumulative impact on others Impact: Overall project schedule slippage, EOT claims | Integrated project delivery entails provision of equipment, materials and resources by different parties (SEDO, Efx, I&C, FLB, Site prep, Sub vendors) | Delays on some activities may lead to cumulative impact on others | Overall project schedule slippage, EOT claims | Closed | Nwosu, Ucheoma | Assa North Project | Assa North Project | 2018-11-10 |  | 2021-03-08 | Can Influence | 3 | 2 | 3 |  |  | 2 | [9 empty] | 2 | 1 | 2 |  |  | 1 | [10 empty] | Contract execution |  | Execute
2 | No direct impact on cost | D-7932 | Bow-tie visual | Contracting for rig may be delayed | Ca: Rig earmarked for the project is yet to be contracted Ev: Contracting for rig may be delayed Co: Schedule and reputational impact (with the unit) | Rig earmarked for the project is yet to be contracted | Contracting for rig may be delayed | Schedule and reputational impact | Closed | Ajao, Bolaji | Assa North Project | Assa North Project | 2019-06-30 |  | 2019-12-23 | Can Control | 3 | 2 | 4 | [6 empty] | 4 | [5 empty] | 1 | [8 empty] | 2 | [6 empty] | Wells |  | Execute
3 | Level of Effort (LoE) | D-7818 | Bow-tie visual | Imo State Government may insist on use of local contractors, especially for the site preparation | Cause: Increased request by Imo state government for certain work scopes to be undertaken by indigenes. Event: Imo State Government may insist on use of local contractors, especially for the site preparation Consequence: Loss of FTO, Cost and schedule overrun | Increased request by Imo state government for certain work scopes to be undertaken by indigenes. | Imo State Government may insist on use of local contractors, especially for the site preparation | Loss of FTO, Cost and schedule overrun | Closed | Tijani, Abimbola | Assa North Project |  | 2019-11-29 |  | 2020-10-31 | Can Influence | 3 | 2 | 2 | [6 empty] | 2 | [5 empty] | 1 | 2 | 2 | [6 empty] | 1 | [6 empty] | Political |  | Execute
4 | Risk redefined | D-4695 | Bow-tie visual | In-country fabrication (incl piperacks, fuel gas skid, air receivers) may arrive late, incomplete or with quality issues | Cause: Strategy to fabricate some modules in-country by a contractor with unproven experience or track record (with stainless steel equipment), and within an aggressive timeline Event: In-country fabrication (incl piperacks, fuel gas skid, air receivers) may arrive late, incomplete or with quality issues Consequence: Schedule and cost overrun due to delay in execution and OSD | Strategy to fabricate some modules in-country by a contractor with unproven experience or track record (with stainless steel equipment), and within an aggressive timeline | In-country fabrication (incl piperacks, fuel gas skid, air receivers) may arrive late, incomplete or with quality issues | Schedule and cost overrun due to delay in execution and OSD | Closed | Mackellar, Andrew | Assa North Project |  | 2019-08-30 |  | 2020-07-31 | Can Influence | 4 | 3 | 3 | [12 empty] | 2 | 3 | 3 | [13 empty] | Commercial, Political |  | Execute
5 |  | D-8306 | Bow-tie visual | 3rd party plant connection to the Process Control Domain | As a result of the requirement to transmit and receive metering and safeguarding information with SEPLAT plant there may be cyber attack through the gateway leading to process upset, plant shutdown and creation of an unsafe environment | As a result of the requirement to transmit and receive metering and safeguarding information with SEPLAT plant | there may be cyber attack through the gateway | leading to process upset, plant shutdown and creation of an unsafe environment | Closed | Ofovwe, Greg | Assa North Project |  | 2019-03-06 |  | 2020-06-01 | Can Control | 3 |  |  | 4 |  |  | 2 |  |  | 3 | [5 empty] | 1 | [8 empty] | 1 | [6 empty] | Technical | Process and utilities | Operate
6 | No direct impact on cost | D-8312 | Bow-tie visual | Significant rework & quality issues with fuel gas skid | As a result of fuel gas skid assembly by Nivafer (having not done stainless steel fabrication works before), There may be significant rework & quality issues, leading to delivery delays | As a result of fuel gas skid assembly by Nivafer (having not done stainless steel fabrication works before) | There may be significant rework & quality issues | Leading to delivery delays | Closed | Mackellar, Andrew | Assa North Project |  | 2019-03-31 |  | 2020-10-23 | Can Control | 3 | 1 | 4 |  |  | 3 | [9 empty] | 1 | 1 | 1 |  |  | 1 | [10 empty] | Technical | Process, utilities and product handling | Execute
7 | No direct impact on cost | D-8205 | Bow-tie visual | Funding during project execution may be suboptimal and Contractor’s cashflow may be impacted | Cause: There has been a delay in payment of cash calls to contractors in 2018 Event: Funding during project execution may be suboptimal and Contractors cashflow may be impacted Conseq: Delay to project execution | There has been a delay in payment of cash calls to contractors in 2018 | Funding during project execution may be suboptimal and Contractors cashflow may be impacted | Delay to project execution | Closed | Ajala, Olufemi | Assa North Project |  | 2019-03-01 |  | 2022-10-31 | Can Influence | 4 | 2 | 3 | [12 empty] | 1 | 1 | 2 | [13 empty] | Funding/Finance |  | Execute
8 | No direct impact on cost | D-8301 | Bow-tie visual | Site Prep mobilization may be further delayed | As a result of ongoing delay in finalizing alignment with contractors to set up a JV arrangement, the Site Prep mobilization may be further delayed, leading to overall schedule delay on the project | As a result of ongoing delay in finalizing alignment with contractors to set up a JV arrangement | Site Prep mobilization may be further delayed | leading to overall schedule delay on the project | Closed | Tijani, Abimbola | Assa North Project |  | 2018-11-23 |  | 2019-01-31 | Can Influence | 3 | 2 | 4 | [12 empty] | 2 | 1 | 2 | [13 empty] | Commercial |  | Execute
9 | Cost impact to be banked | D-7779 | Bow-tie visual | Project may no longer be competitive in event of scope change | Cause: Lessons from BG (Enerflex delivered modules) indicates that Enerflex is commercially astute and would charge a premium on scope changes Event: Project may no longer be competitive in the event of major scope changes Impact: Cost increase | Lessons from BG (Enerflex delivered modules) indicates that Enerflex is commercially astute and would charge a premium on scope changes | Project may no longer be competitive in the event of major scope changes | Cost increase | Closed | Tijani, Abimbola | Assa North Project | Assa North Project | 2019-12-19 |  | 2020-10-31 | Can Control | 2 | 2 | [13 empty] | 1 | 1 | [14 empty] | Contract execution |  | Execute
10 |  | D-6237 | Bow-tie visual | Assa North (OML 21) Licence may not be renewed as at when required and the terms for renewal may not be favourable | Cause: 1.Assa North OML 21 expires in June 2019 and FGN (MoPR/ DPR/ NNPC) does not support pre mature licence renewal. 2. Non alignment between Shell/ FGN on terms for Licence renewal Event: Assa North (OML 21) Licence may not be renewed as at when required and the terms for renewal may not be favourable Consequence: 1. Acreage is lost 2. Delayed FID, 3.Pre FID investment loss, 4. Adverse impact on reputation, 5. Value erosion |  |  |  | Closed | Shittu, Muhammad | Assa North Project |  | 2018-12-31 |  | 2019-06-30 | Can Influence | 2 | [8 empty] | 3 | [5 empty] | 3 | [8 empty] | 3 | [6 empty] | Organisational, Political |  | Operate
11 | No direct impact on cost | D-8008 | Bow-tie visual | Local contractors may not be able to fully comply with NCD Requirements | Cause: Inadequate In-country capacity to fabricate major equipment (vessel with large thickness), inadequate manpower with specialized skills, Nigerian Pipe mills not capable of fabricating line pipe below 24" diameter, new directive issued midstream of the project life, faster to import some industry standard equipment, Law has conflicting requirements in certain areas between article and schedule, only one functional steel mill in the market. Local market prices uncertainty (fluctuate) expensive to procure steel, quality of products poor due to existence of counterfeit materials in the market Event: Local contractors may not be able to fully comply with NCD Requirements Consequences: Heavy Financial Penalty, Contractor may be suspended, schedule and cost impact, reputational damage and Project suspension/cancellation | Inadequate In-country capacity to fabricate major equipment (vessel with large thickness), inadequate manpower with specialized skills, Nigerian Pipe mills not capable of fabricating line pipe below 24" diameter, new directive issued midstream of the project life, faster to import some industry standard equipment, Law has conflicting requirements in certain areas between article and schedule, only one functional steel mill in the market. Local market prices uncertainty (fluctuate) expensive to procure steel, quality of products poor due to existence of counterfeit materials in the market | Local contractors may not be able to fully comply with NCD Requirements | Heavy Financial Penalty, Contractor may be suspended, schedule and cost impact, reputational damage and Project suspension/cancellation | Closed | Emuophedaro, Sunday | Assa North Project |  | 2019-11-30 |  | 2021-03-29 | Can Influence | 3 | 2 |  |  |  |  | 3 |  |  | 2 | [5 empty] | 1 | 2 |  |  |  |  | 3 |  |  | 2 | [6 empty] | Commercial |  | Define
12 | Level of Effort (LoE) | D-7522 | Bow-tie visual | Limited availability of local welders for Corrosion Resistant Alloy (CRA) welding | As a result of limited availability of local welders for CRA welding in-country, there may be high failure rate and repeat welds which would affect project schedule | As a result of limited availability of local welders for CRA welding in-country | There may be high failure rate and repeat welds | Would affect project schedule | Closed | Nwosu, Ucheoma | Assa North Project |  | 2019-02-22 |  | 2021-06-30 | Can Influence | 2 | 1 | 3 |  |  | 3 | [9 empty] | 1 | 1 | 2 |  |  | 2 | [12 empty] | Execute
13 | Level of Effort (LoE) | D-7996 | Bow-tie visual | Tie-in design may not be completed in time due to insufficient data | Cause: Non release of all applicable Obite facility tie-in drawings from TEPNG to SPDC Event: Tie-in design may not be completed in time due to insufficient data Consequence: Delays, standby charges. | Non release of all applicable Obite facility tie-in drawings from TEPNG to SPDC | Tie-in design may not be completed in time due to insufficient data | Delays, standby charges | Closed | Nwosu, Ucheoma | Assa North Project |  | 2018-10-31 |  | 2018-12-31 | Can Influence | 3 | 1 | 3 |  |  | 2 | [9 empty] | 1 | 1 | 1 |  |  | 1 | [10 empty] | Technical |  | Execute
14 | Cost impact to be banked | D-7933 | Bow-tie visual | There may be increased insecurity and political clashes | Cause: 2019 is an election year and project would still be in execution Event: There may be increased insecurity and political clashes Consequences: Delay to construction, cost and HSE | 2019 is an election year and project would still be in execution | There may be increased insecurity and political clashes | Delay to construction, cost and HSE | Closed | Asomba, Meshack | Assa North Project | Assa North Project | 2019-06-21 |  | 2019-07-31 | Cannot Control | 4 | 1 | 2 | [12 empty] | 2 | 1 | 2 | [13 empty] | Corporate Security | All Physical | Execute
15 | Level of Effort (LoE) | D-8458 | Bow-tie visual | Risk of delays during installation of low level pipe spools into the piperack | As a result of piperack execution strategy (modularization & fabrication by Nivafer) and prefabrication of spools, there is a risk of delays during installation of low level pipe spools into the piperack because of the need to thread through the piperack, leading to overall delays and HSSE exposure. | As a result of piperack execution strategy (modularization & fabrication by Nivafer) and prefabrication of spools | There is a risk of delays during installation of low level pipe spools into the piperack because of the need to thread through the piperack | Leading to overall delays and HSSE exposure | Closed | Mackellar, Andrew | Assa North Project |  | 2019-05-24 |  | 2020-07-31 | Can Control | 3 | 2 | 3 |  |  | 2 | [9 empty] | 1 | 1 | 2 |  |  | 1 | [10 empty] | Technical | Onshore installations | Execute
16 | No direct impact on cost | D-5645 | Bow-tie visual | Project economics may be negatively impacted by changes in government policy in relation to gas pricing | Cause: Changes in government policy for gas pricing Event: project economics may be negatively impacted Consequence: Possible Project value erosion | Changes in government policy for gas pricing | Project economics may be negatively impacted | Possible Project value erosion | Closed | Beinisch, Yischai | Assa North Project |  | 2018-07-24 |  | 2018-09-30 | Can Influence | 2 | 2 | [29 empty] | Economic |  | Execute
17 | Risk redefined | D-8282 | Bow-tie visual | Recent increase oil price there is a probability that Contractors/Suppliers may deliver poor quality materials and resources | As a result of recent uptick in the market for Oil and Gas activities due to increase in oil price there is a probability that contractors/Suppliers may deliver poor quality materials ( due to high cost of raw materials) and high demand for competent personnel, could affect overall quality on the project | As a result of recent uptick in the market for Oil and Gas activities, due to increase in oil price there is a risk that contractors/Suppliers may procure poor quality materials ( due to high cost of raw materials) and high demand for competent personnel) | there is a probability that contractors may deliver poor quality materials ( due to high cost of raw materials) and high demand for competent personnel, could affect overall quality on the project | Cost overrun, Schedule delay, low quality | Closed | Ofovwe, Greg | Assa North Project |  | 2019-04-30 |  | 2020-10-31 | Can Control | 2 | 3 | 3 | 3 |  | 3 | [9 empty] | 1 | 2 | 2 |  |  | 2 | [10 empty] | Technical |  | Execute
18 |  | D-8285 | Bow-tie visual | Contractor may not have enough resources to undertake multiple projects | As a result of the proposed contractors billed to handle multiple projects at the same time, there is a risk that they may not have enough resources to undertake all the project activities, leading to schedule delay and low productivity | As a result of the proposed contractors billed to handle multiple projects at the same time | there is a risk that they may not have enough resources to undertake all the project activities | leading to schedule delay and low productivity | Closed | Tijani, Abimbola | Assa North Project
19 |  | D-8287 | Bow-tie visual | Other communities in Imo State may agitate for more SP interventions | SP activities planned for the Assa communities are different from the other oil-producing communities in Imo state, there is a risk that the other communities may agitate for more interventions, leading to community or stakeholder challenges | SP activities planned for the Assa communities are different from the other oil-producing communities in Imo state | there is a risk that the other communities may agitate for more interventions | leading to community or stakeholder challenges | Closed | Asomba, Meshack | Assa North Project |  | 2019-03-15 |  | 2021-06-30 | Can Influence
20 |  | D-8421 | Bow-tie visual | In-country Pipe racks and Fuel Gas Skid Contractor have no proven experience in their Work Scope there is a probability of assembly errors during skid fabrication & fabrication defects during Pressure Vessel fabrication. | As a result of new proven experience or track record for fabrication of Fuel Gas Skid and S.S Pressure Vessels by In-country Pipe rack & FG Skid fabricator , may happen assembly errors during skid fabrication & fabrication defects during Pressure Vessel fabrication, leads to Schedule delay, Integrity/Quality issues during the Contractor Work Scope | As a result of new proven experience or track record for fabrication of Fuel Gas Skid and S.S Pressure Vessels by In-country Pipe rack & FG Skid fabricator , | may happen assembly errors during skid fabrication & fabrication defects during Pressure Vessel fabrication, | leads to Schedule delay, Integrity/Quality issues during the Contractor Work Scope | Closed | Chitharanjan, Thampan | Assa North Project |  | 2019-01-25 |  | 2019-12-20 | Can Control
21 |  | D-8457 | Bow-tie visual | Installation will be carried out by the Installation contractor not the vendor which may result in improper equipment installation | Installation will be carried out by the Installation contractor not the vendor which may result in improper equipment installation leading to poor commissioning |  |  |  | Closed | Ebiem, Enajite | Assa North Project |  | 2019-02-28 |  | 2020-12-31 | Can Control
22 |  | D-8584 | Bow-tie visual | NAPIMS may not support revised OSD |  |  |  |  | Closed | Uche, Ikechukwu | Assa North Project |  |  |  |  | 0
Note on R2: target: Project RAM, Severity: Material (6), Probability: 3, Consequences: 2
Note on S2: target: Cost/Benefit, Severity: Material (6), Probability: 3, Consequences: 2
Note on T2: target: Schedule Type, Severity: Material (9), Probability: 3, Consequences: 3
Note on W2: target: Quality [QUAL], Severity: Material (6), Probability: 3, Consequences: 2
Note on AG2: target: Project RAM, Severity: Small (2), Probability: 2, Consequences: 1
Note on AH2: target: Cost/Benefit, Severity: Small (2), Probability: 2, Consequences: 1
Note on AI2: target: Schedule Type, Severity: Small (4), Probability: 2, Consequences: 2
Note on AL2: target: Quality [QUAL], Severity: Small (2), Probability: 2, Consequences: 1
Note on R3: target: Project RAM, Severity: Material (6), Probability: 3, Consequences: 2
Note on S3: target: Cost/Benefit, Severity: Material (6), Probability: 3, Consequences: 2
Note on T3: target: Schedule Type, Severity: Severe (12), Probability: 3, Consequences: 4
Note on AA3: target: Relationships [REL], Severity: Severe (12), Probability: 3, Consequences: 4
Note on AG3: target: Project RAM, Severity: (), Probability: 1, Consequences:
Note on AP3: target: Relationships [REL], Severity: Small (2), Probability: 1, Consequences: 2
Note on R4: target: Project RAM, Severity: Material (6), Probability: 3, Consequences: 2
Note on S4: target: Cost/Benefit, Severity: Material (6), Probability: 3, Consequences: 2
Note on T4: target: Schedule Type, Severity: Material (6), Probability: 3, Consequences: 2
Note on AA4: target: Relationships [REL], Severity: Material (6), Probability: 3, Consequences: 2
Note on AG4: target: Project RAM, Severity: Small (2), Probability: 1, Consequences: 2
Note on AH4: target: Cost/Benefit, Severity: Small (2), Probability: 1, Consequences: 2
Note on AI4: target: Schedule Type, Severity: Small (2), Probability: 1, Consequences: 2
Note on AP4: target: Relationships [REL], Severity: Small (1), Probability: 1, Consequences: 1
Note on R5: target: Project RAM, Severity: Severe (12), Probability: 4, Consequences: 3
Note on S5: target: Cost/Benefit, Severity: Severe (12), Probability: 4, Consequences: 3
Note on T5: target: Schedule Type, Severity: Severe (12), Probability: 4, Consequences: 3
Note on AG5: target: Project RAM, Severity: Material (6), Probability: 2, Consequences: 3
Note on AH5: target: Cost/Benefit, Severity: Material (6), Probability: 2, Consequences: 3
Note on AI5: target: Schedule Type, Severity: Material (6), Probability: 2, Consequences: 3
Note on R6: target: Project RAM, Severity: (), Probability: 3, Consequences:
Note on U6: target: Production/Availability Type, Severity: Severe (12), Probability: 3, Consequences: 4
Note on X6: target: Legal [LEG], Severity: Material (6), Probability: 3, Consequences: 2
Note on AA6: target: Relationships [REL], Severity: Material (9), Probability: 3, Consequences: 3
Note on AG6: target: Project RAM, Severity: (), Probability: 1, Consequences:
Note on AP6: target: Relationships [REL], Severity: Small (1), Probability: 1, Consequences: 1
Note on R7: target: Project RAM, Severity: Small (3), Probability: 3, Consequences: 1
Note on S7: target: Cost/Benefit, Severity: Small (3), Probability: 3, Consequences: 1
Note on T7: target: Schedule Type, Severity: Severe (12), Probability: 3, Consequences: 4
Note on W7: target: Quality [QUAL], Severity: Material (9), Probability: 3, Consequences: 3
Note on AG7: target: Project RAM, Severity: Small (1), Probability: 1, Consequences: 1
Note on AH7: target: Cost/Benefit, Severity: Small (1), Probability: 1, Consequences: 1
Note on AI7: target: Schedule Type, Severity: Small (1), Probability: 1, Consequences: 1
Note on AL7: target: Quality [QUAL], Severity: Small (1), Probability: 1, Consequences: 1
Note on R8: target: Project RAM, Severity: Material (8), Probability: 4, Consequences: 2
Note on S8: target: Cost/Benefit, Severity: Material (8), Probability: 4, Consequences: 2
Note on T8: target: Schedule Type, Severity: Severe (12), Probability: 4, Consequences: 3
Note on AG8: target: Project RAM, Severity: Small (1), Probability: 1, Consequences: 1
Note on AH8: target: Cost/Benefit, Severity: Small (1), Probability: 1, Consequences: 1
Note on AI8: target: Schedule Type, Severity: Small (2), Probability: 1, Consequences: 2
Note on R9: target: Project RAM, Severity: Material (6), Probability: 3, Consequences: 2
Note on S9: target: Cost/Benefit, Severity: Material (6), Probability: 3, Consequences: 2
Note on T9: target: Schedule Type, Severity: Severe (12), Probability: 3, Consequences: 4
Note on AG9: target: Project RAM, Severity: Small (2), Probability: 2, Consequences: 1
Note on AH9: target: Cost/Benefit, Severity: Small (2), Probability: 2, Consequences: 1
Note on AI9: target: Schedule Type, Severity: Small (4), Probability: 2, Consequences: 2
Note on R10: target: Project RAM, Severity: Small (4), Probability: 2, Consequences: 2
Note on S10: target: Cost/Benefit, Severity: Small (4), Probability: 2, Consequences: 2
Note on AG10: target: Project RAM, Severity: Small (1), Probability: 1, Consequences: 1
Note on AH10: target: Cost/Benefit, Severity: Small (1), Probability: 1, Consequences: 1
Note on R11: target: Project RAM, Severity: (), Probability: 2, Consequences:
Note on AA11: target: Relationships [REL], Severity: Material (6), Probability: 2, Consequences: 3
Note on AG11: target: Project RAM, Severity: Material (9), Probability: 3, Consequences: 3
Note on AP11: target: Relationships [REL], Severity: Material (9), Probability: 3, Consequences: 3
Note on R12: target: Project RAM, Severity: Material (6), Probability: 3, Consequences: 2
Note on S12: target: Cost/Benefit, Severity: Material (6), Probability: 3, Consequences: 2
Note on X12: target: Legal [LEG], Severity: Material (9), Probability: 3, Consequences: 3
Note on AA12: target: Relationships [REL], Severity: Material (6), Probability: 3, Consequences: 2
Note on AG12: target: Project RAM, Severity: Small (2), Probability: 1, Consequences: 2
Note on AH12: target: Cost/Benefit, Severity: Small (2), Probability: 1, Consequences: 2
Note on AM12: target: Legal [LEG], Severity: Small (3), Probability: 1, Consequences: 3
Note on AP12: target: Relationships [REL], Severity: Small (2), Probability: 1, Consequences: 2
Note on R13: target: Project RAM, Severity: Small (2), Probability: 2, Consequences: 1
Note on S13: target: Cost/Benefit, Severity: Small (2), Probability: 2, Consequences: 1
Note on T13: target: Schedule Type, Severity: Material (6), Probability: 2, Consequences: 3
Note on W13: target: Quality [QUAL], Severity: Material (6), Probability: 2, Consequences: 3
Note on AG13: target: Project RAM, Severity: Small (1), Probability: 1, Consequences: 1
Note on AH13: target: Cost/Benefit, Severity: Small (1), Probability: 1, Consequences: 1
Note on AI13: target: Schedule Type, Severity: Small (2), Probability: 1, Consequences: 2
Note on AL13: target: Quality [QUAL], Severity: Small (2), Probability: 1, Consequences: 2
Note on R14: target: Project RAM, Severity: Small (3), Probability: 3, Consequences: 1
Note on S14: target: Cost/Benefit, Severity: Small (3), Probability: 3, Consequences: 1
Note on T14: target: Schedule Type, Severity: Material (9), Probability: 3, Consequences: 3
Note on W14: target: Quality [QUAL], Severity: Material (6), Probability: 3, Consequences: 2
Note on AG14: target: Project RAM, Severity: Small (1), Probability: 1, Consequences: 1
Note on AH14: target: Cost/Benefit, Severity: Small (1), Probability: 1, Consequences: 1
Note on AI14: target: Schedule Type, Severity: Small (1), Probability: 1, Consequences: 1
Note on AL14: target: Quality [QUAL], Severity: Small (1), Probability: 1, Consequences: 1
Note on R15: target: Project RAM, Severity: Small (4), Probability: 4, Consequences: 1
Note on S15: target: Cost/Benefit, Severity: Small (4), Probability: 4, Consequences: 1
Note on T15: target: Schedule Type, Severity: Material (8), Probability: 4, Consequences: 2
Note on AG15: target: Project RAM, Severity: Small (2), Probability: 2, Consequences: 1
Note on AH15: target: Cost/Benefit, Severity: Small (2), Probability: 2, Consequences: 1
Note on AI15: target: Schedule Type, Severity: Small (4), Probability: 2, Consequences: 2
Note on R16: target: Project RAM, Severity: Material (6), Probability: 3, Consequences: 2
Note on S16: target: Cost/Benefit, Severity: Material (6), Probability: 3, Consequences: 2
Note on T16: target: Schedule Type, Severity: Material (9), Probability: 3, Consequences: 3
Note on W16: target: Quality [QUAL], Severity: Material (6), Probability: 3, Consequences: 2
Note on AG16: target: Project RAM, Severity: Small (1), Probability: 1, Consequences: 1
Note on AH16: target: Cost/Benefit, Severity: Small (1), Probability: 1, Consequences: 1
Note on AI16: target: Schedule Type, Severity: Small (2), Probability: 1, Consequences: 2
Note on AL16: target: Quality [QUAL], Severity: Small (1), Probability: 1, Consequences: 1
Note on R17: target: Project RAM, Severity: Small (4), Probability: 2, Consequences: 2
Note on S17: target: Cost/Benefit, Severity: Small (4), Probability: 2, Consequences: 2
Note on R18: target: Project RAM, Severity: Material (6), Probability: 2, Consequences: 3
Note on S18: target: Cost/Benefit, Severity: Material (6), Probability: 2, Consequences: 3
Note on T18: target: Schedule Type, Severity: Material (6), Probability: 2, Consequences: 3
Note on U18: target: Production/Availability Type, Severity: Material (6), Probability: 2, Consequences: 3
Note on W18: target: Quality [QUAL], Severity: Material (6), Probability: 2, Consequences: 3
Note on AG18: target: Project RAM, Severity: Small (2), Probability: 1, Consequences: 2
Note on AH18: target: Cost/Benefit, Severity: Small (2), Probability: 1, Consequences: 2
Note on AI18: target: Schedule Type, Severity: Small (2), Probability: 1, Consequences: 2
Note on AL18: target: Quality [QUAL], Severity: Small (2), Probability: 1, Consequences: 2

## LookUpLists (hidden)
Status | (Sub) Project | Reporting Level | Manageability
Proposed | Shell (Top Node) | Shell (Top Node) | Can Control
Active | Southern Swamp Associated Gas Solution Project | Southern Swamp Associated Gas Solution Project | Can Influence
Taken | SSAGS CEIP Project | SSAGS CEIP Project | Cannot Control
Propose to Close | Forcados Yokri Integrated Project (FYIP) | Forcados Yokri Integrated Project (FYIP)
Closed | FYIP - Offshore | FYIP - Offshore
Occurred | FYIP - Onshore | FYIP - Onshore
| FYIP - Step 2 | FYIP - Step 2
| Obigbo Node Power Improvement Project | Obigbo Node Power Improvement Project
| HI Development | HI Development
| HI Dry Gas Option | HI Dry Gas Option
| HI Wet Gas Option | HI Wet Gas Option
| Central Engineering Onshore and Shallow Offshore | Central Engineering Onshore and Shallow Offshore
| Lekki Gas Transmission Pipeline Project | Lekki Gas Transmission Pipeline Project
| AG Solutions Phase 1 Project | AG Solutions Phase 1 Project
| AG Solutions 1 - Otumara (CPF and Pipeline) | AG Solutions 1 - Otumara (CPF and Pipeline)
| AG Solutions 1 - Adibawa | AG Solutions 1 - Adibawa
| AG Solutions 1 - Bonny | AG Solutions 1 - Bonny
| Assa North Project | Assa North Project
| Eastern Domestic Gas Interim Project | Eastern Domestic Gas Interim Project
| NLNG Supplies Project | NLNG Supplies Project
| Gbaran Ubie Phase 3A Abasere | Gbaran Ubie Phase 3A Abasere
| Soku NAG Compression | Soku NAG Compression
| Gbaran Nodal Compression Project | Gbaran Nodal Compression Project
| Gbaran Ubie Ph2A (Gbaran Infill) | Gbaran Ubie Ph2A (Gbaran Infill)
| Gbaran Ubie Ph2B (Kolocreek to Soku) | Gbaran Ubie Ph2B (Kolocreek to Soku)
| Gbaran Security of Supply | Gbaran Security of Supply
| Gbaran CPF North Bank Shoreline Protection | Gbaran CPF North Bank Shoreline Protection
| Gbaran 3B - Uzu Development | Gbaran 3B - Uzu Development
| Gbaran Ubie Phase 3A Enwhe | Gbaran Ubie Phase 3A Enwhe
| Soku NAG Compression Project 2 | Soku NAG Compression Project 2
| ZARAMA-015 Single Well Opportunity Project | ZARAMA-015 Single Well Opportunity Project
| Kolo creek well 41 | Kolo creek well 41
| Regional Support Directorate | Regional Support Directorate
| SPDC Onshore/Shallow Offshore Projects Leadership | SPDC Onshore/Shallow Offshore Projects Leadership
| Training | Training
| Southern Swamp NAG | Southern Swamp NAG
| Corporate Matrix Projects | Corporate Matrix Projects
| Corporate Civil Projects | Corporate Civil Projects
| Ogbia-Akipelai-Nembe Road Project | Ogbia-Akipelai-Nembe Road Project
| Access Roads Projects | Access Roads Projects
| Location Preparation Projects | Location Preparation Projects
| Dredging Projects | Dredging Projects
| Jetty Upgrade/Shore Protection Projects | Jetty Upgrade/Shore Protection Projects
| Onshore Matrix Projects | Onshore Matrix Projects
| Soku Oil Rim Development Project | Soku Oil Rim Development Project
| Post Divestment Crude Oil Metering Project | Post Divestment Crude Oil Metering Project
| DOMGAS Metering Project | DOMGAS Metering Project
| Iseni Early Hook-Up Project | Iseni Early Hook-Up Project
| Assa North CEIP Project | Assa North CEIP Project
| SOKU Crude Oil Custody Transfer Metering Improvement Project | SOKU Crude Oil Custody Transfer Metering Improvement Project
| Utilities Projects | Utilities Projects
| ROCI Projects | ROCI Projects
| Shallow Offshore Matrix | Shallow Offshore Matrix
| SPM Buoy Refurbishment Project | SPM Buoy Refurbishment Project
| Bonny Terminal - Crude Loading Platform Revamp | Bonny Terminal - Crude Loading Platform Revamp
| EA Platforms Activities | EA Platforms Activities
| EA Asset Engineering | EA Asset Engineering
| PCM Special Projects | PCM Special Projects
| EA FOD Opportunity | EA FOD Opportunity
| EA LOD1 | EA LOD1
| SPDC Integrated Decommissioning and Restoration | SPDC Integrated Decommissioning and Restoration
| EA Swivel Bearing Replacement | EA Swivel Bearing Replacement
| EA Swivel Bearing Bridging Solution | EA Swivel Bearing Bridging Solution
| EA RPA Splitter Project | EA RPA Splitter Project
| Major Pipelines Projects | Major Pipelines Projects
| Pipeline Replacement Projects | Pipeline Replacement Projects
| 48" Export Line Repairs | 48" Export Line Repairs
| FOT Riser Replacement Project | FOT Riser Replacement Project
| Gbaran-Soku Asset Capacity Maximization Project | Gbaran-Soku Asset Capacity Maximization Project
| Brass Fertilizer Project | Brass Fertilizer Project
| Beni/Uden/Kolobiri Project | Beni/Uden/Kolobiri Project
| SPDC Corporate Asset Engineering Projects | SPDC Corporate Asset Engineering Projects
| Alakiri Standard World-Class Facilities | Alakiri Standard World-Class Facilities
| SPDC Tanks Rehab Projects | SPDC Tanks Rehab Projects
| Epu Phase 2 Project | Epu Phase 2 Project
| Shell Nigeria Gas upgrade | Shell Nigeria Gas upgrade
| Diebu Creek Gascap Blowdown Project | Diebu Creek Gascap Blowdown Project
| AMOR (Ahia-Mininta-Obelle-Rumuekpe) Integrated Project | AMOR (Ahia-Mininta-Obelle-Rumuekpe) Integrated Project
| AMOR Phase 1A | AMOR Phase 1A
| AMOR Phase 1B | AMOR Phase 1B
| AMOR Phase 2 | AMOR Phase 2
| Okoloma Compression Project | Okoloma Compression Project
| SPDC Onshore Production Operations | SPDC Onshore Production Operations
| SPDC Inactive Projects | SPDC Inactive Projects
| Aferelow Oroni Uzere | Aferelow Oroni Uzere
| Cluster 2A | Cluster 2A
| Forcados Yokri Gas Project | Forcados Yokri Gas Project
| Eastern Domestic Gas Growth Project | Eastern Domestic Gas Growth Project
| Beseni Samabri IOGP | Beseni Samabri IOGP
| Akri Oguta IOGP | Akri Oguta IOGP
| Santa Barbara Early Oil Development phase 1 | Santa Barbara Early Oil Development phase 1
| Bonny NAG Project | Bonny NAG Project
| Santa Barbara Later Oil Development (LOD) | Santa Barbara Later Oil Development (LOD)
| ROCI | ROCI
| Odidi Node Gas Development Project | Odidi Node Gas Development Project
| Dom Gas Supply project | Dom Gas Supply project
| Commercial&Political - Upstream Supply | Commercial&Political - Upstream Supply
| Technical&Economical | Technical&Economical
| Organizational | Organizational
| Commercial - NGMP | Commercial - NGMP
| Brass LNG Upstream Gas Supply | Brass LNG Upstream Gas Supply
| Brass LNG Commercial | Brass LNG Commercial
| Brass LNG Technical | Brass LNG Technical
| Brass LNG EOP | Brass LNG EOP
| Common DomGas & NLNG T7 | Common DomGas & NLNG T7
| Common Domgas and NLNG Technical Risks | Common Domgas and NLNG Technical Risks
| Common Domgas and NLNG Economics, Organizational, and PoliticalRisks | Common Domgas and NLNG Economics, Organizational, and PoliticalRisks
| Common Domgas and NLNG CommercialRisks | Common Domgas and NLNG CommercialRisks
| NLNG T7 US (updateDec08) | NLNG T7 US (updateDec08)
| [Technical&Economical] NLNG T7 Upstream | [Technical&Economical] NLNG T7 Upstream
| [Organizational] NLNG T7 Upstream | [Organizational] NLNG T7 Upstream
| [Commercial&Political] NLNG T7 Upstream | [Commercial&Political] NLNG T7 Upstream
| Afam F5.0A ORD | Afam F5.0A ORD
| Alakiri Refurbishment Project | Alakiri Refurbishment Project
| SPDC Surge Vessel Gas Gathering Project | SPDC Surge Vessel Gas Gathering Project
| Alakiri Integrated Oil & Gas Developement | Alakiri Integrated Oil & Gas Developement
| NGMP | NGMP
| SPDC Pipeline Replacement Campaign Project Phase 1 | SPDC Pipeline Replacement Campaign Project Phase 1
| Nembe Electrical Interdependency Project | Nembe Electrical Interdependency Project
| Utorogu K Sands NAG Phase 1 Development Project | Utorogu K Sands NAG Phase 1 Development Project
| Trans Niger Pipeline Loop Project | Trans Niger Pipeline Loop Project
| Soku Liquid Evacuation Pipeline and the Ekulama 2 AG Pipeline projects | Soku Liquid Evacuation Pipeline and the Ekulama 2 AG Pipeline projects
| SPDC/NAOC Non Operated Joint Ventures | SPDC/NAOC Non Operated Joint Ventures
| SPDC/NPDC Transferred Fields | SPDC/NPDC Transferred Fields
| Upstream Gas Commercial | Upstream Gas Commercial
| Gbaran CPF Domgas Supply | Gbaran CPF Domgas Supply
| Condensate Storage Facilities Project | Condensate Storage Facilities Project
| Awoba Restart Project | Awoba Restart Project
| Disel to Gas Project | Disel to Gas Project
| Forcados Yokri Water Injection Project | Forcados Yokri Water Injection Project
| Awoba FOD Project | Awoba FOD Project
| Awoba NW Project | Awoba NW Project
| Marine Cable Repair Project | Marine Cable Repair Project
| Ekulama Integrated Oil & Gas Development | Ekulama Integrated Oil & Gas Development
| IA-200 Project | IA-200 Project
| Cluster 2B | Cluster 2B
| Awoba NAG | Awoba NAG
| Bonny and Bonny North Dev. | Bonny and Bonny North Dev.
| Well TUMK-2 | Well TUMK-2
| Well TUMK-3 | Well TUMK-3
| Integrated Egbema Development Project | Integrated Egbema Development Project
| Egbema West Dump flooding Project | Egbema West Dump flooding Project
| Further AG Solutions (Flares Down) Project | Further AG Solutions (Flares Down) Project
| Western Matrix Projects | Western Matrix Projects
| WAGP Common | WAGP Common
| WAGP Utorogu Gas Plant | WAGP Utorogu Gas Plant
| WAGP Oben Gas Plant | WAGP Oben Gas Plant
| Ughelli Pump Station Tank Rehab | Ughelli Pump Station Tank Rehab
| Ovhor FOD Project | Ovhor FOD Project
| Odidi Non-Associated Gas Project | Odidi Non-Associated Gas Project
| NGC Common | NGC Common
| NGC Oben Compressor Station Refurbishment | NGC Oben Compressor Station Refurbishment
| NGC Jones Creek Compressor Station Refurbishment | NGC Jones Creek Compressor Station Refurbishment
| NGC Odidi Compressor Station Refurbishment | NGC Odidi Compressor Station Refurbishment
| Nembe Creek FOD Project | Nembe Creek FOD Project
| NLNG T7 Upstream (superceeded) | NLNG T7 Upstream (superceeded)
| NLNG T7 Upstream Technical | NLNG T7 Upstream Technical
| NLNG T7 Upstream Economics, Organizational, and Political | NLNG T7 Upstream Economics, Organizational, and Political
| NLNG T7 Upstream Commercial | NLNG T7 Upstream Commercial
| OK LNG | OK LNG
| Commercial | Commercial
| Economical, Organisational and Political | Economical, Organisational and Political
| Technical | Technical
| Domgas Western Interim | Domgas Western Interim
| NLNG T7 Midstream | NLNG T7 Midstream
| NLNG T7 Midstream Technical Risks | NLNG T7 Midstream Technical Risks
| NLNG T7 Midstream Economics, Organizational, and Political Risks | NLNG T7 Midstream Economics, Organizational, and Political Risks
| NLNG T7 Midstream Commercial Risks | NLNG T7 Midstream Commercial Risks
| Buguma IOGD | Buguma IOGD
| Cawthorne Channel FOD | Cawthorne Channel FOD
| Agbada H-Block Project | Agbada H-Block Project
| Agbada-Obigbo AGG Facilities Upgrade | Agbada-Obigbo AGG Facilities Upgrade
| EGGS: Eastern Gas Gathering System | EGGS: Eastern Gas Gathering System
| DOMGAS Quality Improvement Project | DOMGAS Quality Improvement Project
| Escravos CEIP Project | Escravos CEIP Project
| Agoro Agge CEIP Project | Agoro Agge CEIP Project
| Single Wells Opportunities (F2200 & F1000) | Single Wells Opportunities (F2200 & F1000)
| Escravos NGC | Escravos NGC
| Shallow water offshore portfolio projects | Shallow water offshore portfolio projects
| HA/HB NAG Development (Phase 1) | HA/HB NAG Development (Phase 1)
| HA only | HA only
| AFAM Gas Supply 2 | AFAM Gas Supply 2
| SSAGS Step 3A | SSAGS Step 3A
| SSAGS Step 3B | SSAGS Step 3B
| West Asset Team | West Asset Team
| Rumuji Offtake Header Project | Rumuji Offtake Header Project
| Trans Ramos Pipeline Project. | Trans Ramos Pipeline Project.
| Okpokunou Cluster Development Project | Okpokunou Cluster Development Project
| Okpokunou Cluster Development Project_Dry Gas Option | Okpokunou Cluster Development Project_Dry Gas Option
| Okpokunou Cluster Development Project_Wet Gas Option | Okpokunou Cluster Development Project_Wet Gas Option
| BOGT Crude Oil Custody Transfer Metering Improvement Project | BOGT Crude Oil Custody Transfer Metering Improvement Project
| SNEPCo Projects | SNEPCo Projects
| OPL245 | OPL245
| Zabazaba | Zabazaba
| Etan | Etan
| OPL245 Exploration & Appraisal | OPL245 Exploration & Appraisal
| Elieli-1X | Elieli-1X
| Ifi-1X | Ifi-1X
| Zabazaba NW-1X | Zabazaba NW-1X
| Songu South-1X | Songu South-1X
| Zabazaba-3X | Zabazaba-3X
| OML118 | OML118
| Bonga SW | Bonga SW
| BSW/A Post-October 2008 | BSW/A Post-October 2008
| BSW/A Pre-September 2008 | BSW/A Pre-September 2008
| Bonga North | Bonga North
| BN_Subsurface | BN_Subsurface
| BN_Well_Engineering | BN_Well_Engineering
| BN_Drilling | BN_Drilling
| BN_PT/Completions | BN_PT/Completions
| BN_Surface_Engineering | BN_Surface_Engineering
| BN_Construction | BN_Construction
| BN_Civil/Marine | BN_Civil/Marine
| BN_Topsides | BN_Topsides
| BN_Logistics | BN_Logistics
| BN_Flow_Assurance | BN_Flow_Assurance
| BN_Subsea | BN_Subsea
| BN_Controls | BN_Controls
| BN_OR&A | BN_OR&A
| BN_Pipelines | BN_Pipelines
| BN_Regulatory | BN_Regulatory
| BN_Commercial | BN_Commercial
| BN_Political | BN_Political
| BN_HSE | BN_HSE
| BN_Economic | BN_Economic
| BN_Organization | BN_Organization
| BN_Archive | BN_Archive
| Bonga Phase 2 & STIFO | Bonga Phase 2 & STIFO
| Bonga Northwest | Bonga Northwest
| Bonga HSE (temp/do not add users) | Bonga HSE (temp/do not add users)
| E2P | E2P
| OPL322 | OPL322
| Bobo | Bobo
| Bobo-3X | Bobo-3X
| OML135 | OML135
| Bolia | Bolia
| OML 133 | OML 133
| Erha Area | Erha Area
| North | North
| Erha North | Erha North
| Erha Expansion | Erha Expansion
| Erha Main | Erha Main
| Bosi Area | Bosi Area
| Ser2 | Ser2
| Bosi Main | Bosi Main
| Gabon Projects | Gabon Projects
| Rabi Re-development | Rabi Re-development
| Appolonia | Appolonia
| Awoun | Awoun
| Black | Black
| Corporate Lands Risk Register | Corporate Lands Risk Register
| Swallow water offshore project | Swallow water offshore project
| West Asset Team | West Asset Team
| COG Nigeria-SPDC | COG Nigeria-SPDC
| â†“spdc | â†“spdc
| H Block HSSE Register (Cycles detected') | H Block HSSE Register (Cycles detected')
| H-Block (Import Tool) (Cycles detected') | H-Block (Import Tool) (Cycles detected')