## I&C Milestone loading
NG01020709 - INSTALLATION AND CONSTRUCTION CONTRACT
[6 empty] | 2019 |  |  | 2020
| I&C CONVERSION-1 TEMPLATE FOR PHASE 2 WORKS (ROADS, FOUNDATIONS, DRAINS, UNDERGROUND PIPING AND CABLING) | Contract Values |  | Discount Amounts |  | Variance |  |  | Variance
|  | Naira | US Dollars | Naira (2%) | US Dollars (1%) | Naira (2%) | US Dollars (1%) | Functional $ | Naira (2%) | US Dollars (1%) | Functional $
1 | Welding Procedure Specification
1.1 | Welding Procedure Specification (WPS) and Qualification (WPQ) for Carbon steel material 50% completed | 10654005.0375 | 0 | 10440924.9368 | 0 | 213080.1008 | 0 | 698.6233 |  |  | 0
1.2 | Welding Procedure Specification (WPS) and Qualification (WPQ) for Carbon steel material 100% completed | 10654005.0375 | 0 | 10440924.9368 | 0 | 213080.1008 | 0 | 698.6233 |  |  | 0
1.5 | Welding Procedure Specification (WPS) and Qualification (WPQ) for stainless steel and Duplex steel material 50% completed | 7990503.7781 | 0 | 7830693.7026 | 0 | 159810.0756 | 0 | 523.9675 |  |  | 0
1.6 | Welding Procedure Specification (WPS) and Qualification (WPQ) for stainless steel and Duplex steel material -100% completed | 7990503.7781 | 0 | 7830693.7026 | 0 | 159810.0756 |  | 523.9675 |  |  | 0
[8 empty] | 0 |  |  | 0
2 | Radiography Inspection | [6 empty] | 0 |  |  | 0
2.1 | Radiography Inspection of welded process piping - 100% completed | 10654005.0375 | 0 | 10440924.9368 | 0 | 213080.1008 |  | 698.6233 |  |  | 0
3 | Pile Testing | [6 empty] | 0 |  |  | 0
3.1 | Pile Integrity Test - 50% Completed | 26635012.5938 |  | 26102312.3419 | 0 |  |  | 0 | 532700.2519 |  | 1746.5582
3.2 | Pile Integrity Test - 100% Completed | 26635012.5938 | 0 | 26102312.3419 | 0 |  |  | 0 | 532700.2519 |  | 1746.5582
3.3 | Static load Test - 100% Completed | 5327002.5187 | 0 | 5220462.4684 | 0 |  |  | 0 | 106540.0504 |  | 349.3116
[8 empty] | 0 |  |  | 0
4 | SITE CONSTRUCTION - Foundations and Underground (U/G) Works | [6 empty] | 0 |  |  | 0
4.1 | Work procedures and resources in place and ready for Commencement of Site Construction Works | 6976064.7 | 8245.4974 | 6836543.406 | 8163.0424 | 139521.294 |  | 457.4469 |  |  | 0
4.2 | Remedial Site Preparation | [6 empty] | 0 |  |  | 0
4.2.1 | Removal of unsuitable materials - 20% | 12556916.46 | 14841.8954 | 12305778.1308 | 14693.4764 | 251138.3292 | 148.419 | 971.8233 |  |  | 0
4.2.2 | Removal of unsuitable materials - 40% | 12556916.46 | 14841.8954 | 12305778.1308 | 14693.4764 | 251138.3292 | 148.419 | 971.8233 |  |  | 0
4.2.3 | Removal of unsuitable materials - 60% | 12556916.46 | 14841.8954 | 12305778.1308 | 14693.4764 | 251138.3292 | 148.419 | 971.8233 |  |  | 0
4.2.4 | Removal of unsuitable materials - 80% | 12556916.46 | 14841.8954 | 12305778.1308 | 14693.4764 | 251138.3292 | 148.419 | 971.8233 |  |  | 0
4.2.5 | Removal of unsuitable materials - 100% | 12556916.46 | 14841.8954 | 12305778.1308 | 14693.4764 | 251138.3292 | 148.419 | 971.8233 |  |  | 0
4.3 | Remedial Sandfilling | [6 empty] | 0 |  |  | 0
4.3.1 | Remedial Sandfilling - 10% completed | 17440161.75 | 20613.7436 | 17091358.515 | 20407.6061 | 348803.235 | 206.1374 | 1349.7546 |  |  | 0
4.3.2 | Remedial Sandfilling - 20% completed | 17440161.75 | 20613.7436 | 17091358.515 | 20407.6061 | 348803.235 | 206.1374 | 1349.7546 |  |  | 0
4.3.3 | Remedial Sandfilling - 30% completed | 17440161.75 | 20613.7436 | 17091358.515 | 20407.6061 | 348803.235 | 206.1374 | 1349.7546 |  |  | 0
4.3.4 | Remedial Sandfilling - 40% completed | 17440161.75 | 20613.7436 | 17091358.515 | 20407.6061 | 348803.235 | 206.1374 | 1349.7546 |  |  | 0
4.3.5 | Remedial Sandfilling - 50% completed | 17440161.75 | 20613.7436 | 17091358.515 | 20407.6061 | 348803.235 | 206.1374 | 1349.7546 |  |  | 0
4.3.6 | Remedial Sandfilling - 60% completed | 17440161.75 | 20613.7436 | 17091358.515 | 20407.6061 | 348803.235 | 206.1374 | 1349.7546 |  |  | 0
4.3.7 | Remedial Sandfilling - 70% completed | 17440161.75 | 20613.7436 | 17091358.515 | 20407.6061 | 348803.235 | 206.1374 | 1349.7546 |  |  | 0
4.3.8 | Remedial Sandfilling - 80% completed | 17440161.75 | 20613.7436 | 17091358.515 | 20407.6061 | 348803.235 | 206.1374 | 1349.7546 |  |  | 0
4.3.9 | Remedial Sandfilling - 90% completed | 17440161.75 | 20613.7436 | 17091358.515 | 20407.6061 | 348803.235 | 206.1374 | 1349.7546 |  |  | 0
4.3.10 | Remedial Sandfilling - 100% completed | 17440161.75 | 20613.7436 | 17091358.515 | 20407.6061 | 348803.235 | 206.1374 | 1349.7546 |  |  | 0
4.4 | Grading to finished level | [6 empty] | 0 |  |  | 0
4.4.1 | Grading to finished level - 50% Completed | 17440161.75 | 20613.7436 | 17091358.515 | 20407.6061 | 348803.235 | 206.1374 | 1349.7546 |  |  | 0
4.4.2 | Grading to finished level - 100% Completed | 17440161.75 | 20613.7436 | 17091358.515 | 20407.6061 | 348803.235 | 206.1374 | 1349.7546 |  |  | 0
4.5 | Internal Roads | [6 empty] | 0 |  |  | 0
4.5.1 | Internal Roads including levelling, geotextiles, sub-base, base aggregates,C40/50 interlocking concrete paving stones and C25/30 concrete kerbs, road markins and road signs | 83712776.4 | 98945.969 | 82038520.872 | 97956.5093 |  |  | 0 | 1674255.528 | 989.4597 | 6478.8221
4.5.2 | Internal roads - 25% completed | 83712776.4 | 98945.969 | 82038520.872 | 97956.5093 |  |  | 0 | 1674255.528 | 989.4597 | 6478.8221
4.5.3 | Internal roads - 50% completed | 83712776.4 | 98945.969 | 82038520.872 | 97956.5093 |  |  | 0 | 1674255.528 | 989.4597 | 6478.8221
4.5.4 | Internal roads - 75% completed | 83712776.4 | 98945.969 | 82038520.872 | 97956.5093 |  |  | 0 | 1674255.528 | 989.4597 | 6478.8221
4.5.5 | Internal roads - 100% completed | 83712776.4 | 98945.969 | 82038520.872 | 97956.5093 |  |  | 0 | 1674255.528 | 989.4597 | 6478.8221
[8 empty] | 0 | 0 | 0 | 0
5 | SHALLOW FOUNDATION FOR EQUIPMENT SKIDS / MODULES/ PIPE RACKS/EQUIPMENT SHELTERS/PITS, | [6 empty] | 0 | 0 | 0 | 0
5.1 | Work procedures and resources in place and ready for Commencement of Shallow Foundations construction | 185747274 | 484402.995 | 182032328.52 | 479558.9651 |  |  | 0 | 3714945.48 | 4844.0299 | 17024.1791
5.2 | Shallow Foundations - 25% completed | 185747274 | 484402.995 | 182032328.52 | 479558.9651 |  |  | 0 | 3714945.48 | 4844.0299 | 17024.1791
5.3 | Shallow Foundations - 50% completed | 139310455.5 | 363302.2463 | 136524246.39 | 359669.2238 |  |  | 0 | 2786209.11 | 3633.0225 | 12768.1343
5.4 | Laser scanning of foundation positions 50% completed | 46436818.5 | 121100.7488 | 45508082.13 | 119889.7413 |  |  | 0 | 928736.37 | 1211.0075 | 4256.0448
5.5 | Shallow Foundations - 75% completed | 185747274 | 484402.995 | 182032328.52 | 479558.9651 |  |  | 0 | 3714945.48 | 4844.0299 | 17024.1791
5.6 | Shallow Foundations - 100% completed | 139310455.5 | 363302.2463 | 136524246.39 | 359669.2238 |  |  | 0 | 2786209.11 | 3633.0225 | 12768.1343
5.7 | Laser scanning of foundation positions 100% completed | 46436818.5 | 121100.7488 | 45508082.13 | 119889.7413 |  |  | 0 | 928736.37 | 1211.0075 | 4256.0448
[8 empty] | 0 | 0 | 0 | 0
6 | PILE FOUNDATIONS | [6 empty] | 0 | 0 | 0 | 0
6.1 | Work procedures and resources in place and ready for Commencement Pile Foundations Works | 6798402 | 4607.658 | 6662433.96 | 4561.5814 |  |  | 0 | 135968.04 | 46.0766 | 491.8734
6.2 | Pile Foundations Construction - 25% completed | 27193608 | 18430.632 | 26649735.84 | 18246.3257 |  |  | 0 | 543872.16 | 184.3063 | 1967.4937
6.3 | Pile Foundations Construction - 50% completed | 16996005 | 11519.145 | 16656084.9 | 11403.9536 |  |  | 0 | 339920.1 | 115.1915 | 1229.6836
6.4 | Laser scanning of pile foundation positions - 50% completed | 16996005 | 11519.145 | 16656084.9 | 11403.9536 |  |  | 0 | 339920.1 | 115.1915 | 1229.6836
6.5 | Pile Foundations Construction - 75% completed | 33992010 | 23038.29 | 33312169.8 | 22807.9071 |  |  | 0 | 679840.2 | 230.3829 | 2459.3672
6.6 | Pile Foundations Construction - 100% completed | 16996005 | 11519.145 | 16656084.9 | 11403.9536 |  |  | 0 | 339920.1 | 115.1915 | 1229.6836
6.7 | Laser scanning of pile foundation positions - 50% completed | 16996005 | 11519.145 | 16656084.9 | 11403.9536 |  |  | 0 | 339920.1 | 115.1915 | 1229.6836
[8 empty] | 0 | 0 | 0 | 0
7 | Pile Caps | [6 empty] | 0 | 0 | 0 | 0
7.1 | Work procedures and resources in place and ready for Commencement Pile Cap Works | 9817686 | 13417.4079 | 9621332.28 | 13283.2338 |  |  | 0 | 196353.72 | 134.1741 | 777.9568
7.2 | Pile Cap Construction - 25% completed | 39270744 | 53669.6316 | 38485329.12 | 53132.9353 |  |  | 0 | 785414.88 | 536.6963 | 3111.8271
7.3 | Pile Cap Construction - 50% completed | 49088430 | 67087.0395 | 48106661.4 | 66416.1691 |  |  | 0 | 981768.6 | 670.8704 | 3889.7838
7.4 | Pile Cap Construction - 75% completed | 49088430 | 67087.0395 | 48106661.4 | 66416.1691 |  |  | 0 | 981768.6 | 670.8704 | 3889.7838
7.5 | Pile Cap Construction - 100% completed | 49088430 | 67087.0395 | 48106661.4 | 66416.1691 |  |  | 0 | 981768.6 | 670.8704 | 3889.7838
[8 empty] | 0 | 0 | 0 | 0
8 | GENERAL CONCRETE(maintenance area and walkways) | [6 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
8.1 | Work procedures and resources in place and ready for Commencement of General Concrete Works including Rebars, mesh reinforcement, fomwork etc. Works | 11237062.5 | 12287.286 | 11012321.25 | 12164.4131 |  |  | 0 | 224741.25 | 122.8729 | 859.7294
8.2 | General Concrete Construction Works - 25% completed | 44948250 | 49149.144 | 44049285 | 48657.6526 |  |  | 0 | 898965 | 491.4914 | 3438.9177
8.3 | General Concrete Construction Works - 50% completed | 56185312.5 | 61436.43 | 55061606.25 | 60822.0657 |  |  | 0 | 1123706.25 | 614.3643 | 4298.6471
8.4 | General Concrete Construction Works - 75% completed | 56185312.5 | 61436.43 | 55061606.25 | 60822.0657 |  |  | 0 | 1123706.25 | 614.3643 | 4298.6471
8.5 | General Concrete Construction Works - 100% completed | 56185312.5 | 61436.43 | 55061606.25 | 60822.0657 |  |  | 0 | 1123706.25 | 614.3643 | 4298.6471
[8 empty] | 0 | 0 | 0 | 0
9 | Storm Water Drains | [6 empty] | 0 | 0 | 0 | 0
9.1 | Work procedures and resources in place and ready for Commencement of Storm Water Drains Works | 10162575 | 18094.725 | 9959323.5 | 17913.7778 |  |  | 0 | 203251.5 | 180.9473 | 847.3456
9.2 | Storm Water Drains Works - 25% completed | 40650300 | 72378.9 | 39837294 | 71655.111 |  |  | 0 | 813006 | 723.789 | 3389.3824
9.3 | Storm Water Drains Works - 50% completed | 50812875 | 90473.625 | 49796617.5 | 89568.8887 |  |  | 0 | 1016257.5 | 904.7363 | 4236.7281
9.4 | Storm Water Drains Works - 75% completed | 50812875 | 90473.625 | 49796617.5 | 89568.8887 |  |  | 0 | 1016257.5 | 904.7363 | 4236.7281
9.5 | Storm Water Drains Works - 100% completed | 50812875 | 90473.625 | 49796617.5 | 89568.8887 |  |  | 0 | 1016257.5 | 904.7363 | 4236.7281
[8 empty] | 0 | 0 | 0 | 0
10 | CONSTRUCTION OF UNDERGROUND PIPING | [6 empty] | 0 | 0 | 0 | 0
10.1 | Work procedures and resources in place and ready for Commencement of Underground Piping Works including trenching, laying and installation and make and break of flanges | 187182789.2321 | 454.952 | 183439133.4475 | 450.4025 |  |  | 0 | 3743655.7846 | 4.5495 | 12278.8308
10.2 | Underground Piping Works - 10% completed | 187182789.2321 | 454.952 | 183439133.4475 | 450.4025 |  |  | 0 | 3743655.7846 | 4.5495 | 12278.8308
10.3 | Underground Piping Works - 20% completed | 374365578.4643 | 909.904 | 366878266.895 | 900.8049 |  |  | 0 | 7487311.5693 | 9.099 | 24557.6616
10.4 | Underground Piping Works - 30% completed | 374365578.4643 | 909.904 | 366878266.895 | 900.8049 |  |  | 0 | 7487311.5693 | 9.099 | 24557.6616
10.5 | Underground Piping Works - 40% completed | 374365578.4643 | 909.904 | 366878266.895 | 900.8049 |  |  | 0 | 7487311.5693 | 9.099 | 24557.6616
10.6 | Underground Piping Works - 50% completed | 374365578.4643 | 909.904 | 366878266.895 | 900.8049 |  |  | 0 | 7487311.5693 | 9.099 | 24557.6616
10.7 | Underground Piping Works - 60% completed | 374365578.4643 | 909.904 | 366878266.895 | 900.8049 |  |  | 0 | 7487311.5693 | 9.099 | 24557.6616
10.8 | Underground Piping Works - 70% completed | 374365578.4643 | 909.904 | 366878266.895 | 900.8049 |  |  | 0 | 7487311.5693 | 9.099 | 24557.6616
10.9 | Underground Piping Works - 80% completed | 374365578.4643 | 909.904 | 366878266.895 | 900.8049 |  |  | 0 | 7487311.5693 | 9.099 | 24557.6616
10.10 | Underground Piping Works - 90% completed | 374365578.4643 | 909.904 | 366878266.895 | 900.8049 |  |  | 0 | 7487311.5693 | 9.099 | 24557.6616
10.11 | Underground Piping Works - 100% completed | 374365578.4643 | 909.904 | 366878266.895 | 900.8049 |  |  | 0 | 7487311.5693 | 9.099 | 24557.6616
[8 empty] | 0 | 0 | 0 | 0
11 | Laying and Termination of Underground Electrical Power Cables | [6 empty] | 0 | 0 | 0 | 0
11.1 | Work procedures and resources in place and ready for Commencement of Electrical construction Works | 18849849.3972 | 248.9927 | 18472852.4093 | 246.5027 |  |  | 0 | 376996.9879 | 2.4899 | 1238.5456
11.2 | Electrical construction and hook up works 50% Completed | 169648644.5748 | 2240.9339 | 166255671.6833 | 2218.5245 |  |  | 0 | 3392972.8915 | 22.4093 | 11146.9106
11.3 | Electrical construction and hook up works 100% Completed | 188498493.972 | 2489.9265 | 184728524.0926 | 2465.0272 |  |  | 0 | 3769969.8794 | 24.8993 | 12385.4562
[8 empty] | 0 | 0 | 0 | 0
12 | BLOCKWORK | [6 empty] | 0 | 0 | 0 | 0
12.1 | Work procedures and resources in place and ready for Commencement of Blockwork | 101250 | 0 | 99225 | 0 |  |  | 0 | 2025 | 0 | 6.6393
12.3 | Blockwork construction - 50% Completed | 911250 | 0 | 893025 | 0 |  |  | 0 | 18225 | 0 | 59.7541
12.4 | Blockwork construction - 100% Completed | 1012500 | 0 | 992250 | 0 |  |  | 0 | 20250 | 0 | 66.3934
[8 empty] | 0 | 0 | 0 | 0
13 | All other Civil works | [6 empty] | 0 | 0 | 0 | 0
13.1 | Work procedures and resources in place and ready for Commencement of Civil Infrastructure works (including mulseal DP application, MIRAFI's 140C, cement/ sand stabilization, landscaping, sand filling, gravel finish, etc.) | 5491300.5 | 0 | 5381474.49 | 0 |  |  | 0 | 109826.01 | 0 | 360.0853
13.3 | Civil Infrastructure works including landscaping - 50% Completed | 49421704.5 | 0 | 48433270.41 | 0 |  |  | 0 | 988434.09 | 0 | 3240.7675
13.5 | Civil Infrastructure works including landscaping - 100% Completed | 54913005 | 0 | 53814744.9 | 0 |  |  | 0 | 1098260.1 | 0 | 3600.8528
[8 empty] | 0 | 0 | 0 | 0
14 | Blasting and Painting Works | [6 empty] | 0 | 0 | 0 | 0
14.1 | Work procedures and resources in place and ready for Commencement of Blasting and Painting works | 1811109.375 | 0 | 1774887.1875 | 0 |  |  | 0 | 36222.1875 | 0 | 118.7613
14.3 | Blasting and Painting Works - 50% Completed | 16299984.375 | 0 | 15973984.6875 | 0 |  |  | 0 | 325999.6875 | 0 | 1068.8514
14.5 | Blasting and Painting Works - 100% Completed | 18111093.75 | 0 | 17748871.875 | 0 |  |  | 0 | 362221.875 | 0 | 1187.6127
|  | 6761923370.4618 | 4228785.1476 | 6626684903.0526 | 4186497.2961 | 6539712.2134 | 3215.744 | 24657.4234 | 135238467.4092 | 42287.8515 | 485692.6627
|  |  |  | 135238467.4092 | 42287.8515
|  | Total 2019 savings | 125747.1204
|  | Total 2020 savings | 692558.4697

## PO_3
PO-3 SUMMARY
PO-1 = Phase-1 Mobilisation
SECTION IV APPENDICES | [6 empty] | PO-2 = EPC Materials Procurement
Appendix 1: | Work Package 1A-1 - LUMPSUM elements in CONTRACT for the PTF Installation | [5 empty] | PO-3 = Phase-2 Mobilisation |  |  | 2019 |  |  | 2020
Work Package 1A –LUMPSUM elements of the PTF Installation |  |  | Original Rates |  | Rates with Discounts |  |  |  |  | Variance |  |  | Variance
S/N | DESCRIPTION | UNIT | ₦ | $ | ₦ | $ | REMARKS |  |  | Naira (2%) | US Dollars (1%) | Functional $ | Naira (2%) | US Dollars (1%) | Functional $
2 | Phase 2 Mobilisation | L/S | 1021505492.56 | 648374.43 | 1001075382.7088 | 641890.6857 | Raise as PO-3 Now | 3997572.7663 | 3924105.0552 | [10 empty] | Documentation | Non-Site Works
2.1.1 | Mobilisation of key Personnel for Project Management, Engineering, Procurement for Phase2 Mobilisation & EPC Activities completed |  | 153225823.884 | 97256.1645 | 150161307.4063 | 96283.6029 |  | 599635.9149 | 588615.7583 |  |  |  | 3064516.4777 | 972.5616 | 11020.1567 |  | 15%
2.1.2 | Inspection and Transportation of Temporary Facilities to Site- completed |  | 102150549.256 | 64837.443 | 100107538.2709 | 64189.0686 |  | 399757.2766 | 392410.5055 | 2043010.9851 | 648.3744 | 7346.7711 |  |  |  |  | 10%
2.1.3 | Furnishing of site offices, living accommodation, conference room, Dinning and Kitchen facilities 50% completed |  | 204301098.512 | 129674.886 | 200215076.5418 | 128378.1371 |  | 799514.5533 | 784821.011 | 4086021.9702 | 1296.7489 | 14693.5422 |  |  |  |  | 20%
2.1.4 | Furnishing of site offices, living accommodation, conference room, Dinning and Kitchen facilities 100% completed |  | 204301098.512 | 129674.886 | 200215076.5418 | 128378.1371 |  | 799514.5533 | 784821.011 | 4086021.9702 | 1296.7489 | 14693.5422 |  |  |  |  | 20%
2.1.5 | Equipment for Carbon Steel, Stainless steel, Re-bar, pre-cast fabrication workshops, Site Laboratories, concrete plant, etc 50% completed |  | 76612911.942 | 48628.0822 | 75080653.7032 | 48141.8014 |  | 299817.9575 | 294307.8791 |  |  |  | 1532258.2388 | 486.2808 | 5510.0783 |  | 7.5%
2.1.6 | Equipment for Carbon Steel, Stainless steel, Re-bar, pre-cast fabrication workshops, Site Laboratories, concrete plant, etc 100% completed |  | 76612911.942 | 48628.0822 | 75080653.7032 | 48141.8014 |  | 299817.9575 | 294307.8791 |  |  |  | 1532258.2388 | 486.2808 | 5510.0783 |  | 7.5%
2.1.7 | Mobilisation of personnel, equipment, and other resources for Phase 2 construction works and EPC Scope completed |  | 204301098.512 | 129674.886 | 200215076.5418 | 128378.1371 |  | 799514.5533 | 784821.011 |  |  |  | 4086021.9702 | 1296.7489 | 14693.5422 |  | 20%
4 | General Project Management Deliverables: Project Management for all work packages covering site administration, Construction Management, Work supervision, CONTRACTOR Light Vehicles Logistics, General overhead, etc throughout project duration. Refer to Scope of work for detailed description | L/S | 591587202.72 | 480455.78 | 579755458.6656 | 475651.2222 | Raise as PO-3 Now (Progress Payment) | 2420085.9529 | 2376488.7916
4.1 | At 2.5% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 | 295793.6014 | 120.1139 | 1089.929 |  |  |  |  | 2.5% | 2.5% | 2.5%
4.2 | At 5% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 | 295793.6014 | 120.1139 | 1089.929 |  |  |  |  | 2.5% | 5% | 2.5%
4.3 | At 7.5% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 | 295793.6014 | 120.1139 | 1089.929 |  |  |  |  | 2.5% | 7.5% | 2.5%
4.4 | At 10% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 | 295793.6014 | 120.1139 | 1089.929 |  |  |  |  | 2.5% | 10% | 2.5%
4.5 | At 12.5% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 | 295793.6014 | 120.1139 | 1089.929 |  |  |  |  | 2.5% | 12.5% | 2.5%
4.6 | At 15% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 | 295793.6014 | 120.1139 | 1089.929 |  |  |  |  | 2.5% | 15% | 2.5%
4.7 | At 17.5% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 | 295793.6014 | 120.1139 | 1089.929 |  |  |  |  | 2.5% | 17.5% | 2.5%
4.8 | At 20% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 | 295793.6014 | 120.1139 | 1089.929 |  |  |  |  | 2.5% | 20% | 2.5%
4.9 | At 22.5% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 |  |  |  | 295793.6014 | 120.1139 | 1089.929 |  | 2.5% | 22.5% | 2.5%
4.10 | At 25% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 |  |  |  | 295793.6014 | 120.1139 | 1089.929 |  | 2.5% | 25% | 2.5%
4.11 | At 30% Overall Project Completion |  | 29579360.136 | 24022.789 | 28987772.9333 | 23782.5611 |  | 121004.2976 | 118824.4396 |  |  |  | 591587.2027 | 240.2279 | 2179.8581 |  | 5% | 30% | 5%
4.12 | At 35% Overall Project Completion |  | 29579360.136 | 24022.789 | 28987772.9333 | 23782.5611 |  | 121004.2976 | 118824.4396 |  |  |  | 591587.2027 | 240.2279 | 2179.8581 |  | 5% | 35% | 5%
4.13 | At 40% Overall Project Completion |  | 29579360.136 | 24022.789 | 28987772.9333 | 23782.5611 |  | 121004.2976 | 118824.4396 |  |  |  | 591587.2027 | 240.2279 | 2179.8581 |  | 5% | 40% | 5%
4.14 | At 45% Overall Project Completion |  | 29579360.136 | 24022.789 | 28987772.9333 | 23782.5611 |  | 121004.2976 | 118824.4396 |  |  |  | 591587.2027 | 240.2279 | 2179.8581 |  | 5% | 45% | 5%
4.15 | At 50% Overall Project Completion |  | 29579360.136 | 24022.789 | 28987772.9333 | 23782.5611 |  | 121004.2976 | 118824.4396 |  |  |  | 591587.2027 | 240.2279 | 2179.8581 |  | 5% | 50% | 5%
4.16 | At 55% Overall Project Completion |  | 29579360.136 | 24022.789 | 28987772.9333 | 23782.5611 |  | 121004.2976 | 118824.4396 |  |  |  | 591587.2027 | 240.2279 | 2179.8581 |  | 5% | 55% | 5%
4.17 | At 60% Overall Project Completion |  | 29579360.136 | 24022.789 | 28987772.9333 | 23782.5611 |  | 121004.2976 | 118824.4396 |  |  |  | 591587.2027 | 240.2279 | 2179.8581 |  | 5% | 60% | 5%
4.18 | At 65% Overall Project Completion |  | 29579360.136 | 24022.789 | 28987772.9333 | 23782.5611 |  | 121004.2976 | 118824.4396 |  |  |  | 591587.2027 | 240.2279 | 2179.8581 |  | 5% | 65% | 5%
4.19 | At 70% Overall Project Completion |  | 29579360.136 | 24022.789 | 28987772.9333 | 23782.5611 |  | 121004.2976 | 118824.4396 |  |  |  | 591587.2027 | 240.2279 | 2179.8581 |  | 5% | 70% | 5%
4.20 | At 72.5% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 |  |  |  | 295793.6014 | 120.1139 | 1089.929 |  | 2.5% | 72.5% | 2.5%
4.21 | At 75% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 |  |  |  | 295793.6014 | 120.1139 | 1089.929 |  | 2.5% | 75% | 2.5%
4.22 | At 77.5% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 |  |  |  | 295793.6014 | 120.1139 | 1089.929 |  | 2.5% | 77.5% | 2.5%
4.23 | At 80% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 |  |  |  | 295793.6014 | 120.1139 | 1089.929 |  | 2.5% | 80% | 2.5%
4.24 | At 82.5% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 |  |  |  | 295793.6014 | 120.1139 | 1089.929 |  | 2.5% | 82.5% | 2.5%
4.25 | At 85% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 |  |  |  | 295793.6014 | 120.1139 | 1089.929 |  | 2.5% | 85% | 2.5%
4.26 | At 87.5% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 |  |  |  | 295793.6014 | 120.1139 | 1089.929 |  | 2.5% | 87.5% | 2.5%
4.27 | At 90% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 |  |  |  | 295793.6014 | 120.1139 | 1089.929 |  | 2.5% | 90% | 2.5%
4.28 | At 92.5% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 |  |  |  | 295793.6014 | 120.1139 | 1089.929 |  | 2.5% | 92.5% | 2.5%
4.29 | At 95% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 |  |  |  | 295793.6014 | 120.1139 | 1089.929 |  | 2.5% | 95% | 2.5%
4.30 | At 97.5% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 |  |  |  | 295793.6014 | 120.1139 | 1089.929 |  | 2.5% | 97.5% | 2.5%
4.31 | At 100% Overall Project Completion |  | 14789680.068 | 12011.3945 | 14493886.4666 | 11891.2806 |  | 60502.1488 | 59412.2198 |  |  |  | 295793.6014 | 120.1139 | 1089.929 |  | 2.5% | 100% | 2.5%
5 | Information Management and Technology | L/S | 12262725 |  | 12017470.5 | 0 | Raise as PO-3 Now | 40205.6557 | 39401.5426
5.1 | Provision of dedicated Internet Connectivity, IT Server Room, UPS, CAT6A Structured Cabling Syyem, etc; as specified in Section V, article 4.4.3 |  | 3065681.25 | 0 | 3004367.625 | 0 |  | 10051.4139 | 9850.3857 | 61313.625 | 0 | 201.0283 |  |  |  |  | 25%
5.2 | Provision of dedicated and secure IT/Telecoms equipment room, WAN setup, printers, plotters and Public address and Alarm Systems |  | 3065681.25 | 0 | 3004367.625 | 0 |  | 10051.4139 | 9850.3857 | 61313.625 | 0 | 201.0283 |  |  |  |  | 25%
5.3 | Provision of IP desk phones in offices, living rooms and construction work areas |  | 3065681.25 | 0 | 3004367.625 | 0 |  | 10051.4139 | 9850.3857 |  |  |  | 61313.625 | 0 | 201.0283 |  | 25%
5.4 | Provision of video/audio conference facilities in the Conference Room; including projectors and polycom roundatable device capable of interfacing with Company GID Network |  | 3065681.25 | 0 | 3004367.625 | 0 |  | 10051.4139 | 9850.3857 |  |  |  | 61313.625 | 0 | 201.0283 |  | 25%
6 | General HSE | L/S | 22536900 | 405164.85 | 22086162 | 401113.2015 | Raise as PO-3 Now | 479056.3254 | 473526.8474
6.1 | JHA for Temporary camp activities completed |  | 563422.5 | 10129.1213 | 552154.05 | 10027.83 |  | 11976.4081 | 11838.1712 | 11268.45 | 101.2912 | 138.237 |  |  |  |  | 2.5%
6.2 | JHA for Permanent Works completed |  | 563422.5 | 10129.1213 | 552154.05 | 10027.83 |  | 11976.4081 | 11838.1712 |  |  |  | 11268.45 | 101.2912 | 138.237 |  | 2.5%
6.3 | Relevant PPEs Available/Inspected at commencement |  | 563422.5 | 10129.1213 | 552154.05 | 10027.83 |  | 11976.4081 | 11838.1712 | 11268.45 | 101.2912 | 138.237 |  |  |  |  | 2.5%
6.4 | Relevant PPEs Available/Inspected at 50% completion |  | 1126845 | 20258.2425 | 1104308.1 | 20055.6601 |  | 23952.8163 | 23676.3424 |  |  |  | 22536.9 | 202.5824 | 276.4739 |  | 5%
6.5 | Relevant PPEs Available/Inspected at 90% completion |  | 1126845 | 20258.2425 | 1104308.1 | 20055.6601 |  | 23952.8163 | 23676.3424 |  |  |  | 22536.9 | 202.5824 | 276.4739 |  | 5%
6.6 | Land Transport HSSE Documentation - Done/Implemented |  | 1126845 | 20258.2425 | 1104308.1 | 20055.6601 |  | 23952.8163 | 23676.3424 | 22536.9 | 202.5824 | 276.4739 |  |  |  |  | 5% |  |  | 23952.8163
6.7 | Worksite Hazard Management System completed and operational |  | 1126845 | 20258.2425 | 1104308.1 | 20055.6601 |  | 23952.8163 | 23676.3424 | 22536.9 | 202.5824 | 276.4739 |  |  |  |  | 5% |  |  | 23952.8163
6.8 | Care-for-People Plan - prepared/implemented |  | 563422.5 | 10129.1213 | 552154.05 | 10027.83 |  | 11976.4081 | 11838.1712 | 11268.45 | 101.2912 | 138.237 |  |  |  |  | 2.5% |  |  | 11976.4081
6.9 | HSSE Clearance Certificate Issued for Mobilization for Temporary Facilities Construction |  | 1126845 | 20258.2425 | 1104308.1 | 20055.6601 |  | 23952.8163 | 23676.3424 | 22536.9 | 202.5824 | 276.4739 |  |  |  |  | 5%
6.1 | HSSE Clearance Certificate Issued for Mobilization for Permanent Facilities Construction |  | 1126845 | 20258.2425 | 1104308.1 | 20055.6601 |  | 23952.8163 | 23676.3424 | 22536.9 | 202.5824 | 276.4739 |  |  |  |  | 5%
6.11 | At 10% Overall Project Completion |  | 2253690 | 40516.485 | 2208616.2 | 40111.3201 |  | 47905.6325 | 47352.6847 | 45073.8 | 405.1649 | 552.9478 |  |  |  |  | 10%
6.12 | At 25% Overall Project Completion |  | 2253690 | 40516.485 | 2208616.2 | 40111.3201 |  | 47905.6325 | 47352.6847 | 45073.8 | 405.1649 | 552.9478 |  |  |  |  | 10%
6.13 | At 50% Overall Project Completion |  | 2253690 | 40516.485 | 2208616.2 | 40111.3201 |  | 47905.6325 | 47352.6847 |  |  |  | 45073.8 | 405.1649 | 552.9478 |  | 10%
6.14 | At 75% Overall Project Completion |  | 2253690 | 40516.485 | 2208616.2 | 40111.3201 |  | 47905.6325 | 47352.6847 |  |  |  | 45073.8 | 405.1649 | 552.9478 |  | 10%
6.15 | At 90% Overall Project Completion |  | 2253690 | 40516.485 | 2208616.2 | 40111.3201 |  | 47905.6325 | 47352.6847 |  |  |  | 45073.8 | 405.1649 | 552.9478 |  | 10%
6.16 | At 100% Overall Project Completion |  | 2253690 | 40516.485 | 2208616.2 | 40111.3201 |  | 47905.6325 | 47352.6847 |  |  |  | 45073.8 | 405.1649 | 552.9478 |  | 10%
7 | Social Performance | L/S | 12709044 |  | 12454863.12 | 0 | Raise as PO-3 Now | 41668.9967 | 40835.6168
7.1 | Sustainable Community Development Plan, Workshop and procedures issued and Approved by COMPANY |  | 1270904.4 | 0 | 1245486.312 | 0 |  | 4166.8997 | 4083.5617 | 25418.088 | 0 | 83.338 |  |  |  |  | 10% |  |  | 4166.8997
7.2 | Sustainable Community Engagements at 10% Completion |  | 1906356.6 | 0 | 1868229.468 | 0 |  | 6250.3495 | 6125.3425 | 38127.132 | 0 | 125.007 |  |  |  |  | 15%
7.3 | Sustainable Community Engagements at 25% Completion |  | 2541808.8 | 0 | 2490972.624 | 0 |  | 8333.7993 | 8167.1234 | 50836.176 | 0 | 166.676 |  |  |  |  | 20%
7.4 | Sustainable Community Engagements at 50% Completion |  | 2541808.8 | 0 | 2490972.624 | 0 |  | 8333.7993 | 8167.1234 |  |  |  | 50836.176 | 0 | 166.676 |  | 20%
7.5 | Sustainable Community Engagements at 75% Completion |  | 3177261 | 0 | 3113715.78 | 0 |  | 10417.2492 | 10208.9042 |  |  |  | 63545.22 | 0 | 208.345 |  | 25%
7.6 | Sustainable Community Engagements at 100% Completion |  | 1270904.4 | 0 | 1245486.312 | 0 |  | 4166.8997 | 4083.5617 |  |  |  | 25418.088 | 0 | 83.338 |  | 10%
9 | CONTRACTOR Premob Documentation at Phase 2 | L/S | 114753332.9 | 59784.76 | 112458266.242 | 59186.9124 | Raise as PO-3 Now | 436025.1957 | 427902.5394 | [10 empty] | 436025.1957
9.1 | Pre-Mob Certificate for heavy duty/ earthmoving equipment secured at Phase 2 |  | 17212999.935 | 8967.714 | 16868739.9363 | 8878.0369 |  | 65403.7794 | 64185.3809 |  |  |  | 344259.9987 | 89.6771 | 1218.3984 |  | 15%
9.2 | Pre-Mob Certificate for heavy duty/ earthmoving equipment secured at Phase 3 |  | 17212999.935 | 8967.714 | 16868739.9363 | 8878.0369 |  | 65403.7794 | 64185.3809 |  |  |  | 344259.9987 | 89.6771 | 1218.3984 |  | 15%
9.3 | Pre-Mob Certificate for light vehicles secured |  | 22950666.58 | 11956.952 | 22491653.2484 | 11837.3825 |  | 87205.0391 | 85580.5079 | 459013.3316 | 119.5695 | 1624.5313 |  |  |  |  | 20%
9.4 | Workers Accommodation Certified |  | 22950666.58 | 11956.952 | 22491653.2484 | 11837.3825 |  | 87205.0391 | 85580.5079 | 459013.3316 | 119.5695 | 1624.5313 |  |  |  |  | 20%
9.5 | Lifting IADC Cerfitication Verified |  | 22950666.58 | 11956.952 | 22491653.2484 | 11837.3825 |  | 87205.0391 | 85580.5079 |  |  |  | 459013.3316 | 119.5695 | 1624.5313 |  | 20%
9.6 | HSSE Onboarding Induction Pack approved |  | 11475333.29 | 5978.476 | 11245826.6242 | 5918.6912 |  | 43602.5196 | 42790.2539 |  |  |  | 229506.6658 | 59.7848 | 812.2656 |  | 10%
11 | Running cost for Standard Office accommodation/ Site Accommocation as defined in 1A for 40 SPDC personnel throught duration of Site Works duration of CONTRACT | LS | 222791250 |  | 218335425 | 0 | Raise as PO-3 Now (Progress Payment) | 730463.1148 | 715853.8525
11.1 | At 2.5% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 | 111395.625 | 0 | 365.2316 |  |  |  |  | 2.5% | 2.5% | 2.5%
11.2 | At 5% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 | 111395.625 | 0 | 365.2316 |  |  |  |  | 2.5% | 5% | 2.5%
11.3 | At 7.5% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 | 111395.625 | 0 | 365.2316 |  |  |  |  | 2.5% | 7.5% | 2.5%
11.4 | At 10% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 | 111395.625 | 0 | 365.2316 |  |  |  |  | 2.5% | 10% | 2.5%
11.5 | At 12.5% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 | 111395.625 | 0 | 365.2316 |  |  |  |  | 2.5% | 12.5% | 2.5%
11.6 | At 15% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 | 111395.625 | 0 | 365.2316 |  |  |  |  | 2.5% | 15% | 2.5%
11.7 | At 17.5% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 | 111395.625 | 0 | 365.2316 |  |  |  |  | 2.5% | 17.5% | 2.5%
11.8 | At 20% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 | 111395.625 | 0 | 365.2316 |  |  |  |  | 2.5% | 20% | 2.5%
11.9 | At 22.5% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 | 111395.625 | 0 | 365.2316 |  |  |  |  | 2.5% | 22.5% | 2.5%
11.10 | At 25% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 |  |  |  | 111395.625 | 0 | 365.2316 |  | 2.5% | 25% | 2.5%
11.11 | At 30% Overall Project Completion |  | 11139562.5 | 0 | 10916771.25 | 0 |  | 36523.1557 | 35792.6926 |  |  |  | 222791.25 | 0 | 730.4631 |  | 5% | 30% | 5%
11.12 | At 35% Overall Project Completion |  | 11139562.5 | 0 | 10916771.25 | 0 |  | 36523.1557 | 35792.6926 |  |  |  | 222791.25 | 0 | 730.4631 |  | 5% | 35% | 5%
11.13 | At 40% Overall Project Completion |  | 11139562.5 | 0 | 10916771.25 | 0 |  | 36523.1557 | 35792.6926 |  |  |  | 222791.25 | 0 | 730.4631 |  | 5% | 40% | 5%
11.14 | At 45% Overall Project Completion |  | 11139562.5 | 0 | 10916771.25 | 0 |  | 36523.1557 | 35792.6926 |  |  |  | 222791.25 | 0 | 730.4631 |  | 5% | 45% | 5%
11.15 | At 50% Overall Project Completion |  | 11139562.5 | 0 | 10916771.25 | 0 |  | 36523.1557 | 35792.6926 |  |  |  | 222791.25 | 0 | 730.4631 |  | 5% | 50% | 5%
11.16 | At 55% Overall Project Completion |  | 11139562.5 | 0 | 10916771.25 | 0 |  | 36523.1557 | 35792.6926 |  |  |  | 222791.25 | 0 | 730.4631 |  | 5% | 55% | 5%
11.17 | At 60% Overall Project Completion |  | 11139562.5 | 0 | 10916771.25 | 0 |  | 36523.1557 | 35792.6926 |  |  |  | 222791.25 | 0 | 730.4631 |  | 5% | 60% | 5%
11.18 | At 65% Overall Project Completion |  | 11139562.5 | 0 | 10916771.25 | 0 |  | 36523.1557 | 35792.6926 |  |  |  | 222791.25 | 0 | 730.4631 |  | 5% | 65% | 5%
11.19 | At 70% Overall Project Completion |  | 11139562.5 | 0 | 10916771.25 | 0 |  | 36523.1557 | 35792.6926 |  |  |  | 222791.25 | 0 | 730.4631 |  | 5% | 70% | 5%
11.20 | At 72.5% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 |  |  |  | 111395.625 | 0 | 365.2316 |  | 2.5% | 72.5% | 2.5%
11.21 | At 75% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 |  |  |  | 111395.625 | 0 | 365.2316 |  | 2.5% | 75% | 2.5%
11.22 | At 77.5% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 |  |  |  | 111395.625 | 0 | 365.2316 |  | 2.5% | 77.5% | 2.5%
11.23 | At 80% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 |  |  |  | 111395.625 | 0 | 365.2316 |  | 2.5% | 80% | 2.5%
11.24 | At 82.5% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 |  |  |  | 111395.625 | 0 | 365.2316 |  | 2.5% | 82.5% | 2.5%
11.25 | At 85% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 |  |  |  | 111395.625 | 0 | 365.2316 |  | 2.5% | 85% | 2.5%
11.26 | At 87.5% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 |  |  |  | 111395.625 | 0 | 365.2316 |  | 2.5% | 87.5% | 2.5%
11.27 | At 90% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 |  |  |  | 111395.625 | 0 | 365.2316 |  | 2.5% | 90% | 2.5%
11.28 | At 92.5% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 |  |  |  | 111395.625 | 0 | 365.2316 |  | 2.5% | 92.5% | 2.5%
11.29 | At 95% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 |  |  |  | 111395.625 | 0 | 365.2316 |  | 2.5% | 95% | 2.5%
11.30 | At 97.5% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 |  |  |  | 111395.625 | 0 | 365.2316 |  | 2.5% | 97.5% | 2.5%
11.31 | At 100% Overall Project Completion |  | 5569781.25 | 0 | 5458385.625 | 0 |  | 18261.5779 | 17896.3463 |  |  |  | 111395.625 | 0 | 365.2316 |  | 2.5% | 100% | 2.5%
12 | Provision of 1 No. Toyota HIACE Bus (model HiAce SLWB Commuter Bus -newly purchased; diesel engine-driven until end of Succesful Performance Tests.throughout project duration. This include driver, maintenance, fueling etc | LS | 28096002 |  | 27534081.96 | 0 | Raise as PO-3 Now (Progress Payment) | 92118.0393 | 90275.6786
12.1 | At Delivery |  | 11238400.8 | 0 | 11013632.784 | 0 |  | 36847.2157 | 36110.2714 | 224768.016 | 0 | 736.9443 |  |  |  |  | 40%
12.2 | At 10% Overall Project Completion |  | 1685760.12 | 0 | 1652044.9176 | 0 |  | 5527.0824 | 5416.5407 | 33715.2024 | 0 | 110.5416 |  |  |  |  | 6%
12.3 | At 20% Overall Project Completion |  | 1685760.12 | 0 | 1652044.9176 | 0 |  | 5527.0824 | 5416.5407 | 33715.2024 | 0 | 110.5416 |  |  |  |  | 6%
12.4 | At 30% Overall Project Completion |  | 1685760.12 | 0 | 1652044.9176 | 0 |  | 5527.0824 | 5416.5407 |  |  |  | 33715.2024 | 0 | 110.5416 |  | 6%
12.5 | At 40% Overall Project Completion |  | 1685760.12 | 0 | 1652044.9176 | 0 |  | 5527.0824 | 5416.5407 |  |  |  | 33715.2024 | 0 | 110.5416 |  | 6%
12.6 | At 50% Overall Project Completion |  | 1685760.12 | 0 | 1652044.9176 | 0 |  | 5527.0824 | 5416.5407 |  |  |  | 33715.2024 | 0 | 110.5416 |  | 6%
12.7 | At 60% Overall Project Completion |  | 1685760.12 | 0 | 1652044.9176 | 0 |  | 5527.0824 | 5416.5407 |  |  |  | 33715.2024 | 0 | 110.5416 |  | 6%
12.8 | At 70% Overall Project Completion |  | 1685760.12 | 0 | 1652044.9176 | 0 |  | 5527.0824 | 5416.5407 |  |  |  | 33715.2024 | 0 | 110.5416 |  | 6%
12.9 | At 80% Overall Project Completion |  | 1685760.12 | 0 | 1652044.9176 | 0 |  | 5527.0824 | 5416.5407 |  |  |  | 33715.2024 | 0 | 110.5416 |  | 6%
12.10 | At 90% Overall Project Completion |  | 1685760.12 | 0 | 1652044.9176 | 0 |  | 5527.0824 | 5416.5407 |  |  |  | 33715.2024 | 0 | 110.5416 |  | 6%
12.11 | At 100% Overall Project Completion |  | 1685760.12 | 0 | 1652044.9176 | 0 |  | 5527.0824 | 5416.5407 |  |  |  | 33715.2024 | 0 | 110.5416 |  | 6%
13 | Provision of 2Nos 4WD Toyota hilux vehicles (model Hilux 4WD dual cabin-diesel engine driven pick-up type vehicles newly purchased). Cost includes driver, maintenance, fueling etc | LS | 51960075 |  | 50920873.5 | 0 | Raise as PO-3 Now (Progress Payment) | 170360.9016 | 166953.6836
13.1 | At delivery of two (2) Vehicles |  | 20784030 | 0 | 20368349.4 | 0 |  | 68144.3607 | 66781.4734 | 415680.6 | 0 | 1362.8872 |  |  |  |  | 40%
13.2 | At 10% Overall Project Completion |  | 3117604.5 | 0 | 3055252.41 | 0 |  | 10221.6541 | 10017.221 | 62352.09 | 0 | 204.4331 |  |  |  |  | 6%
13.3 | At 20% Overall Project Completion |  | 3117604.5 | 0 | 3055252.41 | 0 |  | 10221.6541 | 10017.221 | 62352.09 | 0 | 204.4331 |  |  |  |  | 6%
13.4 | At 30% Overall Project Completion |  | 3117604.5 | 0 | 3055252.41 | 0 |  | 10221.6541 | 10017.221 | 62352.09 | 0 | 204.4331 |  |  |  |  | 6%
13.5 | At 40% Overall Project Completion |  | 3117604.5 | 0 | 3055252.41 | 0 |  | 10221.6541 | 10017.221 |  |  |  | 62352.09 | 0 | 204.4331 |  | 6%
13.6 | At 50% Overall Project Completion |  | 3117604.5 | 0 | 3055252.41 | 0 |  | 10221.6541 | 10017.221 |  |  |  | 62352.09 | 0 | 204.4331 |  | 6%
13.7 | At 60% Overall Project Completion |  | 3117604.5 | 0 | 3055252.41 | 0 |  | 10221.6541 | 10017.221 |  |  |  | 62352.09 | 0 | 204.4331 |  | 6%
13.8 | At 70% Overall Project Completion |  | 3117604.5 | 0 | 3055252.41 | 0 |  | 10221.6541 | 10017.221 |  |  |  | 62352.09 | 0 | 204.4331 |  | 6%
13.9 | At 80% Overall Project Completion |  | 3117604.5 | 0 | 3055252.41 | 0 |  | 10221.6541 | 10017.221 |  |  |  | 62352.09 | 0 | 204.4331 |  | 6%
13.10 | At 90% Overall Project Completion |  | 3117604.5 | 0 | 3055252.41 | 0 |  | 10221.6541 | 10017.221 |  |  |  | 62352.09 | 0 | 204.4331 |  | 6%
13.11 | At 100% Overall Project Completion |  | 3117604.5 | 0 | 3055252.41 | 0 |  | 10221.6541 | 10017.221 |  |  |  | 62352.09 | 0 | 204.4331 |  | 6%
14 | Nigerian Content and Community Content Requirements (Human capacity development) | L/S | 115885595.52 |  | 113567883.6096 | 0 | Raise as PO-3 Now (Progress Payment) | 379952.7722 | 372353.7168 | [10 empty] | 379952.7722 | 379952.7722
14.1 | HCD Plan Approved |  | 11588559.552 | 0 | 11356788.361 | 0 |  | 37995.2772 | 37235.3717 | 231771.191 | 0 | 759.9055 |  |  |  |  | 10%
14.1 | Trainings Commenced |  | 23177119.104 | 0 | 22713576.7219 | 0 |  | 75990.5544 | 74470.7434 |  |  |  | 62352.09 | 0 | 204.4331 |  | 20%
14.1 | Training 50% Completed |  | 23177119.104 | 0 | 22713576.7219 | 0 |  | 75990.5544 | 74470.7434 |  |  |  | 2317711.9104 | 0 | 7599.0554 |  | 20%
14.1 | Training 100% Completed |  | 23177119.104 | 0 | 22713576.7219 | 0 |  | 75990.5544 | 74470.7434 |  |  |  | 231771.191 | 0 | 759.9055 |  | 20%
14.1 | Confirm Certificates issued to all trainees |  | 34765678.656 | 0 | 34070365.0829 | 0 |  | 113985.8317 | 111706.115 |  |  |  | 463542.3821 | 0 | 1519.8111 |  | 30%
15 | Asset Management Deliverables | L/S | 40087695 |  | 39285941.1 | 0 | Raise as PO-3 Now (Progress Payment) | 131435.0656 | 128806.3643
15.1 | Work procedure and resources in place and qualified CONTRACTOR staff deployed for developing of all project handover data as listed in the SoW |  | 4008769.5 | 0 | 3928594.11 | 0 |  | 13143.5066 | 12880.6364 | [7 empty] | 10% |  |  | 13143.5066 | 13143.5066
15.2 | Develop and implement Concurrent Operations Plan (COP) as listed in Article 9 of the Scope of Work Section IV |  | 4008769.5 | 0 | 3928594.11 | 0 |  | 13143.5066 | 12880.6364 | [7 empty] | 10% |  |  | 13143.5066 | 13143.5066
15.3 | Mobilize resources for startup and Initial Operations Phase |  | 8017539 | 0 | 7857188.22 | 0 |  | 26287.0131 | 25761.2729 | [7 empty] | 20%
15.4 | Support for Performance Tests and Outstanding Punchlist items |  | 8017539 | 0 | 7857188.22 | 0 |  | 26287.0131 | 25761.2729 | [7 empty] | 20%
15.5 | Management of limited site infrastructure to follow-up Operations and Maintenance problems during innitial Operations Period. |  | 8017539 | 0 | 7857188.22 | 0 |  | 26287.0131 | 25761.2729 | [7 empty] | 20%
15.6 | All personnel and records available for Pre Start-Up Audit and Start-Up Review |  | 8017539 | 0 | 7857188.22 | 0 |  | 26287.0131 | 25761.2729 | [7 empty] | 20% |  |  | 26287.0131 | 26287.0131
16 | Materials Tracking, Management & Preservation | L/S | 51495343.5 |  | 50465436.63 | 0 | Raise as PO-3 Now (Progress Payment) | 168837.1918 | 165460.448
16.1 | Setup Materials Track & Trace System |  | 12873835.875 | 0 | 12616359.1575 | 0 |  | 42209.298 | 41365.112 |  |  |  | 160350.78 | 0 | 525.7403 |  | 25%
16.2 | Deploy Preservation Team, Tools and Equipment |  | 7724301.525 | 0 | 7569815.4945 | 0 |  | 25325.5788 | 24819.0672 |  |  |  | 160350.78 | 0 | 525.7403 |  | 15%
16.3 | At 20% Overall Construction Completion |  | 5149534.35 | 0 | 5046543.663 | 0 |  | 16883.7192 | 16546.0448 |  |  |  | 1029906.87 | 0 | 3376.7438 |  | 10%
16.4 | At 30% Overall Construction Completion |  | 5149534.35 | 0 | 5046543.663 | 0 |  | 16883.7192 | 16546.0448 |  |  |  | 257476.7175 | 0 | 844.186 |  | 10%
16.5 | At 40% Overall Construction Completion |  | 5149534.35 | 0 | 5046543.663 | 0 |  | 16883.7192 | 16546.0448 |  |  |  | 154486.0305 | 0 | 506.5116 |  | 10%
16.6 | At 60% Overall Construction Completion |  | 5149534.35 | 0 | 5046543.663 | 0 |  | 16883.7192 | 16546.0448 |  |  |  | 102990.687 | 0 | 337.6744 |  | 10%
16.7 | At 80% Overall Construction Completion |  | 5149534.35 | 0 | 5046543.663 | 0 |  | 16883.7192 | 16546.0448 |  |  |  | 102990.687 | 0 | 337.6744 |  | 10%
16.8 | At 100% Overall Construction Completion |  | 5149534.35 | 0 | 5046543.663 | 0 |  | 16883.7192 | 16546.0448 |  |  |  | 102990.687 | 0 | 337.6744 |  | 10%
17 | Materials Handling at Project Site | L/S | 63044400 |  | 61783512 | 0 | Raise as PO-3 Now (Progress Payment) | 206702.9508 | 202568.8918
171 | Setup Secured Materials Laydown areas around the construction site |  | 9456660 | 0 | 9267526.8 | 0 |  | 31005.4426 | 30385.3338 |  |  |  | 102990.687 | 0 | 337.6744 |  | 15%
17.2 | Deploy Materials Handling Personnel, Equipment, systems and procedures |  | 15761100 | 0 | 15445878 | 0 |  | 51675.7377 | 50642.223 |  |  |  | 102990.687 | 0 | 337.6744 |  | 25%
17.3 | At 20% Overall Project Completion |  | 4728330 | 0 | 4633763.4 | 0 |  | 15502.7213 | 15192.6669 |  |  |  | 1260888 | 0 | 4134.059 |  | 7.5%
17.4 | At 30% Overall Project Completion |  | 4728330 | 0 | 4633763.4 | 0 |  | 15502.7213 | 15192.6669 |  |  |  | 189133.2 | 0 | 620.1089 |  | 7.5%
17.5 | At 40% Overall Project Completion |  | 4728330 | 0 | 4633763.4 | 0 |  | 15502.7213 | 15192.6669 |  |  |  | 315222 | 0 | 1033.5148 |  | 7.5%
17.6 | At 50% Overall Project Completion |  | 4728330 | 0 | 4633763.4 | 0 |  | 15502.7213 | 15192.6669 |  |  |  | 94566.6 | 0 | 310.0544 |  | 7.5%
17.7 | At 60% Overall Project Completion |  | 4728330 | 0 | 4633763.4 | 0 |  | 15502.7213 | 15192.6669 |  |  |  | 94566.6 | 0 | 310.0544 |  | 7.5%
17.8 | At 70% Overall Project Completion |  | 4728330 | 0 | 4633763.4 | 0 |  | 15502.7213 | 15192.6669 |  |  |  | 94566.6 | 0 | 310.0544 |  | 7.5%
17.9 | At 80% Overall Project Completion |  | 4728330 | 0 | 4633763.4 | 0 |  | 15502.7213 | 15192.6669 |  |  |  | 94566.6 | 0 | 310.0544 |  | 7.5%
17.10 | At 100% Overall Project Completion |  | 4728330 | 0 | 4633763.4 | 0 |  | 15502.7213 | 15192.6669 |  |  |  | 94566.6 | 0 | 310.0544 |  | 7.5%
18 | Health: Health Risk Management, Retainership Clinic, establishment and operation of Site Clinic, MEDEVAC Facility, Freedom to Work (FTW), etc) | L/S | 21503682.56 |  | 21073608.9088 | 0 |  | 70503.8772 | 69093.7997
18.1 | Health Risk Assessment Completed |  | 1075184.128 | 0 | 1053680.4454 | 0 |  | 3525.1939 | 3454.69 | 21503.6826 | 0 | 70.5039 |  |  |  |  | 5% |  |  | 3525.1939 | 3525.1939
18.2 | Retainership Clinic Approved |  | 1075184.128 | 0 | 1053680.4454 | 0 |  | 3525.1939 | 3454.69 | 21503.6826 | 0 | 70.5039 |  |  |  |  | 5%
18.3 | Site Clinic Commenced |  | 2150368.256 | 0 | 2107360.8909 | 0 |  | 7050.3877 | 6909.38 | 43007.3651 | 0 | 141.0078 |  |  |  |  | 10%
18.4 | Medevac Facilities in Place |  | 1612776.192 | 0 | 1580520.6682 | 0 |  | 5287.7908 | 5182.035 | 32255.5238 | 0 | 105.7558 |  |  |  |  | 7.5%
18.5 | Health management at 10% completion |  | 1612776.192 | 0 | 1580520.6682 | 0 |  | 5287.7908 | 5182.035 | 32255.5238 | 0 | 105.7558 |  |  |  |  | 7.5%
18.6 | Health management at 20% completion |  | 1612776.192 | 0 | 1580520.6682 | 0 |  | 5287.7908 | 5182.035 | 32255.5238 | 0 | 105.7558 |  |  |  |  | 7.5%
18.7 | Health management at 30% completion |  | 1612776.192 | 0 | 1580520.6682 | 0 |  | 5287.7908 | 5182.035 |  |  |  | 32255.5238 | 0 | 105.7558 |  | 7.5%
18.8 | Health management at 40% completion |  | 1612776.192 | 0 | 1580520.6682 | 0 |  | 5287.7908 | 5182.035 |  |  |  | 32255.5238 | 0 | 105.7558 |  | 7.5%
18.9 | Health management at 50% completion |  | 1612776.192 | 0 | 1580520.6682 | 0 |  | 5287.7908 | 5182.035 |  |  |  | 32255.5238 | 0 | 105.7558 |  | 7.5%
18.10 | Health management at 60% completion |  | 1612776.192 | 0 | 1580520.6682 | 0 |  | 5287.7908 | 5182.035 |  |  |  | 32255.5238 | 0 | 105.7558 |  | 7.5%
18.11 | Health management at 70% completion |  | 1612776.192 | 0 | 1580520.6682 | 0 |  | 5287.7908 | 5182.035 |  |  |  | 32255.5238 | 0 | 105.7558 |  | 7.5%
18.12 | Health management at 80% completion |  | 1612776.192 | 0 | 1580520.6682 | 0 |  | 5287.7908 | 5182.035 |  |  |  | 32255.5238 | 0 | 105.7558 |  | 7.5%
18.13 | Health management at 90% completion |  | 1612776.192 | 0 | 1580520.6682 | 0 |  | 5287.7908 | 5182.035 |  |  |  | 32255.5238 | 0 | 105.7558 |  | 7.5%
18.14 | Health management at 100% completion |  | 1075184.128 | 0 | 1053680.4454 | 0 |  | 3525.1939 | 3454.69 |  |  |  | 32255.5238 | 0 | 105.7558 |  | 5%
19 | Construction Site Safety Standardisation (CSSS) Program and Requirements, including HSSE and SP related Training | L/S | 76519404.99 |  | 74989016.8902 | 0 | Raise as PO-3 Now | 250883.295 | 245865.6291
19.1 | CSSS Roadmap Prepared and Starting Strong Workshop held |  | 7651940.499 | 0 | 7498901.689 | 0 |  | 25088.3295 | 24586.5629 | 153038.81 | 0 | 501.7666 |  |  |  |  | 10% |  |  | 25088.3295 | 25088.3295
19.2 | DROPS Campaign Launched and DROPS Prevention Tools Inspected and approved |  | 22955821.497 | 0 | 22496705.0671 | 0 |  | 75264.9885 | 73759.6887 |  |  |  | 21503.6826 | 0 | 70.5039 |  | 30% |  |  | 75264.9885 | 75264.9885
19.3 | CSSS Site setup/Site Traffic Management Plan Implemented; including Worker's shelters and mobile toilets for construiction site |  | 15303880.998 | 0 | 14997803.378 | 0 |  | 50176.659 | 49173.1258 |  |  |  | 1530388.0998 | 0 | 5017.6659 |  | 20%
19.4 | CSSS Implementation at 20% Completion |  | 7651940.499 | 0 | 7498901.689 | 0 |  | 25088.3295 | 24586.5629 |  |  |  | 153038.81 | 0 | 501.7666 |  | 10%
19.5 | CSSS Implementation at 40% Completion |  | 7651940.499 | 0 | 7498901.689 | 0 |  | 25088.3295 | 24586.5629 |  |  |  | 459116.4299 | 0 | 1505.2998 |  | 10%
19.6 | CSSS Implementation at 60% Completion |  | 7651940.499 | 0 | 7498901.689 | 0 |  | 25088.3295 | 24586.5629 |  |  |  | 306077.62 | 0 | 1003.5332 |  | 10%
19.7 | CSSS Implementation at 100% Completion |  | 7651940.499 | 0 | 7498901.689 | 0 |  | 25088.3295 | 24586.5629 |  |  |  | 153038.81 | 0 | 501.7666 |  | 10%
20 | Envronmental Management and Monitoring Plan (EMP) Implementation | L/S | 28972676.36 |  | 28393222.8328 | 0 | Raise as PO-3 Now (Progress Payment) | 94992.3815 | 93092.5339
20.1 | EMP approved |  | 2897267.636 | 0 | 2839322.2833 | 0 |  | 9499.2382 | 9309.2534 | 57945.3527 | 0 | 189.9848 |  |  |  |  | 10% |  |  | 9499.2382 | 9499.2382
20.2 | EMP Implementation at 25% Completed |  | 6518852.181 | 0 | 6388475.1374 | 0 |  | 21373.2858 | 20945.8201 |  |  |  | 153038.81 | 0 | 501.7666 |  | 22.5% |  | 22.5
20.3 | EMP Implementation at 50% Completed |  | 6518852.181 | 0 | 6388475.1374 | 0 |  | 21373.2858 | 20945.8201 |  |  |  | 579453.5272 | 0 | 1899.8476 |  | 22.5%
20.4 | EMP Implementation at 75% Completed |  | 6518852.181 | 0 | 6388475.1374 | 0 |  | 21373.2858 | 20945.8201 |  |  |  | 57945.3527 | 0 | 189.9848 |  | 22.5%
20.5 | EMP Implementation at 100% Completed |  | 6518852.181 | 0 | 6388475.1374 | 0 |  | 21373.2858 | 20945.8201 |  |  |  | 130377.0436 | 0 | 427.4657 |  | 22.5%
21 | Waste Management - General Site | L/S | 67448011.75 |  | 66099051.515 | 0 | Raise as PO-3 Now (Progress Payment) | 221141.0221 | 216718.2017
21.1 | At 2.5% Overall Project Completion |  | 1686200.2938 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 | 33724.0059 | 0 | 110.5705 |  |  |  |  | 2.5% | 2.5% | 2.5%
21.2 | At 5% Overall Project Completion |  | 1686200.2938 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 | 33724.0059 | 0 | 110.5705 |  |  |  |  | 2.5% | 5% | 2.5%
21.3 | At 7.5% Overall Project Completion |  | 1686200.2937 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 | 33724.0059 | 0 | 110.5705 |  |  |  |  | 2.5% | 7.5% | 2.5%
21.4 | At 10% Overall Project Completion |  | 1686200.2938 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 | 33724.0059 | 0 | 110.5705 |  |  |  |  | 2.5% | 10% | 2.5%
21.5 | At 12.5% Overall Project Completion |  | 1686200.2937 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 | 33724.0059 | 0 | 110.5705 |  |  |  |  | 2.5% | 12.5% | 2.5%
21.6 | At 15% Overall Project Completion |  | 1686200.2937 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 | 33724.0059 | 0 | 110.5705 |  |  |  |  | 2.5% | 15% | 2.5%
21.7 | At 17.5% Overall Project Completion |  | 1686200.2937 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 | 33724.0059 | 0 | 110.5705 |  |  |  |  | 2.5% | 17.5% | 2.5%
21.8 | At 20% Overall Project Completion |  | 1686200.2938 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 | 33724.0059 | 0 | 110.5705 |  |  |  |  | 2.5% | 20% | 2.5%
21.9 | At 22.5% Overall Project Completion |  | 1686200.2937 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 2.5% | 22.5% | 2.5%
21.10 | At 25% Overall Project Completion |  | 1686200.2937 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 2.5% | 25% | 2.5%
21.11 | At 30% Overall Project Completion |  | 3372400.5875 | 0 | 3304952.5757 | 0 |  | 11057.0511 | 10835.9101 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 5% | 30% | 5%
21.12 | At 35% Overall Project Completion |  | 3372400.5875 | 0 | 3304952.5757 | 0 |  | 11057.0511 | 10835.9101 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 5% | 35% | 5%
21.13 | At 40% Overall Project Completion |  | 3372400.5875 | 0 | 3304952.5758 | 0 |  | 11057.0511 | 10835.9101 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 5% | 40% | 5%
21.14 | At 45% Overall Project Completion |  | 3372400.5875 | 0 | 3304952.5757 | 0 |  | 11057.0511 | 10835.9101 |  |  |  | 67448.0118 | 0 | 221.141 |  | 5% | 45% | 5%
21.15 | At 50% Overall Project Completion |  | 3372400.5875 | 0 | 3304952.5757 | 0 |  | 11057.0511 | 10835.9101 |  |  |  | 67448.0118 | 0 | 221.141 |  | 5% | 50% | 5%
21.16 | At 55% Overall Project Completion |  | 3372400.5875 | 0 | 3304952.5758 | 0 |  | 11057.0511 | 10835.9101 |  |  |  | 67448.0118 | 0 | 221.141 |  | 5% | 55% | 5%
21.17 | At 60% Overall Project Completion |  | 3372400.5875 | 0 | 3304952.5757 | 0 |  | 11057.0511 | 10835.9101 |  |  |  | 67448.0118 | 0 | 221.141 |  | 5% | 60% | 5%
21.18 | At 65% Overall Project Completion |  | 3372400.5875 | 0 | 3304952.5758 | 0 |  | 11057.0511 | 10835.9101 |  |  |  | 67448.0118 | 0 | 221.141 |  | 5% | 65% | 5%
21.19 | At 70% Overall Project Completion |  | 3372400.5875 | 0 | 3304952.5757 | 0 |  | 11057.0511 | 10835.9101 |  |  |  | 67448.0118 | 0 | 221.141 |  | 5% | 70% | 5%
21.20 | At 72.5% Overall Project Completion |  | 1686200.2938 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 |  |  |  | 67448.0118 | 0 | 221.141 |  | 2.5% | 72.5% | 2.5%
21.21 | At 75% Overall Project Completion |  | 1686200.2938 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 |  |  |  | 67448.0118 | 0 | 221.141 |  | 2.5% | 75% | 2.5%
21.22 | At 77.5% Overall Project Completion |  | 1686200.2938 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 |  |  |  | 67448.0118 | 0 | 221.141 |  | 2.5% | 77.5% | 2.5%
21.23 | At 80% Overall Project Completion |  | 1686200.2938 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 2.5% | 80% | 2.5%
21.24 | At 82.5% Overall Project Completion |  | 1686200.2937 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 2.5% | 82.5% | 2.5%
21.25 | At 85% Overall Project Completion |  | 1686200.2938 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 2.5% | 85% | 2.5%
21.26 | At 87.5% Overall Project Completion |  | 1686200.2938 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 2.5% | 87.5% | 2.5%
21.27 | At 90% Overall Project Completion |  | 1686200.2938 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 2.5% | 90% | 2.5%
21.28 | At 92.5% Overall Project Completion |  | 1686200.2938 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 2.5% | 92.5% | 2.5%
21.29 | At 95% Overall Project Completion |  | 1686200.2937 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 2.5% | 95% | 2.5%
21.30 | At 97.5% Overall Project Completion |  | 1686200.2938 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 2.5% | 97.5% | 2.5%
2.131 | At 100% Overall Project Completion |  | 1686200.2938 | 0 | 1652476.2879 | 0 |  | 5528.5256 | 5417.955 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 2.5% | 100% | 2.5%
22 | General Signages (Sign Posts, Access Control Boards, notice Boards) | L/S | 10072751.46 |  | 9871296.4308 | 0 | Raise as PO-3 Now | 33025.4146 | 32364.9063
22.1 | General Signages at Phase2 Mobilisation for underground work and EPC Scope |  | 5036375.73 | 0 | 4935648.2154 | 0 |  | 16512.7073 | 16182.4532 |  |  |  | 33724.0059 | 0 | 110.5705 |  | 50%
22.2 | General Signages at Phase3 Mobilisation |  | 5036375.73 | 0 | 4935648.2154 | 0 |  | 16512.7073 | 16182.4532 | [7 empty] | 50%
23 | Project Site, Personnel Transport and Materials Security Cover during Security Operating Level (SOL) Red | L/S | 24615935.02 |  | 24123616.3196 | 0 | Raise as PO-3 Now (Progress Payment) | 80707.9837 | 79093.824
23.1 | At 2.5% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 | 12307.9675 | 0 | 40.354 |  |  |  |  | 2.5% | 2.5% | 2.5%
23.2 | At 5% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 | 12307.9675 | 0 | 40.354 |  |  |  |  | 2.5% | 5% | 2.5%
23.3 | At 7.5% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 | 12307.9675 | 0 | 40.354 |  |  |  |  | 2.5% | 7.5% | 2.5%
23.4 | At 10% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 | 12307.9675 | 0 | 40.354 |  |  |  |  | 2.5% | 10% | 2.5%
23.5 | At 12.5% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 | 12307.9675 | 0 | 40.354 |  |  |  |  | 2.5% | 12.5% | 2.5%
23.6 | At 15% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 | 12307.9675 | 0 | 40.354 |  |  |  |  | 2.5% | 15% | 2.5%
23.7 | At 17.5% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 | 12307.9675 | 0 | 40.354 |  |  |  |  | 2.5% | 17.5% | 2.5%
23.8 | At 20% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 | 12307.9675 | 0 | 40.354 |  |  |  |  | 2.5% | 20% | 2.5%
23.9 | At 22.5% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 |  |  |  | 12307.9675 | 0 | 40.354 |  | 2.5% | 22.5% | 2.5%
23.10 | At 25% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 |  |  |  | 12307.9675 | 0 | 40.354 |  | 2.5% | 25% | 2.5%
23.11 | At 30% Overall Project Completion |  | 1230796.751 | 0 | 1206180.816 | 0 |  | 4035.3992 | 3954.6912 |  |  |  | 12307.9675 | 0 | 40.354 |  | 5% | 30% | 5%
23.12 | At 35% Overall Project Completion |  | 1230796.751 | 0 | 1206180.816 | 0 |  | 4035.3992 | 3954.6912 |  |  |  | 12307.9675 | 0 | 40.354 |  | 5% | 35% | 5%
23.13 | At 40% Overall Project Completion |  | 1230796.751 | 0 | 1206180.816 | 0 |  | 4035.3992 | 3954.6912 |  |  |  | 12307.9675 | 0 | 40.354 |  | 5% | 40% | 5%
23.14 | At 45% Overall Project Completion |  | 1230796.751 | 0 | 1206180.816 | 0 |  | 4035.3992 | 3954.6912 |  |  |  | 24615.935 | 0 | 80.708 |  | 5% | 45% | 5%
23.15 | At 50% Overall Project Completion |  | 1230796.751 | 0 | 1206180.816 | 0 |  | 4035.3992 | 3954.6912 |  |  |  | 24615.935 | 0 | 80.708 |  | 5% | 50% | 5%
23.16 | At 55% Overall Project Completion |  | 1230796.751 | 0 | 1206180.816 | 0 |  | 4035.3992 | 3954.6912 |  |  |  | 24615.935 | 0 | 80.708 |  | 5% | 55% | 5%
23.17 | At 60% Overall Project Completion |  | 1230796.751 | 0 | 1206180.816 | 0 |  | 4035.3992 | 3954.6912 |  |  |  | 24615.935 | 0 | 80.708 |  | 5% | 60% | 5%
23.18 | At 65% Overall Project Completion |  | 1230796.751 | 0 | 1206180.816 | 0 |  | 4035.3992 | 3954.6912 |  |  |  | 24615.935 | 0 | 80.708 |  | 5% | 65% | 5%
23.19 | At 70% Overall Project Completion |  | 1230796.751 | 0 | 1206180.816 | 0 |  | 4035.3992 | 3954.6912 |  |  |  | 24615.935 | 0 | 80.708 |  | 5% | 70% | 5%
23.20 | At 72.5% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 |  |  |  | 24615.935 | 0 | 80.708 |  | 2.5% | 72.5% | 2.5%
23.21 | At 75% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 |  |  |  | 24615.935 | 0 | 80.708 |  | 2.5% | 75% | 2.5%
23.22 | At 77.5% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 |  |  |  | 24615.935 | 0 | 80.708 |  | 2.5% | 77.5% | 2.5%
23.23 | At 80% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 |  |  |  | 12307.9675 | 0 | 40.354 |  | 2.5% | 80% | 2.5%
23.24 | At 82.5% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 |  |  |  | 12307.9675 | 0 | 40.354 |  | 2.5% | 82.5% | 2.5%
23.25 | At 85% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 |  |  |  | 12307.9675 | 0 | 40.354 |  | 2.5% | 85% | 2.5%
23.26 | At 87.5% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 |  |  |  | 12307.9675 | 0 | 40.354 |  | 2.5% | 87.5% | 2.5%
23.27 | At 90% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 |  |  |  | 12307.9675 | 0 | 40.354 |  | 2.5% | 90% | 2.5%
23.28 | At 92.5% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 |  |  |  | 12307.9675 | 0 | 40.354 |  | 2.5% | 92.5% | 2.5%
23.29 | At 95% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 |  |  |  | 12307.9675 | 0 | 40.354 |  | 2.5% | 95% | 2.5%
23.30 | At 97.5% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 |  |  |  | 12307.9675 | 0 | 40.354 |  | 2.5% | 97.5% | 2.5%
23.31 | At 100% Overall Project Completion |  | 615398.3755 | 0 | 603090.408 | 0 |  | 2017.6996 | 1977.3456 |  |  |  | 12307.9675 | 0 | 40.354 |  | 2.5% | 100% | 2.5%
24 | Technical Coordination with Shell Design Office, Module VENDOR, Electrical Equipment OEMs, Utility Plant Vendors, MAC and Modular Piperack Fabricator | L/S | 133301289.26 | 225369 | 130635263.4748 | 223115.31 | Raise as PO-3 Now | 662422.4074 | 651427.6493
| Contractor Representation in Piperack Fabricator Yards in Lagos; from Rack assembly until delivery to site |  | 79980773.556 | 135221.4 | 78381158.0849 | 133869.186 |  | 397453.4444 | 390856.5896 |  |  |  | 12307.9675 | 0 | 40.354 |  | 60%
| Interface Management with Company and OEMS until equipment is installed |  | 26660257.852 | 45073.8 | 26127052.695 | 44623.062 |  | 132484.4815 | 130285.5299 |  |  |  | 12307.9675 | 0 | 40.354 |  | 20%
| Logistics Support to the OEMs on site |  | 26660257.852 | 45073.8 | 26127052.695 | 44623.062 |  | 132484.4815 | 130285.5299 |  |  |  | 2666025.7852 | 2253.69 | 10994.7581 |  | 20%
25 | Establishment of site temporary facilities (include but not limited to batching plant, workshops, offices, site clinic, stores, workers village for its own workforce, utilities, waste cell, electrical and instrumentation tooL/S calibration facilities, etc,). Note that this would include temporary acquisition of land. | L/S | 364890622.8 | 55927.97 | 357592810.344 | 55368.6903 | Raise as PO-3 Now | 1252290.6677 | 1227804.1341
25.1 | Site Preparation and Temporary Fencing for set up of site offices, batching plant, workshops, site clinic, stores, etc at the project site and hookup to Contractor provided utilities - electricity, water, compressed air -completed |  | 91222655.7 | 13981.9925 | 89398202.586 | 13842.1726 |  | 313072.6669 | 306951.0335 | 1824453.114 | 139.8199 | 6121.6334 |  |  |  |  | 25%
25.2 | Installation of site offices, living accommodation and Conference Room and Hookup to contractor provided utilities - water, electricity, sorrounding illumination - completed |  | 91222655.7 | 13981.9925 | 89398202.586 | 13842.1726 |  | 313072.6669 | 306951.0335 | 1824453.114 | 139.8199 | 6121.6334 |  |  |  |  | 25%
25.3 | Installation of site batching plant, workshops, site clinic, stores, camp for security men, etc. including telecommunication |  | 91222655.7 | 13981.9925 | 89398202.586 | 13842.1726 |  | 313072.6669 | 306951.0335 | 1824453.114 | 139.8199 | 6121.6334 |  |  |  |  | 25%
25.4 | Establishment of secured Materials Laydown areas, heavy equipment parking slots and light vehicles car parks |  | 91222655.7 | 13981.9925 | 89398202.586 | 13842.1726 |  | 313072.6669 | 306951.0335 | 1824453.114 | 139.8199 | 6121.6334 |  |  |  |  | 25%
26 | Establishment and Inspection of Temporary camp for a maximum of 40 COMPANY and Partners Representatives; complete with messing, laundary and office infrastructure | L/S | 119971160.34 | 202832.1 | 117571737.1332 | 200803.779 | Raise as PO-3 Now | 596180.1667 | 586284.8844
26.1 | Temporary Camp 25% Completed |  | 29992790.085 | 50708.025 | 29392934.2833 | 50200.9448 |  | 149045.0417 | 146571.2211 | 599855.8017 | 507.0802 | 2473.8206 |  |  | This will be based on the progress of work |  | 25%
26.2 | Temporary Camp 50% Completed |  | 29992790.085 | 50708.025 | 29392934.2833 | 50200.9448 |  | 149045.0417 | 146571.2211 | 599855.8017 | 507.0802 | 2473.8206 |  |  |  |  | 25%
26.3 | Temporary Camp 75% Completed |  | 29992790.085 | 50708.025 | 29392934.2833 | 50200.9448 |  | 149045.0417 | 146571.2211 | 599855.8017 | 507.0802 | 2473.8206 |  |  |  |  | 25%
26.4 | Temporary Camp 100% Completed |  | 29992790.085 | 50708.025 | 29392934.2833 | 50200.9448 |  | 149045.0417 | 146571.2211 | 599855.8017 | 507.0802 | 2473.8206 |  |  |  |  | 25%
27 | Premobilization inspection of light vehicles, fucklifts, flat bed trucks, low bed trucks, Module Transporters (50- 100tons, 100- 150 tons, 150- 200 tons), Safe-loaders (upto 15tons), Cranes (25tons, 50tons, 100tons, 150tons, 250tons and 450tons), hoists, pipe handlers, excavators, tool boxes, scaffolding materiaL/S, Piling Rigs, etc. Premobilization of road construction equipment and materiaL/S | L/S | 119971160.34 | 202832.1 | 117571737.1332 | 200803.779 | Divide into two (Phase-2 = 40%; Phase-3=60%) Raise all PO Now? | 596180.1667 | 586284.8844
27.1 | Premobilization inspection of light vehicles completed at Phase 2 |  | 23994232.068 | 40566.42 | 23514347.4266 | 40160.7558 |  | 119236.0333 | 117256.9769 |  |  |  | 599855.8017 | 507.0802 | 2473.8206 |  | 20%
27.2 | Premobilization inspection of light vehicles completed at Phase 3 |  | 35991348.102 | 60849.63 | 35271521.14 | 60241.1337 |  | 178854.05 | 175885.4653 |  |  |  | 599855.8017 | 507.0802 | 2473.8206 |  | 30%
27.3 | Premobilization inspection of heavy duty vehicles/ equipment completed at Phase 2 |  | 23994232.068 | 40566.42 | 23514347.4266 | 40160.7558 |  | 119236.0333 | 117256.9769 |  |  |  | 2399423.2068 | 2028.321 | 9895.2823 |  | 20%
27.4 | Premobilization inspection of heavy duty vehicles/ equipment completed at Phase 3 |  | 35991348.102 | 60849.63 | 35271521.14 | 60241.1337 |  | 178854.05 | 175885.4653 |  |  |  | 479884.6414 | 405.6642 | 1979.0565 |  | 30%
28 | NDT: Pre-mobilisation inspection and review of NDT sub-CONTRACTORs | L/S | 119971160.34 | 202832.1 | 117571737.1332 | 200803.779 | Raise as PO-3 Now | 596180.1667 | 586284.8844
28.1 | Premobilization NDT inspection at Phase 2 Completed |  | 35991348.102 | 60849.63 | 35271521.14 | 60241.1337 |  | 178854.05 | 175885.4653 |  |  |  | 479884.6414 | 405.6642 | 1979.0565 |  | 30%
28.2 | Premobilization NDT inspection at Phase 3 Completed |  | 83979812.238 | 141982.47 | 82300215.9932 | 140562.6453 |  | 417326.1167 | 410399.419 |  |  |  | 719826.962 | 608.4963 | 2968.5847 |  | 70%
30 | Premobilisation of Personnel, including fitness to work tests, minimum mandatory training for workers; PPEs | L/S | 119971160.34 | 202832.1 | 117571737.1332 | 200803.779 | Raise as PO-3 Now | 596180.1667 | 586284.8844
30.1 | HSSE Premobilization of personnel, including provision of all PPE 100% Completed for Phase 2 permanent work |  | 17995674.051 | 30424.815 | 17635760.57 | 30120.5668 |  | 89427.025 | 87942.7327 |  |  |  | 719826.962 | 608.4963 | 2968.5847 |  | 15%
30.2 | Premobilization of all personnel, including provision of all PPE 100% Completed for Phase 3 |  | 23994232.068 | 40566.42 | 23514347.4266 | 40160.7558 |  | 119236.0333 | 117256.9769 | 479884.6414 | 405.6642 | 1979.0565 |  |  |  |  | 20%
30.3 | HAZID and Bow-Tie Workshop Completed |  | 35991348.102 | 60849.63 | 35271521.14 | 60241.1337 |  | 178854.05 | 175885.4653 |  |  |  | 2399423.2068 | 2028.321 | 9895.2823 |  | 30% |  |  |  | 178854.05
30.4 | Mandatory Training/Induction_Phase 2 Completed |  | 17995674.051 | 30424.815 | 17635760.57 | 30120.5668 |  | 89427.025 | 87942.7327 |  |  |  | 359913.481 | 304.2481 | 1484.2924 |  | 15% |  |  |  | 89427.025
30.5 | Mandatory Training/Induction_Phase 3 Completed |  | 23994232.068 | 40566.42 | 23514347.4266 | 40160.7558 |  | 119236.0333 | 117256.9769 |  |  |  | 479884.6414 | 405.6642 | 1979.0565 |  | 20% |  |  |  | 119236.0333
32 | Construction Readiness Reviews | L/S | 119971160.34 | 202832.1 | 117571737.1332 | 200803.779 | Raise as PO-3 Now | 596180.1667 | 586284.8844
32.1 | Construction Readiness Reviews for Temporary Facilities |  | 35991348.102 | 60849.63 | 35271521.14 | 60241.1337 |  | 178854.05 | 175885.4653 | 719826.962 | 608.4963 | 2968.5847 |  |  |  |  | 30% |  |  |  | 178854.05
32.2 | Construction Readiness Reviews for Phase 2 |  | 35991348.102 | 60849.63 | 35271521.14 | 60241.1337 |  | 178854.05 | 175885.4653 |  |  |  | 479884.6414 | 405.6642 | 1979.0565 |  | 30% |  |  |  | 178854.05
32.3 | Construction Readiness Reviews for Phase 3 |  | 47988464.136 | 81132.84 | 47028694.8533 | 80321.5116 |  | 238472.0667 | 234513.9537 |  |  |  | 2399423.2068 | 2028.321 | 9895.2823 |  | 40% |  |  |  | 238472.0667
33 | Construction of temporary roads, access, material laydown areas, construction equipment park, timbering, concrete slabs, hard standing areas to facilitate materials handling and skid installation. | L/S | 20000000 | 15950 | 19600000 | 15790.5 | Raise as PO-3 Now | 81523.7705 | 80052.7951
33.1 | Temporary Road, access roads, etc - 50% progressed |  | 10000000 | 7975 | 9800000 | 7895.25 |  | 40761.8852 | 40026.3975 |  |  |  | 719826.962 | 608.4963 | 2968.5847 |  | 50%
33.2 | Temporary Road, access roads, etc - 100% progressed |  | 5000000 | 3987.5 | 4900000 | 3947.625 |  | 20380.9426 | 20013.1988 |  |  |  | 959769.2827 | 811.3284 | 3958.1129 |  | 25%
33.3 | Reintastement of Temporary Roads at completion |  | 5000000 | 3987.5 | 4900000 | 3947.625 |  | 20380.9426 | 20013.1988 |  |  |  | 400000 | 159.5 | 1470.9754 |  | 25%
34 | Survey and Setting Out of equipment locations and foundations | L/S | 9000000 | 10854 | 8820000 | 10745.46 | Raise as PO-3 Now | 40362.1967 | 39663.4928
34.1 | Survey and Setting Out of equipment locations and foundations at 25% Completed |  | 2250000 | 2713.5 | 2205000 | 2686.365 |  | 10090.5492 | 9915.8732 | 45000 | 27.135 | 174.676 |  |  |  |  | 25%
34.2 | Survey and Setting Out of equipment locations and foundations at 50% Completed |  | 2250000 | 2713.5 | 2205000 | 2686.365 |  | 10090.5492 | 9915.8732 |  |  |  | 100000 | 39.875 | 367.7439 |  | 25%
34.3 | Survey and Setting Out of equipment locations and foundations at 75% Completed |  | 2250000 | 2713.5 | 2205000 | 2686.365 |  | 10090.5492 | 9915.8732 |  |  |  | 180000 | 108.54 | 698.7039 |  | 25%
34.4 | Survey and Setting Out of equipment locations and foundations at 100% Completed |  | 2250000 | 2713.5 | 2205000 | 2686.365 |  | 10090.5492 | 9915.8732 |  |  |  | 45000 | 27.135 | 174.676 |  | 25%
| TOTAL Value of PO_3 |  | 3478107566.076 | 2568973.03 | 3408545414.7545 | 2543283.2997 |  | 13972604.3942 | 13718842.0366 | [7 empty] | 13972604.3942 |  |  | 1045978.6845 | 1529601.8235
[12 empty] | 101089.697 |  |  | 206865.807 | 63094071.1382 |  |  |  | 7.486% | 10.95%
|  |  |  | 13972604.3942 |  | 13718842.0366
253762.3576