## Summary
2019 PK 2 Materials
ENWHE PROJECT CALCULATED IDEC FOR 2019
TOTAL SAVINGS FROM CUSTOM DUTY AND VAT (FUSD)
Enwhe Pk 2 | 1367730.49
Total | 1367730.49
2020 Materisls
ENWHE PROJECT CALCULATED IDEC FOR 2020
TOTAL SAVINGS FROM CUSTOM DUTY AND VAT (FUSD)
Enwhe Pk 1 | 1198789.3141
Enwhe Pk 2 | 26180.7782
Total | 1224970.0923
Grand Total Pk1 & 2 (2019 & 2020) | 2592700.5823
Savings Banked in 2019 | 1500000
Estimated Savings in 2020 | 1092700.5823
Guestimated losses due to Custom Clearance delays following change to IDEC Approval process ($1k/day for 90days) | 90000
Revised Bankable Savings 2020 | 1002700.5823

## Pk1_2020 materials (hidden)
2020 Batch 1
S/N | Description | Qty | UOM | Ex-Works Price $ | Discount 0% | Price Ex-works (FOB) | Packaging 2% | Insurance 1% | Freight (ACTUAL) | A (Price CIF) | Custom HS code | HS CODE DESCRIPTION | Duty | VAT | Custom Duty Rate | VAT Rate | Levy on Custom Duty 7% | ETLS 0.5% of CIF | CISS 1% of FOB |  | REMARKS
1 | CARBON STEEL 2 | 1 | EA | 20316.77 | 0 | 20316.77 | 406.3354 | 203.1677 | 7000 | 27926.2731 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 1396.3137 | 2232.2346 | 97.742 | 139.6314 | 203.1677
2 | CARBON STEEL 3 | 1 | EA | 3957.48 | 0 | 3957.48 | 79.1496 | 39.5748 | 2200 | 6276.2044 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 313.8102 | 501.2203 | 21.9667 | 31.381 | 39.5748
3 | CARBON STEEL PIPE UK | 1 | EA | 50314.6 | 0 | 50314.6 | 1006.292 | 503.146 | 2793 | 54617.038 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 2730.8519 | 4373.6461 | 191.1596 | 273.0852 | 503.146
4 | CHEMICAL INJECTOR | 1 | EA | 130879.21 | 0 | 130879.21 | 2617.5842 | 1308.7921 | 2200 | 137005.5863 | 8481300000 | Check (nonreturn) valves | 10% |  | 13700.5586 | 0 | 959.0391 | 685.0279 | 1308.7921
5 | FENCE | 1 | EA | 103136.54 | 0 | 103136.54 | 2062.7308 | 1031.3654 | 4050 | 110280.6362 | 7318290000 | Screws, bolts, nuts, coach screws, screw Other | 20% | 7.5% | 22056.1272 | 10159.7596 | 1543.9289 | 551.4032 | 1031.3654
6 | FITTINGS 1 | 1 | EA | 23733.6 | 0 | 23733.6 | 474.672 | 237.336 | 2580 | 27025.608 | 7307920000 | Threaded elbows, bends and sleeves material not specified | 20% | 7.5% | 5405.1216 | 2488.6164 | 378.3585 | 135.128 | 237.336
7 | FITTINGS 2 | 1 | EA | 50756.3 | 0 | 50756.3 | 1015.126 | 507.563 | 2580 | 54858.989 | 7307920000 | Threaded elbows, bends and sleeves material not specified | 20% | 7.5% | 10971.7978 | 5053.5503 | 768.0258 | 274.2949 | 507.563
8 | FITTINGS 3 | 1 | EA | 30302.9 | 0 | 30302.9 | 606.058 | 303.029 | 2580 | 33791.987 | 7307920000 | Threaded elbows, bends and sleeves material not specified | 20% | 7.5% | 6758.3974 | 3112.1596 | 473.0878 | 168.9599 | 303.029
9 | FITTINGS 4 | 1 | EA | 97261.1 | 0 | 97261.1 | 1945.222 | 972.611 | 2185 | 102363.933 | 7307910000 | Flanges of material not specified | 20% | 7.5% | 20472.7866 | 9431.5684 | 1433.0951 | 511.8197 | 972.611
10 | FITTINGS 5 | 1 | EA | 333152.2 | 0 | 333152.2 | 6663.044 | 3331.522 | 2185 | 345331.766 | 7307920000 | Threaded elbows, bends and sleeves material not specified | 20% | 7.5% | 69066.3532 | 31821.8209 | 4834.6447 | 1726.6588 | 3331.522
11 | FLANGES 1 | 1 | EA | 48498.21 | 0 | 48498.21 | 969.9642 | 484.9821 | 2600 | 52553.1563 | 7307910000 | Flanges of material not specified | 20% | 7.5% | 10510.6313 | 4841.046 | 735.7442 | 262.7658 | 484.9821
12 | FLANGES 2 | 1 | EA | 545480.7 | 0 | 545480.7 | 10909.614 | 5454.807 | 8460 | 570305.121 | 7307210000 | Flanges of stainless steel | 20% | 7.5% | 114061.0242 | 52549.2562 | 7984.2717 | 2851.5256 | 5454.807
13 | FLANGES 3 | 1 | EA | 4500 | 0 | 4500 | 90 | 45 | 2100 | 6735 | 7307910000 | Flanges of material not specified | 20% | 7.5% | 1347 | 619.1224 | 94.29 | 33.675 | 45
14 | GASKET AND INSULATION | 1 | EA | 52614.3 | 0 | 52614.3 | 1052.286 | 526.143 | 2500 | 56692.729 | 4016930000 | Gaskets, washers and other seals | 10% | 7.5% | 5669.2729 | 4767.6343 | 396.8491 | 283.4636 | 526.143
15 | LEVEL TRANSMITTER | 1 | EA | 11289.7 | 0 | 11289.7 | 225.794 | 112.897 | 869.31 | 12497.701 | 9026100000 | Instruments and apparatus for measuring or checking the flow or level of liquids | 5% |  | 624.8851 | 0 | 43.742 | 62.4885 | 112.897
16 | MAMUAL SAMPLING SYSTEM | 1 | EA | 1323684.18 | 0 | 1323684.18 | 26473.6836 | 13236.8418 | 4200 | 1367594.7054 | 9031800000 | Other measuring or checking instruments, appliances and machines, not specified | 10% |  | 136759.4705 | 0 | 9573.1629 | 6837.9735 | 13236.8418
17 | OVERHEAD TANK | 1 | EA | 53093.64 | 0 | 53093.64 | 1061.8728 | 530.9364 | 3200 | 57886.4492 | 7309009000 | Other Reservoirs, tanks, vats and similar containers for any material not specified. | 10% | 8% | 5788.6449 | 5192.0534 | 405.2051 | 289.4322 | 530.9364
18 | PIPE 3 | 1 | EA | 490645.88 | 0 | 490645.88 | 9812.9176 | 4906.4588 | 16350 | 521715.2564 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 26085.7628 | 41785.6543 | 1826.0034 | 2608.5763 | 4906.4588
19 | PIPE 5 | 1 | EA | 134558.31 | 0 | 134558.31 | 2691.1662 | 1345.5831 | 3000 | 141595.0593 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 7079.753 | 11341.7965 | 495.5827 | 707.9753 | 1345.5831
20 | STUD BOLT | 1 | EA | 214296.61 | 0 | 214296.61 | 4285.9322 | 2142.9661 | 6510 | 227235.5083 | 7318150000 | Other screws and bolts, whether or not with their nuts or washers | 10% | 8% | 22723.5508 | 20386.3081 | 1590.6486 | 1136.1775 | 2142.9661
21 | VALVE 1 | 1 | EA | 862077.95 | 0 | 862077.95 | 17241.559 | 8620.7795 | 9700 | 897640.2885 | 8540890000 | Other valves and tube not specified | 10% | 8% | 89764.0289 | 80543.7424 | 6283.482 | 4488.2014 | 8620.7795
22 | VALVE 2 | 1 | EA | 1534483.37 | 0 | 1534483.37 | 30689.6674 | 15344.8337 | 7600 | 1588117.8711 | 8540890000 | Other valves and tube not specified | 10% | 8% | 158811.7871 | 142506.5525 | 11116.8251 | 7940.5894 | 15344.8337
23 | VALVE 3 | 1 | EA | 190574.75 | 0 | 190574.75 | 3811.495 | 1905.7475 | 2100 | 198391.9925 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified | 5% | 8% | 9919.5996 | 16952.2937 | 694.372 | 991.96 | 1905.7475
24 | VALVE INTERLOCK | 1 | EA | 57395.62 | 0 | 57395.62 | 1147.9124 | 573.9562 | 2000 | 61117.4886 | 8481300000 | Check (nonreturn) valves | 10% | 0% | 6111.7489 | 0 | 427.8224 | 305.5874 | 573.9562
[10 empty] | 0 |  |  |  |  | 748129.2782 | 450660.036
[9 empty] | TOTAL SAVINGS FROM CUSTOM DUTY AND VAT US$ | [5 empty] | 1198789.3141
[9 empty] | TOTAL SAVINGS FROM CUSTOM DUTY AND VAT IN NG₦ | [5 empty] | 432762942.4004 | EXCHANGE RATE USED IS $1 TO ₦361.00
2020 Batch 2
S/N | Description | PO Number | Ref. No. | Voyage No. | C/C Amount (CIF) | Location Site / Clearance / Sea(Air) | Qty | UOM | Ex-Works Price $ | Discount 0% | Price Ex-works (FOB) | Packaging 2% | Insurance 1% | Freight (ACTUAL) | A (Price CIF) | Custom HS code | HS CODE DESCRIPTION | Duty | VAT | Custom Duty Rate | VAT Rate | Levy on Custom Duty 7% | ETLS 0.5% of CIF | CISS 1% of FOB | Arrival Month/Year | Comment | Remark
1 | MAMUAL SAMPLING SYSTEM (2 YEAR SPARE PARTS) | OPAM1-KIM08P-01 | IDEC-A-06 |  | 37500 | Clearance
2 | INSRUMENTATION TUBING & FITTING | OPAM1-KIM28P | IDEC-10 | V-NG20003 | 331567.3287 | Site |  |  |  |  | 335012.03
3 | PIG SIGNALLER | OPAM1-KIM30P | GI3A-11 | V-NG20005 | 65391.531 | Site |  |  |  |  | 89399.17
3 | VALVE 2 | OPAM1-KPM07P-01 | IDEC-20 | V-NG20016 | 45444.9003 | Clearance |  |  |  |  | 44995.95 | [13 empty] | Arrived at the Port
4 | VALVE 2 | OPAM1-KPM07P-01 | IDEC-29 | V-NG20027(B) | 36944.3728 | Sea |  |  |  |  | 36460.57 | [13 empty] | In Transit | ETA: 22-Oct-20
5 | VALVES | OPAM1-KPM10P | IDEC-23 | V-NG20020 | 125632.5998 | Site |  |  |  |  | 190574.75 | [13 empty] | Arrived at the Port
5 | VALVES | OPAM1-KPM11P | IDEC-16 | V-NG20012 | 18268.586 | Clearance |  |  |  |  | 17975.44 | [13 empty] | Arrived at the Port
6 | END CLOSURE | OPAM1-KMM01P-01 | IDEC-21 | V-NG20023 | 104520 | Sea |  |  |  |  | 140887.5 | [13 empty] | Arrived at the Port
7 | PRESSURE GAUGE | OPAM1-KIM16P-01 | IDEC-A-02 | A-NG20052 | 10835.42 | Clearance |  |  |  |  | 10813.46 | [13 empty] | Arrived at the Port
7 | TEMPERATURE GAUGE WITH THERMOWELL | OPAM1-KIM20P-01 | IDEC-A-02 | A-NG20052 | 15091.32 | Clearance |  |  |  |  | 15093.94 | [13 empty] | Arrived at the Port
8 | TEMPERATURE TRANSMITTER | OPAM1-KIM21P-01 | IDEC-A-03 |  | 35658.9979 | Clearance |  |  |  |  | 33457.11 | [13 empty] | Arrived at the Port
9 | FITTING FOR PIG TRAPS | OPAM1-KPM02P-01 | [8 empty] | 36959.12 | [13 empty] | In Transit | ETA: 23-Oct-20
9 | FITTINGS 6 | OPAM1-KPM02P-01 | IDEC-30 | V-NG20029(A) | 96108.9741 | Sea |  |  |  |  | 60841.7 | [13 empty] | In Transit | ETA: 23-Oct-20
10 | FLANGE 4 | OPAM1-KPM03P-01 | IDEC-33 | V-NG20030 | 86411.9603 | Sea |  |  |  |  | 96763.63 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November
11 | VALVE 4 | OPAM1-KPM09P-01 | IDEC-16 | V-NG20012 | 19006.2733 | Clearance |  |  |  |  | 36460.57 | [13 empty] | Arrived at the Port
11 | HOSE COUPLING | OPAM1-KPM16P-01 | IDEC-A-04 | A-NG20053 | 50467.8438 | Clearance |  |  |  |  | 48521 | [13 empty] | Arrived at the Port
12 | INSTRUMENT CABLE TRAY AND GLAND | OPAM1-KIM26P-01 | IDEC-28 | V-NG20027(A) | 75321.5642 | Sea |  |  |  |  | 61909.33 | [13 empty] | In Transit | ETA: 15-Oct-20
13 | INSTRUMENT SUPPORT | OPAM1-KIM29P-01 | IDEC-31 | V-NG20029(B) | 102715.3316 | Sea |  |  |  |  | 136274.31 | [13 empty] | In Transit | ETA: 23-Oct-20
13 | MAJOR & MINOR BARREL FOR PIG TRAP | OPAM1-KMM02P-02 | IDEC-35 | V-NG20033 | 44188.8852 | Site |  |  |  |  | 39317.7 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
14 | MAJOR & MINOR BARREL FOR PIG TRAP | OPAM1-KMM02P-02 | IDEC-14 | V-NG20010 | 4404.7944 | Site |  |  |  |  | 1082.88
15 | CORROSION INHIBITION PACKAGE | OPAM1-KMM05P-01 | IDEC-32 | V-NG20031 | 1559905.73 | Sea |  |  |  |  | 882510 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November | May be delayed since Packing Inspection has been put on hold by SPDC
15 | NAG WELL EQUALIZATION INJECTION PACKAGE | OPAM1-KMM05P-02 | IDEC-32 | V-NG20031 | 671732.868 | Sea |  |  |  |  | 667450 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November | May be delayed since Packing Inspection has been put on hold by SPDC
16 | CABLE TRAY, and OUTLET & TRENCH 2 | OPAM1-KEM06P-01 | Not fixed | V-NG20034 |  | Sea |  |  |  |  | 44800 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
17 | LIGHTING SYSTEM | OPAM1-KEM07P-01 | Not fixed | V-NG20034 |  | Sea |  |  |  |  | 321800 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Lighting Pole; 20-Nov-2020, Cable Tie and Sealing Compound to arrive 22-Oct-2020 (Partial delivery)
17 | EARTHING SYSTEM | OPAM1-KEM08P-01 | [8 empty] | 41000 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Vessel arrangement ongoing
18 | OUTLET & TRENCH 1 | OPAM1-KEM09P-01 | IDEC-A-05 | A-NG20054 | 32501.7 | Clearance |  |  |  |  | 119400 | [13 empty] | Oct 2020 | ETA: 15-Oct-20
19 | DUAL CHANNEL TRANSFORMER | OPAM1-KEM12P-01 | IDEC-34 | V-NG20032 | 174686.688 | Sea |  |  |  |  | 170317.6 | [13 empty] | Oct 2020 | ETA: 31-Oct-20
19 | MAC SYSTEM/SIS/FGS SYSTEM | OPAM1-KIM01P-01 | [8 empty] | 2940862.75 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November | Packing Inspection on hold by COMPANY. Items currently stored at Vendor's Shop
20 | FIRE & GAS DETECTORS | OPAM1-KIM03P-01 | [8 empty] | 79722 | [13 empty] | Dec 2020 | Estimated arrival; Middle of December | Under Manufacturing
21 | WELLHEAD CONTROL PANEL | OPAM1-KIM05P-01 | [8 empty] | 1442716.76 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November | May be delayed since Packing Inspection has been put on hold by SPDC
21 | RELIEF VALVE AND BURSTING DISC | OPAM1-KIM14P-01 | [8 empty] | 58412.79 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Under Manufacturing
22 | SAND DETECTOR | OPAM1-KIM15P-01 | [8 empty] | 63787.71 | [13 empty] | Oct 2020 | Estimated arrival; End of October | Pre-Vessel arrangement proceedings
23 | CORROSION PROBE AND COUPON | OPAM1-KIM09P-01 | [8 empty] | 151216.72 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
23 | LEVEL TRANSMITTER | OPAM1-KIM19P-01 | [8 empty] | 14826.57 | [13 empty] | Oct 2020 | Estimated arrival; Middle of October
24 | RESTRICTION ORIFICE | OPAM1-KIM24P-01 | [8 empty] | 43128.41 | [13 empty] | Oct 2020 | Estimated arrival; Middle of October
25 | FITTINGS 7 | OPAM1-KPM02P-01 | [8 empty] | 4257.28 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
25 | PIPE 6 | OPAM1-KPM01P-01 | IDEC-18 | V-NG20014 | 277749.438 | Sea |  |  |  |  | 55331.76 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
26 | PIPE 7 | OPAM1-KPM01P-01 | IDEC-24 | V-NG20021 | 7957.477 | Clearance |  |  |  |  | 68678.4 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November | Pre-Vessel arrangement proceedings
27 | PIPE 8 | OPAM1-KPM01P-01 | IDEC-27 | V-NG20026 | 22794.6361 | Sea |  |  |  |  | 3350 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
27 | VALVE 5 | OPAM1-KPM06P-01 | [8 empty] | 196710.22 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
28 | GASKET AND INSULATION | OPAM1-KPM13P-01 | GI3A-12 | V-NG20006 | 24641.3199 | Site |  |  |  |  | 29954.51 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November | Pre-Vessel arrangement proceedings
29 | STUDBOLT | OPAM1-KPM14P-01 | [8 empty] | 54794.97 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Under Manufacturing
29 | CHOKE VALVE | OPAM1-KIM10P-01 | [8 empty] | 769094 | [13 empty] | Dec 2020 | Estimated arrival; Middle of December | Under Manufacturing
30 | PRESSURE & DIFF. PRESSURE TRANSMITTER | OPAM1-KIM17P-01 | [8 empty] | 105705.66 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November | Under Manufacturing
31 | LEVEL GAUGE | OPAM1-KIM18P-01 | [8 empty] | 59831.19 | [13 empty] | Dec 2020 | Estimated arrival; Middle of December | Under Manufacturing
31 | ULTRASONIC FLOWMETER | OPAM1-KIM22P-01 | [8 empty] | 493231.51 | [13 empty] | April 2021 | Estimated arrival; end of April March 2021 | Under Manufacturing
32 | VARIABLE AREA FLOWMETER | OPAM1-KIM23P-01 | [8 empty] | 47900 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
33 | INSTRUMENT CABLE | OPAM1-KIM25P-01 | [8 empty] | 310446.11 | [13 empty] | Dec 2020 | Estimated arrival; End of December | Under Manufacturing
33 | INSTRUMENT JUNCTION BOX & FRAME | OPAM1-KIM27P-01 | [8 empty] | 119408.01 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
34 | SHUTDOWN VALVE | OPAM1-KIM11P-01 | [8 empty] | 2284030 | [13 empty] | Jan 2021/ End of Mar 2021 | End of Jan 2021; Planned arrival of Valves required during CPF Shutdown | Under Manufacturing
35 | CONTROL VALVE | OPAM1-KIM13P-01 | [8 empty] | 277000 | [13 empty] | Feb 2021 | Estimated arrival; end of February 2021 | Under Manufacturing
35 | SURFACE HYDRAULIC SYSTEM | OPAM1-KIM06P-01 | [8 empty] | 1176074.16 | [13 empty] | Mar 2021 | Estimated arrival; end of March 2021 | Under Manufacturing
36 | PACKAGED SUBSTATION WITH TR, RMU ETC. | OPAM1-KEM02P-01 | [8 empty] | 4200000 | [13 empty] | Feb 2021 | Estimated arrival; end of February 2021 | Under Manufacturing
37 | TELECOMMUNICATION WITH TOWER | OPAM1-KEM05P-01 | [8 empty] | 3043266.34 | [13 empty] | Mar 2021 | Estimated arrival; end of March 2021 | Under Manufacturing
Note on C38: raymond: consist of all manual valves: KPM06,07,08,09,10&11P
Note on C39: raymond: consist of all manual valves: KPM06,07,08,09,10&11P
Note on B47: 2nd BOM
Note on B48: 2nd & 3rd BOM
Note on B49: Bronze Valve
Note on C49: raymond: consist of all manual valves: KPM06,07,08,09,10&11P
Note on B50: Main order and 2nd BOM
Note on B70: 3rd BOM
Note on B71: DSS Pipe for Hitech 2nd bom
Note on B72: DSS/SS of Acteon 2nd BOM
Note on B73: Hitech 3rd BOM
Note on B74: 2nd BOM & Blowdown with pending check valve
Note on B75: 2nd & 3rd BOM
Note on C75: raymond: consist of Gasket and Insulation (KPM12 & KPM13P)
Note on B76: Studbolt 2nd & 3rd

## 2019 Pk 2 materials
S/N | Description | Qty | UOM | Ex-Works Price € | Discount 0% | Price Ex-works (FOB) | Packaging 2% | Insurance 1% | Freight (ACTUAL) | A (Price CIF) | Custom HS code | HS CODE DESCRIPTION | Duty | VAT | Custom Duty Rate | VAT Rate | Levy on Custom Duty 7% | ETLS 0.5% of CIF | CISS 1% of FOB
1 | COMPOSITE CABLES | 46 | PK | 2970618.4 | 0 | 2970618.4 | 59412.368 | 29706.184 | 85219.45 | 3144956.402 | 8544700000 | Optical fibre cables | 5% | 7.5% | 157247.8201 | 251898.1902 | 11007.3474 | 15724.782 | 29706.184
2 | SPLICING / JUNCTION BOX | 51 | PK | 506487.3138 | 0 | 506487.3138 | 10129.7463 | 5064.8731 | 14529.83 | 536211.7632 | 8544700000 | Optical fibre cables | 5% | 7.5% | 26810.5882 | 42948.3768 | 1876.7412 | 2681.0588 | 5064.8731
3 | SPLITTER JOINTS FOR COMPOSITE CABLES | 5 | PK | 48486.7305 | 0 | 48486.7305 | 969.7346 | 484.8673 | 1390.96 | 51332.2924 | 8536700000 | Connectors for optical fibres, optical fibre bundles or cables | 20% | 7.5% | 10266.4585 | 4729.4199 | 718.6521 | 256.6615 | 484.8673
4 | DISCREET POWER CABLES | 2 | PK | 139296.8772 | 0 | 139296.8772 | 2785.9375 | 1392.9688 | 3996.07 | 147471.8535 | 8536700000 | Connectors for optical fibres, optical fibre bundles or cables | 20% | 7.5% | 29494.3707 | 13587.0869 | 2064.6059 | 737.3593 | 1392.9688
5 | 48 CORE DISCREET FIBER OPTIC CABLES | 2 | PK | 5059.08 | 0 | 5059.08 | 101.1816 | 50.5908 | 145.13 | 5355.9824 | 8544700000 | Optical fibre cables | 5% | 7.5% | 267.7991 | 428.9924 | 18.7459 | 26.7799 | 50.5908
6 | ADDITIONAL TYPE TEST | 2 | PK | 46800 | 0 | 46800 | 936 | 468 | 1342.57 | 49546.57 | 8536700000 | Connectors for optical fibres, optical fibre bundles or cables | 20% | 7.5% | 9909.314 | 4564.8952 | 693.652 | 247.7329 | 468
7 | ADDITIONAL COST FOR STEEL DRUMS FOR COMPOSITE cables | 45 | PK | 131625 | 0 | 131625 | 2632.5 | 1316.25 | 3775.99 | 139349.74 | 8536700000 | Connectors for optical fibres, optical fibre bundles or cables | 20% | 7.5% | 27869.948 | 12838.7687 | 1950.8964 | 696.7487 | 1316.25
8 | WELDING NECK FLANGES 12' 1500 RF ASME B16.5 | 5 | PK | 20943 | 0 | 20943 | 418.86 | 209.43 | 3906.1 | 25477.39 | 7307210000 | Flanges of stainless steel | 20% | 7.5% | 5095.478 | 2344.9776 | 356.6835 | 127.3869 | 209.43
9 | MONOLITHIC INSULATING JOINTS DN12' ANSI 900 | 4 | PK | 28255.5 | 0 | 28255.5 | 565.11 | 282.555 | 2592.25 | 31695.415 | 7307920000 | Threaded elbows, bends and sleeves material not specified | 20% | 7.5% | 6339.083 | 2918.9449 | 443.7358 | 158.4771 | 282.555
10 | CABLE LUGS (4 JOINTS) | 16 | PK | 1216.8 | 0 | 1216.8 | 24.336 | 12.168 | 111.6297 | 1364.9337 | 7307920000 | Threaded elbows, bends and sleeves material not specified | 20% | 7.5% | 272.9867 | 125.7017 | 19.1091 | 6.8247 | 12.168
11 | SPARK GAPS/SURGE ARRESTORS (1 FOR JOINT) | 4 | PK | 1708.2 | 0 | 1708.2 | 34.164 | 17.082 | 156.7098 | 1916.1558 | 7307920000 | Threaded elbows, bends and sleeves material not specified | 20% | 7.5% | 383.2312 | 176.4657 | 26.8262 | 9.5808 | 17.082
12 | TEST RING L = 500MM | 2 | PK | 702 | 0 | 702 | 14.04 | 7.02 | 64.35 | 787.41 | 7307920000 | Threaded elbows, bends and sleeves material not specified | 20% | 7.5% | 157.482 | 72.5155 | 11.0237 | 3.937 | 7.02
13 | STUDBOLTS 2' X 430MM ASTM | 1 | PK | 3353.6 | 0 | 3353.6 | 67.072 | 33.536 | 1860 | 5314.208 | 7318150000 | Other screws and bolts, whether or not with their nuts or washers | 10% | 7.5% | 531.4208 | 445.7201 | 37.1995 | 26.571 | 33.536
14 | ARTICLE NUMBER : 34 OD 323.8 x WT 13.03mm HOT | 37400 | PK | 4140554 | 0 | 4140554 | 82811.08 | 41405.54 | 857508.36 | 5122278.98 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 256113.949 | 409750.338 | 17927.9764 | 25611.3949 | 41405.54
15 | ARTICLE : 34 OD 323.8 x WT 14.74 MM HOT FINISHED | 4500 | PK | 560520 | 0 | 560520 | 11210.4 | 5605.2 | 116083.64 | 693419.24 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 34670.962 | 55469.2099 | 2426.9673 | 3467.0962 | 5605.2
[15 empty] | 565430.8913 | 802299.6035 | 39580.1624
[11 empty] | CUSTOM DUTY VALUE $ |  |  |  | 565430.89
[11 empty] | VAT VALUE $ |  |  |  | 802299.6
[9 empty] | CUSTOM DUTY VALUE plus VAT VALUUE IS F$ | [5 empty] | 1367730.49
[6 empty] | $1,367,730.49 CONVERTED TO NAIRA @$1 to ₦361 EXCHANGE RATE IS NGN | [8 empty] | 493750706.89

## Pk 2020 Materials -updated
S/N | Description | PO Number | Ref. No. | Voyage No. | C/C Amount (CIF) | Location Site / Clearance / Sea(Air) | Qty | UOM | Ex-Works Price $ | Discount 0% | Price Ex-works (FOB) | Packaging 2% | Insurance 1% | Freight (ACTUAL) | A (Price CIF) | Custom HS code | HS CODE DESCRIPTION | Duty | VAT | Custom Duty Rate | VAT Rate | Levy on Custom Duty 7% | ETLS 0.5% of CIF | CISS 1% of FOB | Arrival Month/Year | Comment | Remark
1 | CARBON STEEL 2 | OPAM1-KPM01P-01 | IDEC-08 | V-NG20001 | 22778.928 | Site | 1 | EA | 20316.77 | 0 | 20316.77 | 406.3354 | 203.1677 | 7000 | 27926.2731 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 1396.3137 | 2232.2346 | 97.742 | 139.6314 | 203.1677
2 | CARBON STEEL 3 | OPAM1-KPM01P-01 | IDEC-04 | V-NG19008 | 27454.8613 | Site | 1 | EA | 3957.48 | 0 | 3957.48 | 79.1496 | 39.5748 | 2200 | 6276.2044 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 313.8102 | 501.2203 | 21.9667 | 31.381 | 39.5748
3 | CARBON STEEL PIPE UK | OPAM1-KPM01P-01 | IDEC-01 | V-NG19009 | 51475.095 | Site | 1 | EA | 50314.6 | 0 | 50314.6 | 1006.292 | 503.146 | 2793 | 54617.038 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 2730.8519 | 4373.6461 | 191.1596 | 273.0852 | 503.146
4 | CHEMICAL INJECTOR | OPAM1-KPM15P-01 | IDEC-19 | V-NG20015 | 133744.8874 | Clearance | 1 | EA | 130879.21 | 0 | 130879.21 | 2617.5842 | 1308.7921 | 2200 | 137005.5863 | 8481300000 | Check (nonreturn) valves | 10% |  | 13700.5586 | 0 | 959.0391 | 685.0279 | 1308.7921
5 | FENCE | OPAM1-KCM01P-01 | IDEC-13 | V-NG20008 | 107722.4727 | Clearance | 1 | EA | 103136.54 | 0 | 103136.54 | 2062.7308 | 1031.3654 | 4050 | 110280.6362 | 7318290000 | Screws, bolts, nuts, coach screws, screw Other | 20% | 7.5% | 22056.1272 | 10159.7596 | 1543.9289 | 551.4032 | 1031.3654
6 | FITTINGS 1 | OPAM1-KPM02P-01 | IDEC-03 | V-NG19013 | 26445.168 | Site | 1 | EA | 23733.6 | 0 | 23733.6 | 474.672 | 237.336 | 2580 | 27025.608 | 7307920000 | Threaded elbows, bends and sleeves material not specified | 20% | 7.5% | 5405.1216 | 2488.6164 | 378.3585 | 135.128 | 237.336
7 | FITTINGS 2 | OPAM1-KPM02P-01 | IDEC-05 | V-NG19015 | 53602.9815 | Site | 1 | EA | 50756.3 | 0 | 50756.3 | 1015.126 | 507.563 | 2580 | 54858.989 | 7307920000 | Threaded elbows, bends and sleeves material not specified | 20% | 7.5% | 10971.7978 | 5053.5503 | 768.0258 | 274.2949 | 507.563
8 | FITTINGS 3 | OPAM1-KPM02P-01 | IDEC-07 | V-NG19018 | 33047.3145 | Site | 1 | EA | 30302.9 | 0 | 30302.9 | 606.058 | 303.029 | 2580 | 33791.987 | 7307920000 | Threaded elbows, bends and sleeves material not specified | 20% | 7.5% | 6758.3974 | 3112.1596 | 473.0878 | 168.9599 | 303.029
9 | FITTINGS 4 | OPAM1-KPM02P-01 | IDEC-09 | V-NG20002 | 99943.3305 | Site | 1 | EA | 97261.1 | 0 | 97261.1 | 1945.222 | 972.611 | 2185 | 102363.933 | 7307910000 | Flanges of material not specified | 20% | 7.5% | 20472.7866 | 9431.5684 | 1433.0951 | 511.8197 | 972.611
10 | FITTINGS 5 | OPAM1-KPM02P-01 | IDEC-11 | V-NG20004 | 337013.886 | Site | 1 | EA | 333152.2 | 0 | 333152.2 | 6663.044 | 3331.522 | 2185 | 345331.766 | 7307920000 | Threaded elbows, bends and sleeves material not specified | 20% | 7.5% | 69066.3532 | 31821.8209 | 4834.6447 | 1726.6588 | 3331.522
11 | FLANGES 1 | OPAM1-KPM03P-01 | IDEC-02 | V-NG19012 | 51353.7915 | Site | 1 | EA | 48498.21 | 0 | 48498.21 | 969.9642 | 484.9821 | 2600 | 52553.1563 | 7307910000 | Flanges of material not specified | 20% | 7.5% | 10510.6313 | 4841.046 | 735.7442 | 262.7658 | 484.9821
12 | FLANGES 2 | OPAM1-KPM03P-01 | IDEC-06 | V-NG19017 | 556710.4035 | Site | 1 | EA | 545480.7 | 0 | 545480.7 | 10909.614 | 5454.807 | 8460 | 570305.121 | 7307210000 | Flanges of stainless steel | 20% | 7.5% | 114061.0242 | 52549.2562 | 7984.2717 | 2851.5256 | 5454.807
13 | FLANGES 3 | OPAM1-KPM03P-01 | IDEC-15 | V-NG20011 | 6633 | Clearance | 1 | EA | 4500 | 0 | 4500 | 90 | 45 | 2100 | 6735 | 7307910000 | Flanges of material not specified | 20% | 7.5% | 1347 | 619.1224 | 94.29 | 33.675 | 45
14 | GASKET AND INSULATION | OPAM1-KPM12P-01 | GI3A-12 | V-NG20006 | 30748.5516 | Site | 1 | EA | 52614.3 | 0 | 52614.3 | 1052.286 | 526.143 | 2500 | 56692.729 | 4016930000 | Gaskets, washers and other seals | 10% | 7.5% | 5669.2729 | 4767.6343 | 396.8491 | 283.4636 | 526.143
15 | LEVEL TRANSMITTER | OPAM1-KIM19P-01 | IDEC-A-01 | A-NG20018 | 12219.8051 | Clearance | 1 | EA | 11289.7 | 0 | 11289.7 | 225.794 | 112.897 | 869.31 | 12497.701 | 9026100000 | Instruments and apparatus for measuring or checking the flow or level of liquids | 5% |  | 624.8851 | 0 | 43.742 | 62.4885 | 112.897
16 | MAMUAL SAMPLING SYSTEM | OPAM1-KIM08P-01 | IDEC-25 | V-NG20024 | 1334523.6009 | Clearance | 1 | EA | 1323684.18 | 0 | 1323684.18 | 26473.6836 | 13236.8418 | 4200 | 1367594.7054 | 9031800000 | Other measuring or checking instruments, appliances and machines, not specified | 10% |  | 136759.4705 | 0 | 9573.1629 | 6837.9735 | 13236.8418
17 | MAMUAL SAMPLING SYSTEM (2 YEAR SPARE PARTS) | OPAM1-KIM08P-01 | IDEC-A-06 |  | 37500 | Clearance
18 | INSRUMENTATION TUBING & FITTING | OPAM1-KIM28P | IDEC-10 | V-NG20003 | 331567.3287 | Site |  |  |  |  | 335012.03
19 | PIG SIGNALLER | OPAM1-KIM30P | GI3A-11 | V-NG20005 | 65391.531 | Site |  |  |  |  | 89399.17
20 | OVERHEAD TANK | OPAM1-KMM07P-01 | GI3A-14 | V-NG20017 | 56575.1082 | Clearance | 1 | EA | 53093.64 | 0 | 53093.64 | 1061.8728 | 530.9364 | 3200 | 57886.4492 | 7309009000 | Other Reservoirs, tanks, vats and similar containers for any material not specified. | 10% | 8% | 5788.6449 | 5192.0534 | 405.2051 | 289.4322 | 530.9364
21 | PIPE 3 | OPAM1-KPM01P-01 | IDEC-12 | V-NG20007 | 509530.8594 | Clearance | 1 | EA | 490645.88 | 0 | 490645.88 | 9812.9176 | 4906.4588 | 16350 | 521715.2564 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 26085.7628 | 41785.6543 | 1826.0034 | 2608.5763 | 4906.4588
22 | PIPE 5 | OPAM1-KPM01P-01 | IDEC-17 | V-NG20013 | 138246.1015 | Clearance | 1 | EA | 134558.31 | 0 | 134558.31 | 2691.1662 | 1345.5831 | 3000 | 141595.0593 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 7079.753 | 11341.7965 | 495.5827 | 707.9753 | 1345.5831
23 | STUD BOLT | OPAM1-KPM14P-01 | IDEC-22 | V-NG20019 | 221910.643 | Clearance | 1 | EA | 214296.61 | 0 | 214296.61 | 4285.9322 | 2142.9661 | 6510 | 227235.5083 | 7318150000 | Other screws and bolts, whether or not with their nuts or washers | 10% | 8% | 22723.5508 | 20386.3081 | 1590.6486 | 1136.1775 | 2142.9661
24 | VALVE 1 | OPAM1-KPM06P-01 | IDEC-20 | V-NG20016 | 1504348.8866 | Clearance | 1 | EA | 862077.95 | 0 | 862077.95 | 17241.559 | 8620.7795 | 9700 | 897640.2885 | 8540890000 | Other valves and tube not specified | 10% | 8% | 89764.0289 | 80543.7424 | 6283.482 | 4488.2014 | 8620.7795
25 | VALVE 2 | OPAM1-KPM07P-01 | IDEC-16 | V-NG20012 | 838861.9804 | Clearance | 1 | EA | 1534483.37 | 0 | 1534483.37 | 30689.6674 | 15344.8337 | 7600 | 1588117.8711 | 8540890000 | Other valves and tube not specified | 10% | 8% | 158811.7871 | 142506.5525 | 11116.8251 | 7940.5894 | 15344.8337
26 | VALVE 2 | OPAM1-KPM07P-01 | IDEC-20 | V-NG20016 | 45444.9003 | Clearance |  |  |  |  | 44995.95 | [13 empty] | Arrived at the Port
27 | VALVE 2 | OPAM1-KPM07P-01 | IDEC-29 | V-NG20027(B) | 36944.3728 | Sea |  |  |  |  | 36460.57 | [13 empty] | In Transit | ETA: 22-Oct-20
28 | VALVE 3 | OPAM1-KPM08P-01 | IDEC-23 | V-NG20020 | 68005.5239 | Site | 1 | EA | 190574.75 | 0 | 190574.75 | 3811.495 | 1905.7475 | 2100 | 198391.9925 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified | 5% | 8% | 9919.5996 | 16952.2937 | 694.372 | 991.96 | 1905.7475
29 | VALVES | OPAM1-KPM10P | IDEC-23 | V-NG20020 | 125632.5998 | Site |  |  |  |  | 190574.75 | [13 empty] | Arrived at the Port
30 | VALVES | OPAM1-KPM11P | IDEC-16 | V-NG20012 | 18268.586 | Clearance |  |  |  |  | 17975.44 | [13 empty] | Arrived at the Port
31 | VALVE INTERLOCK | OPAM1-KPM17P-01 | IDEC-26 | V-NG20022 | 61560.0489 | Clearance | 1 | EA | 57395.62 | 0 | 57395.62 | 1147.9124 | 573.9562 | 2000 | 61117.4886 | 8481300000 | Check (nonreturn) valves | 10% | 0% | 6111.7489 | 0 | 427.8224 | 305.5874 | 573.9562
32 | END CLOSURE | OPAM1-KMM01P-01 | IDEC-21 | V-NG20023 | 104520 | Sea |  |  |  |  | 140887.5 | [13 empty] | Arrived at the Port
33 | PRESSURE GAUGE | OPAM1-KIM16P-01 | IDEC-A-02 | A-NG20052 | 10835.42 | Clearance |  |  |  |  | 10813.46 | [13 empty] | Arrived at the Port
34 | TEMPERATURE GAUGE WITH THERMOWELL | OPAM1-KIM20P-01 | IDEC-A-02 | A-NG20052 | 15091.32 | Clearance |  |  |  |  | 15093.94 | [13 empty] | Arrived at the Port
35 | TEMPERATURE TRANSMITTER | OPAM1-KIM21P-01 | IDEC-A-03 |  | 35658.9979 | Clearance |  |  |  |  | 33457.11 | [13 empty] | Arrived at the Port
36 | FITTING FOR PIG TRAPS | OPAM1-KPM02P-01 | [8 empty] | 36959.12 | [13 empty] | In Transit | ETA: 23-Oct-20
37 | FITTINGS 6 | OPAM1-KPM02P-01 | IDEC-30 | V-NG20029(A) | 96108.9741 | Sea |  |  |  |  | 60841.7 | [13 empty] | In Transit | ETA: 23-Oct-20
38 | FLANGE 4 | OPAM1-KPM03P-01 | IDEC-33 | V-NG20030 | 86411.9603 | Sea |  |  |  |  | 96763.63 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November
39 | VALVE 4 | OPAM1-KPM09P-01 | IDEC-16 | V-NG20012 | 19006.2733 | Clearance |  |  |  |  | 36460.57 | [13 empty] | Arrived at the Port
40 | HOSE COUPLING | OPAM1-KPM16P-01 | IDEC-A-04 | A-NG20053 | 50467.8438 | Clearance |  |  |  |  | 48521 | [13 empty] | Arrived at the Port
41 | INSTRUMENT CABLE TRAY AND GLAND | OPAM1-KIM26P-01 | IDEC-28 | V-NG20027(A) | 75321.5642 | Sea |  |  |  |  | 61909.33 | [13 empty] | In Transit | ETA: 15-Oct-20
42 | INSTRUMENT SUPPORT | OPAM1-KIM29P-01 | IDEC-31 | V-NG20029(B) | 102715.3316 | Sea |  |  |  |  | 136274.31 | [13 empty] | In Transit | ETA: 23-Oct-20
43 | MAJOR & MINOR BARREL FOR PIG TRAP | OPAM1-KMM02P-02 | IDEC-35 | V-NG20033 | 44188.8852 | Site |  |  |  |  | 39317.7 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
44 | MAJOR & MINOR BARREL FOR PIG TRAP | OPAM1-KMM02P-02 | IDEC-14 | V-NG20010 | 4404.7944 | Site |  |  |  |  | 1082.88
45 | CORROSION INHIBITION PACKAGE | OPAM1-KMM05P-01 | IDEC-32 | V-NG20031 | 1559905.73 | Sea |  |  |  |  | 882510 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November | May be delayed since Packing Inspection has been put on hold by SPDC
46 | NAG WELL EQUALIZATION INJECTION PACKAGE | OPAM1-KMM05P-02 | IDEC-32 | V-NG20031 | 671732.868 | Sea |  |  |  |  | 667450 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November | May be delayed since Packing Inspection has been put on hold by SPDC
47 | CABLE TRAY, and OUTLET & TRENCH 2 | OPAM1-KEM06P-01 | Not fixed | V-NG20034 |  | Sea |  |  |  |  | 44800 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
48 | LIGHTING SYSTEM | OPAM1-KEM07P-01 | Not fixed | V-NG20034 |  | Sea |  |  |  |  | 321800 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Lighting Pole; 20-Nov-2020, Cable Tie and Sealing Compound to arrive 22-Oct-2020 (Partial delivery)
49 | EARTHING SYSTEM | OPAM1-KEM08P-01 | [8 empty] | 41000 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Vessel arrangement ongoing
50 | OUTLET & TRENCH 1 | OPAM1-KEM09P-01 | IDEC-A-05 | A-NG20054 | 32501.7 | Clearance |  |  |  |  | 119400 | [13 empty] | Oct 2020 | ETA: 15-Oct-20
51 | DUAL CHANNEL TRANSFORMER | OPAM1-KEM12P-01 | IDEC-34 | V-NG20032 | 174686.688 | Sea |  |  |  |  | 170317.6 | [13 empty] | Oct 2020 | ETA: 31-Oct-20
52 | MAC SYSTEM/SIS/FGS SYSTEM | OPAM1-KIM01P-01 | [8 empty] | 2940862.75 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November | Packing Inspection on hold by COMPANY. Items currently stored at Vendor's Shop
53 | FIRE & GAS DETECTORS | OPAM1-KIM03P-01 | [8 empty] | 79722 | [13 empty] | Dec 2020 | Estimated arrival; Middle of December | Under Manufacturing
54 | WELLHEAD CONTROL PANEL | OPAM1-KIM05P-01 | [8 empty] | 1442716.76 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November | May be delayed since Packing Inspection has been put on hold by SPDC
55 | RELIEF VALVE AND BURSTING DISC | OPAM1-KIM14P-01 | [8 empty] | 58412.79 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Under Manufacturing
56 | SAND DETECTOR | OPAM1-KIM15P-01 | [8 empty] | 63787.71 | [13 empty] | Oct 2020 | Estimated arrival; End of October | Pre-Vessel arrangement proceedings
57 | CORROSION PROBE AND COUPON | OPAM1-KIM09P-01 | [8 empty] | 151216.72 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
58 | LEVEL TRANSMITTER | OPAM1-KIM19P-01 | [8 empty] | 14826.57 | [13 empty] | Oct 2020 | Estimated arrival; Middle of October
59 | RESTRICTION ORIFICE | OPAM1-KIM24P-01 | [8 empty] | 43128.41 | [13 empty] | Oct 2020 | Estimated arrival; Middle of October
60 | FITTINGS 7 | OPAM1-KPM02P-01 | [8 empty] | 4257.28 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
61 | PIPE 6 | OPAM1-KPM01P-01 | IDEC-18 | V-NG20014 | 277749.438 | Sea |  |  |  |  | 55331.76 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
62 | PIPE 7 | OPAM1-KPM01P-01 | IDEC-24 | V-NG20021 | 7957.477 | Clearance |  |  |  |  | 68678.4 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November | Pre-Vessel arrangement proceedings
63 | PIPE 8 | OPAM1-KPM01P-01 | IDEC-27 | V-NG20026 | 22794.6361 | Sea |  |  |  |  | 3350 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
64 | VALVE 5 | OPAM1-KPM06P-01 | [8 empty] | 196710.22 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
65 | GASKET AND INSULATION | OPAM1-KPM13P-01 | GI3A-12 | V-NG20006 | 24641.3199 | Site |  |  |  |  | 29954.51 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November | Pre-Vessel arrangement proceedings
66 | STUDBOLT | OPAM1-KPM14P-01 | [8 empty] | 54794.97 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Under Manufacturing
67 | CHOKE VALVE | OPAM1-KIM10P-01 | [8 empty] | 769094 | [13 empty] | Dec 2020 | Estimated arrival; Middle of December | Under Manufacturing
68 | PRESSURE & DIFF. PRESSURE TRANSMITTER | OPAM1-KIM17P-01 | [8 empty] | 105705.66 | [13 empty] | Nov 2020 | Estimated arrival; Middle of November | Under Manufacturing
69 | LEVEL GAUGE | OPAM1-KIM18P-01 | [8 empty] | 59831.19 | [13 empty] | Dec 2020 | Estimated arrival; Middle of December | Under Manufacturing
#REF! | VARIABLE AREA FLOWMETER | OPAM1-KIM23P-01 | [8 empty] | 47900 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
#REF! | INSTRUMENT CABLE | OPAM1-KIM25P-01 | [8 empty] | 310446.11 | [13 empty] | Dec 2020 | Estimated arrival; End of December | Under Manufacturing
#REF! | INSTRUMENT JUNCTION BOX & FRAME | OPAM1-KIM27P-01 | [8 empty] | 119408.01 | [13 empty] | Nov 2020 | Estimated arrival; End of November | Pre-Vessel arrangement proceedings
[15 empty] | 0 |  |  |  |  | 748129.2782 | 450660.036
[14 empty] | TOTAL SAVINGS FROM CUSTOM DUTY AND VAT US$ | [5 empty] | 1198789.3141
[14 empty] | TOTAL SAVINGS FROM CUSTOM DUTY AND VAT IN NG₦ | [5 empty] | 432762942.4004 | EXCHANGE RATE USED IS $1 TO ₦361.00
Note on C15: raymond: consist of Gasket and Insulation (KPM12 & KPM13P)
Note on C25: raymond: consist of all manual valves: KPM06,07,08,09,10&11P
Note on C26: raymond: consist of all manual valves: KPM06,07,08,09,10&11P
Note on C27: raymond: consist of all manual valves: KPM06,07,08,09,10&11P
Note on C28: raymond: consist of all manual valves: KPM06,07,08,09,10&11P
Note on C29: raymond: consist of all manual valves: KPM06,07,08,09,10&11P
Note on C32: raymond: consist of all manual valves: KPM06,07,08,09,10&11P
Note on B38: 2nd BOM
Note on B39: 2nd & 3rd BOM
Note on B40: Bronze Valve
Note on C40: raymond: consist of all manual valves: KPM06,07,08,09,10&11P
Note on B41: Main order and 2nd BOM
Note on B61: 3rd BOM
Note on B62: DSS Pipe for Hitech 2nd bom
Note on B63: DSS/SS of Acteon 2nd BOM
Note on B64: Hitech 3rd BOM
Note on B65: 2nd BOM & Blowdown with pending check valve
Note on B66: 2nd & 3rd BOM
Note on C66: raymond: consist of Gasket and Insulation (KPM12 & KPM13P)
Note on B67: Studbolt 2nd & 3rd

## Pk 2_2020 materials
2020 Batch 1
S/N | Description | Qty | UOM | Ex-Works Price $ | Discount 0% | Price Ex-works (FOB) | Packaging 2% | Insurance 1% | Freight (ACTUAL) | A (Price CIF) | Custom HS code | HS CODE DESCRIPTION | Duty | VAT | Custom Duty Rate | VAT Rate | Levy on Custom Duty 7% | ETLS 0.5% of CIF | CISS 1% of FOB
1 | 12'' x 15.9 MM INDUCTION BENDS | 1 | EA | 3935.12 | 0 | 3935.12 | 78.7024 | 39.3512 | 2143.4 | 6196.5736 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 309.8287 | 494.8818 | 21.688 | 30.9829 | 39.3512
2 | 12'' x 15.9 MM INDUCTION BENDS - 12 DEGREES, OD | 4 | EA | 14850.4 | 0 | 14850.4 | 297.008 | 148.504 | 8088.78 | 23384.692 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 1169.2346 | 1867.59 | 81.8464 | 116.9235 | 148.504
3 | 12'' x 15.9 MM INDUCTION BENDS - 18 DEGREES | 1 | EA | 3845.94 | 0 | 3845.94 | 76.9188 | 38.4594 | 2094.82 | 6056.1382 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 302.8069 | 483.6661 | 21.1965 | 30.2807 | 38.4594
[18 empty] | 0 | 0
[15 empty] | 1781.8702 | 2846.138 |  | 0 | 0
[9 empty] | TOTAL SAVINGS FROM CUSTOM DUTY AND VAT US$ | [5 empty] | 4628.0082
[9 empty] | TOTAL SAVINGS FROM CUSTOM DUTY AND VAT IN NG₦ | [5 empty] | 1670710.9527 | EXCHANGE RATE USED IS $1 TO ₦361.00
2020 Batch 2
| 2020 Batch 2 |  |  | Custom HS code
D | INDUCTION BENDS
S/N | Description | Qty | UOM | Ex-Works Price $ | Discount 0% | Price Ex-works (FOB) | Packaging 2% | Insurance 1% | Freight (ACTUAL) | A (Price CIF) | Custom HS code | HS CODE DESCRIPTION | Duty | VAT | Custom Duty Rate | VAT Rate | Levy on Custom Duty 7% | ETLS 0.5% of CIF | CISS 1% of FOB
1 | IND BEND 323.8X17.5R=1619 MM 45 X65 | 8 | PK | 27089.6 | 0 | 27089.6 | 541.792 | 270.896 | 4735.69 | 32637.978 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 1631.8989 | 2611.3647 | 114.2329 | 163.1899 | 270.896
2 | IND BEND 323.8X17.5R=1619 MM 90 X65 | 9 | PK | 34402.32 | 0 | 34402.32 | 688.0464 | 344.0232 | 6014.07 | 41448.4596 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 2072.423 | 3316.2913 | 145.0696 | 207.2423 | 344.0232
3 | IND BEND 323.8X17.5R=1619 MM 82 X65 | 1 | PK | 3331.02 | 0 | 3331.02 | 66.6204 | 33.3102 | 582.31 | 4013.2606 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 200.663 | 321.101 | 14.0464 | 20.0663 | 33.3102
4 | IND BEND 323.8X17.5R=1619 MM 10 X65 | 1 | PK | 2632.97 | 0 | 2632.97 | 52.6594 | 26.3297 | 460.28 | 3172.2391 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 158.612 | 253.8109 | 11.1028 | 15.8612 | 26.3297
5 | IND BEND 323.8X17.5R=1619 MM 78 X65 | 1 | PK | 3292.24 | 0 | 3292.24 | 65.8448 | 32.9224 | 575.54 | 3966.5472 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 198.3274 | 317.3634 | 13.8829 | 19.8327 | 32.9224
6 | IND BEND 323.8X17.5R=1619 MM 66 X65 | 2 | PK | 6351.8 | 0 | 6351.8 | 127.036 | 63.518 | 1110.39 | 7652.744 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 382.6372 | 612.2961 | 26.7846 | 38.2637 | 63.518
7 | IND BEND 323.8X17.5R=1619 MM 63 X65 | 1 | PK | 3146.81 | 0 | 3146.81 | 62.9362 | 31.4681 | 550.11 | 3791.3243 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 189.5662 | 303.3439 | 13.2696 | 18.9566 | 31.4681
8 | IND BEND 323.8X17.5R=1619 MM 48 X65 | 1 | PK | 3001.38 | 0 | 3001.38 | 60.0276 | 30.0138 | 524.69 | 3616.1114 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 180.8056 | 289.3251 | 12.6564 | 18.0806 | 30.0138
9 | IND BEND 323.8X17.5R=1619 MM 42 X65 | 1 | PK | 2943.21 | 0 | 2943.21 | 58.8642 | 29.4321 | 514.52 | 3546.0263 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 177.3013 | 283.7176 | 12.4111 | 17.7301 | 29.4321
10 | IND BEND 323.8X17.5R=1619 MM 39 X65 | 1 | PK | 2914.13 | 0 | 2914.13 | 58.2826 | 29.1413 | 509.44 | 3510.9939 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 175.5497 | 280.9146 | 12.2885 | 17.555 | 29.1413
11 | IND BEND 323.8X17.5R=1619 MM 29 X65 | 1 | PK | 2817.18 | 0 | 2817.18 | 56.3436 | 28.1718 | 492.49 | 3394.1854 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 169.7093 | 271.5688 | 11.8796 | 16.9709 | 28.1718
12 | IND BEND 323.8X17.5R=1619 MM 25 X65 | 1 | PK | 2778.4 | 0 | 2778.4 | 55.568 | 27.784 | 485.71 | 3347.462 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 167.3731 | 267.8304 | 11.7161 | 16.7373 | 27.784
13 | IND BEND 323.8X17.5R=1619 MM 20 X65 | 1 | PK | 2729.92 | 0 | 2729.92 | 54.5984 | 27.2992 | 477.23 | 3289.0476 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 164.4524 | 263.1567 | 11.5117 | 16.4452 | 27.2992
14 | IND BEND 323.8X17.5R=1619 MM 18 X65 | 1 | PK | 2710.53 | 0 | 2710.53 | 54.2106 | 27.1053 | 473.84 | 3265.6859 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 163.2843 | 261.2875 | 11.4299 | 16.3284 | 27.1053
15 | IND BEND 323.8X17.5R=1619 MM 15 X65 | 1 | PK | 2681.45 | 0 | 2681.45 | 53.629 | 26.8145 | 468.76 | 3230.6535 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 161.5327 | 258.4846 | 11.3073 | 16.1533 | 26.8145
16 | IND BEND 323.8X17.5R=1619 MM 8 X65 | 2 | PK | 5227.16 | 0 | 5227.16 | 104.5432 | 52.2716 | 913.79 | 6297.7648 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 314.8882 | 503.8842 | 22.0422 | 31.4888 | 52.2716
17 | 12'' x 15.9 MM INDUCTIONBENDS - 35 DEGREES, OD 323.8 x WT 15.90 MM STEEL PIPES | 1 |  | 3935.12 | 0 | 3935.12 | 78.7024 | 39.3512 | 2143.4 | 6196.5736 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 309.8287 | 494.8818 | 21.688 | 30.9829 | 39.3512
18 | 12'' x 15.9 MM INDUCTION BENDS - 12 DEGREES, OD 323.8 x WT 15.90 MM STEEL PIPES | 4 |  | 14850.4 | 0 | 14850.4 | 297.008 | 148.504 | 8088.78 | 23384.692 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 1169.2346 | 1867.59 | 81.8464 | 116.9235 | 148.504
19 | 12'' x 15.9 MM INDUCTION BENDS - 18 DEGREES, OD 323.8 x WT 15.90 MM STEEL PIPES | 1 |  | 3845.94 | 0 | 3845.94 | 76.9188 | 38.4594 | 2094.82 | 6056.1382 | 7304190000 | Other Line pipe of a kind used for oil or gas pipelines not specified. | 5% | 7.5% | 302.8069 | 483.6661 | 21.1965 | 30.2807 | 38.4594
[15 empty] | 8290.8944 | 13261.8787 | 580.3626
[12 empty] | CUSTOM DUTY VALUE $ |  |  | 8290.89
[12 empty] | VAT VALUE $ |  |  | 13261.88
[10 empty] | CUSTOM DUTY VALUE plus VAT VALUUE IS F$ |  |  |  |  | 21552.77
$21,552.77 CONVERTED TO NAIRA @$1 to ₦361 EXCHANGE RATE IS NGN = 7,780,549.97

## Pk1 2021 materials
S/N | Description | PO Number | Ref. No. | Voyage No. | C/C Amount (CIF) | Location Site / Clearance / Sea(Air) | Qty | UOM | Ex-Works Price $ | Discount 0% | Price Ex-works (FOB) | Packaging 2% | Insurance 1% | Freight (ACTUAL) | A (Price CIF) | Custom HS code | HS CODE DESCRIPTION | Duty | VAT | Custom Duty Rate | VAT Rate | Levy on Custom Duty 7% | ETLS 0.5% of CIF | CISS 1% of FOB | Arrival Month/Year | Comment | Remark
1 | ULTRASONIC FLOWMETER | OPAM1-KIM22P-01 | [8 empty] | 493231.51 | [13 empty] | April 2021 | Estimated arrival; end of April March 2021 | Under Manufacturing
2 | SHUTDOWN VALVE | OPAM1-KIM11P-01 | [8 empty] | 2284030 | [13 empty] | Jan 2021/ End of Mar 2021 | End of Jan 2021; Planned arrival of Valves required during CPF Shutdown | Under Manufacturing
3 | CONTROL VALVE | OPAM1-KIM13P-01 | [8 empty] | 277000 | [13 empty] | Feb 2021 | Estimated arrival; end of February 2021 | Under Manufacturing
4 | SURFACE HYDRAULIC SYSTEM | OPAM1-KIM06P-01 | [8 empty] | 1176074.16 | [13 empty] | Mar 2021 | Estimated arrival; end of March 2021 | Under Manufacturing
5 | PACKAGED SUBSTATION WITH TR, RMU ETC. | OPAM1-KEM02P-01 | [8 empty] | 4200000 | [13 empty] | Feb 2021 | Estimated arrival; end of February 2021 | Under Manufacturing
6 | TELECOMMUNICATION WITH TOWER | OPAM1-KEM05P-01 | [8 empty] | 3043266.34 | [13 empty] | Mar 2021 | Estimated arrival; end of March 2021 | Under Manufacturing